## Blank Template
A1 Group Risk Assessment Form
Removal of Pipework from Chatham Place Development
Date: |  | 2019-01-01 | [8 empty] | Security and Retention Period: Standard
Assessment Type : |  | Re-Assessment | Conducted By: |  | Sean Whittle H&S Advisor | [5 empty] | Version 1.0
A | B | C | D | E | F | G | H | I | J | K | L
Ref No. | Activity / Task / Equipment | Controls currently in place | Threat / Hazard | Frequency | Value 1-5 | Vulnerability | Value 1-5 | Impact | Value 1-5 | Risk Value FXHXJ | Corrective Action requirement
1 | Park A1 Group Vehicle | Park vehicle outside Chatham Place Development site. Ensure area is clear of hazards prior to exiting vehicle | No issues as area is non pedestrian. | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
2 | Exit Vehicle wearing Hi visibility Jacket | Hi visibility jackets provided and correct PPE to be worn at all times | No wearing jackets not being seen by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
3 | Remove high pressure hose from vehicle and take to ground floor by rodding eye | Ensure area is clear of workers prior to removal and do so using correct manual handling techniques | Injuring back whilst lifting equipment incorrectly | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
4 | Ensure barriers are erected by A1 Group vehicle and around alley tower | Cones and safety barriers are erected | Injuring back whilst lifting equipment incorrectly | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
5 | Climb onto alley tower and ensure securely attached using correct PPE prior to commencing work | working at heights - employees have had training on working at heights and use the correct PPE | Falling from tower onto concrete floor | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
6 | Place High pressure hose into rodding eye and release water into pipework but not under high pressure | Working with high pressure equipment. High pressure motor will not be on just using equipment to release water into pipework. | Working with water can make area slippery. Barriers are erected and correct PPE worn at all times | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
7 | Once 200 gallons of water have been released into pipework on both ground floor and basement remove hose and place equipment back in A1 Group vehicle | Working with water can make area slippery. Barriers are erected and correct PPE worn at all times | Working with water can make area slippery. Injury to persons is they fall or slip | Very unlikely | 1 | Developed Management process in place | 2 | Easy workaround / Minor injury | 2 | 4 | Not required
8 | Place camera system into pipework on both ground floor and basement and ensure clear of debris | Working at heights on alley tower. Correct PPE to be worn at all times | Falling from tower onto concrete floor | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
9 | Once clear of debris cut pipework into 1 metre sections using hacksaw | All A1 employees have undertaken correct training in using sharp equipment and will wear appropriate PPE i.e. Gloves | Damage to hands. | Very unlikely | 1 | Developed Management process in place | 2 | Easy workaround / Minor injury | 2 | 4 | Not required
10 | Once sections cut on both floors then remove retaining brackets form ceiling and then pass piece of pipework to another A1 Group employee to dispose of in skip | Once cut and retaining brackets removed the A1 Group employee will pass in a controlled manner the section of pipework to a fellow A1 Group employee. A1 Group employee will wear correct PPE including hard hat, safety shoes and gloves | Heavy item falling on heads whist being removed and also pipework will have sharp edge which may cut persons | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
11 | Once all pipework has been safely removed into skip place all barriers and equipment into A1 Group vehicle securely | Safely place in skip provided using gloves to ensure sharp edges on pipework don’t cut hands | Cut from sharp edges or being hit by pipework whilst being transporting to skip area | Very unlikely | 1 | Developed Management process in place | 2 | Easy workaround / Minor injury | 2 | 4 | Not required
12 | Exit site in vehicle | Ensure road is clear of moving traffic using van signals to exit pavement in a controlled manner | Not using correct signals and vehicle being hit by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
Value | Frequency | Vulnerability | Impact |  |  |  | Risk Value | Meaning | Requirement
5 | Certain | Unmanaged | Catastrophic / Death |  |  |  | 40+ | Very High Risk | Improvement required
4 | Likely | Reactive Management | SLA compromised / Permanent Disability |  |  |  | 31 to 40 | High Risk | Improvement required
3 | May Happen | Workaround Planned | Workaround possible / Serious injury |  |  |  | 21 to 30 | Medium Risk | Improvement opportunity
2 | Unlikely | Developed Management | Easy Workaround / Minor injury |  |  |  | 11 to 20 | Low Risk | No action required
1 | Very unlikely | Negligible | Negligible |  |  |  | 1 to 10 | Very Low Risk | No action required
Note on D7: Type either of the following: a) Initial b) Re-Assessment