## Blank Template
A1 Group Risk Assessment Form
Pumping Station Installation and Pipe Laying Client Site
Date: |  | 2019-01-01 | [8 empty] | Security and Retention Period: Standard
Assessment Type : |  | Re-Assessment | Conducted By: |  | Sean Whittle H&S Advisor | [5 empty] | Version 1.0
A | B | C | D | E | F | G | H | Impact | J | K | L
Ref No. | Activity / Task / Equipment | Controls currently in place | Threat / Hazard | Frequency | Value 1-5 | Vulnerability | Value 1-5 | Impact | Value 1-5 | Risk Value FXHXJ | Corrective Action requirement
1 | Park A1 Group Vehicle | Park A1 vehicle away from traffic flow and close to working area. Exit A1 vehicle incontrolled and safe manner | Being hit by other vehicles on campus | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
3 | Exit Vehicle wearing Hi visability Jacket | Hi visability jackets provided and worn at all times | No wearing jackets not being seen by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
2 | Place out safety barriers around working area | Safety barriers erected around area to be excavated. Warning signs will be used if required | Manual handling of barriers | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
| Unload 1.5 tonne excavtor from A1 Group vehicle | Only trained A1 employee can operate the excavator | Being hit by excavator | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
4 | Digging hole to install new pumping station | Only trained A1 employee can operate the excavator | Being hit by excavator | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
| Place pumping station into hole and fill with water and place concrete around pumping station | Use excavator to lift pumping station into hole | being hit by the pumping station whilst being manoverved into hole | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
6 | Place all debris away from working area | Place away from working area safe working distance away | Trip hazard - falling over loose material not stored away from working area correctly | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
| Dig trench from pumping station to main sewer system | Only trained A1 employee can operate the excavator | Being hit by excavator | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
| Conduct work in 25 metre sections and ensure CAT scan is conducted prior to digging trench | Trained A1 Group employee conducts CAT scan before trench is dug using excavator | hitting a main utility ie GAS / Water / Electric | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
8 | Filling trench with clean shingle | Materials will be safly placed in ecavated area in a controlled manner | Manual handling of materials | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
9 | Lifing pipe into trench | Pipe will be placed in trench by two A1 employees in controlled and safe manner | Manual handling damage to back twisting and turning | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
10 | Filling area around and on top of pipe with shingle | All filling will be conducted by using excavator | Being hit by excavator | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
11 | Using compactor to compact shingle in trench | Compactor will only be used by trained A1 employees. A1 employes wear appropriate PPE at all times | Crush injury to feet | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
12 | Placing top soil in trench to fill hole to existing level of surface area | Material will be lifted carefully into trench. Top soile will be compacted in hole using compactor. Only trained A1 employees will use compactor and appropriate PPE will be worn at all times | Crush from heavy compactor equipment | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
13 | Store barriers on vehicle | Lift barriers onto vehcicle using correct manual handling techniques and ensure stored safely in vehicle | Lifting heavy items - damage to back/damage to feet | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
14 | Exit site in vehicle | Ensure road is clear of moving traffic using van signals to exit area in a controlled manner | Not using correct signals and vehicle being hit by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
Value | Frequency | Vulnerability | Impact |  |  |  | Risk Value | Meaning | Requirement
5 | Certain | Unmanaged | Catastrophic / Death |  |  |  | 40+ | Very High Risk | Improvement required
4 | Likely | Reactive Management | SLA compromised / Permanent Disability |  |  |  | 31 to 40 | High Risk | Improvement required
3 | May Happen | Workaround Planned | Workaround possible / Serious injury |  |  |  | 21 to 30 | Medium Risk | Improvement opportunity
2 | Unlikely | Developed Management | Easy Workaround / Minor injury |  |  |  | 11 to 20 | Low Risk | No action required
1 | Very unlikely | Negligible | Negligible |  |  |  | 1 to 10 | Very Low Risk | No action required
Note on D7: Type either of the following: a) Initial b) Re-Assessment