## Blank Template
A1 Group Risk Assessment Form
Removal of Old Bromide Recover Plant - Kodak Pinewood Studios
Date: |  | 2019-01-01
Site Location | [10 empty] | Security and Retention Period: Standard
Assessment Type : |  | Re-Assessment | Conducted By: |  | Garry Webb | [5 empty] | Version 1.0
A | B | C | D | E | F | G | H | I | J | K | L
Ref No. | Activity / Task / Equipment | Controls currently in place | Threat / Hazard | Frequency | Value 1-5 | Vulnerability | Value 1-5 | Impact | Value 1-5 | Risk Value FXHXJ | Corrective Action requirement
1 | Park A1 Group Vehicle at clients site | Park vehicle at client site near empty old bromide plant and engage hand brake and switch off engine. Ensure area is clear of hazards prior to exiting. Ensure hazards on vehilce are on whilst parked | Possible employees working in collection area although area is non pedestrian. Care required as other vehicles may be in operation in collection area | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 5 | 10 | Not required
3 | Exit Vehicle wearing Hi visability Jacket and correct PPE | Hi visability jackets provided and worn at all times | Not wearing jackets not being seen by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
4 | Using hiab crane on A1 vehicle | Only trained A1 Group employees are able to use the crane | Being hit by the crane | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
5 | Lifting empty bromide recover plant from from site onto A1 vehicle using hiab crane | place straps from hiab crane under and around old bromide plant and ensure secure to hiab crane and plant prior to lift. Ensure area is clear of other employees prior to movment of plant | Operation is manual and non manual | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 3 | 6 | Not required
6 | Place bromide recover plant onto back of A1 Group vehicle and secure with straping. Check strapsare secure before leaving site. | All A1 employees have undertaken training on ensuring safety staps are attached and secured correctly to both item and A1 Group vehicle | Plant falling off A1 Group vehicle | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
8 | Exit site in vehicle | Ensure road is clear of moving traffic using van signals to exit pstore in a controlled manner | Not using correct signals and vehicle being hit by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
Value | Frequency | Vulnerability | Impact |  |  |  | Risk Value | Meaning | Requirement
5 | Certain | Unmanaged | Catastrophic / Death |  |  |  | 40+ | Very High Risk | Improvement required
4 | Likely | Reactive Management | SLA compromised / Permanent Disability |  |  |  | 31 to 40 | High Risk | Improvement required
3 | May Happen | Workaround Planned | Workaround possible / Serious injury |  |  |  | 21 to 30 | Medium Risk | Improvement opportunity
2 | Unlikely | Developed Management | Easy Workaround / Minor injury |  |  |  | 11 to 20 | Low Risk | No action required
1 | Very unlikely | Negligible | Negligible |  |  |  | 1 to 10 | Very Low Risk | No action required
Note on D8: Type either of the following: a) Initial b) Re-Assessment