## Blank Template
A1 Group Risk Assessment Form
Removal of Water and Silt from client site
Date: |  | 2019-01-01 | [8 empty] | Security and Retention Period: Standard
Assessment Type : |  | Re Assessment | Conducted By: |  | Sean Whittle H&S Advisor | [5 empty] | Version 1.0
A | B | C | D | E | F | G | H | I | J | K | L
Ref No. | Activity / Task / Equipment | Controls currently in place | Threat / Hazard | Frequency | Value 1-5 | Vulnerability | Value 1-5 | Impact | Value 1-5 | Risk Value FXHXJ | Corrective Action requirement
1 | Place Welfare unit close to the entrance to the site using a forklift | Ensure forklift only operated by trained member of A1 staff and ensure area is clear at all times whilst placing into postion | Other A1 employees being hit by the forklift | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
2 | Place three 6000 gallon tanks along side secuity fencing close to the lagoon | Remove using forklift truck only operated by trained member of A1 staff ensure area is clear of people and obstacles at all times | Other A1 employees being hit by the forklift | Very unlikely | 1 | Developed Management process in place | 3 | Negligible | 1 | 2 | Not required
3 | Exit Vehicles at all times wearing Hi visibility Jacket | Hi visibility jackets provided and worn at all times whilst on site. Supervisor / Secuity to monitor at all times to ensure compliance | Not wearing jackets not being seen by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
4 | Electricity | Ensure BAA isolate all electical power to the lagoon prior to commencment of any work. A1 to obtain sign for action complete prior to start | A1 employees cutting through high voltage cable | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
5 | Water | Ensure BAA isolate water supply into lagoon prior to commencment of any work. A1 to obtain sign off for action complete prior to start | High pressure water hitting A1 employee | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
6 | Entering the lagoon via the ramp situated at the near side of the lagoon | Ensure Heras fencing erected alongside slo[e into the lagoon to prevent employees, excavator and other vehicles from slipping to the lagoon whilst silt removal in operation. All vehicles are well maintained and will maintian safe and controlled speed whilst in operation | Excavator of fork lift falling into the lagoon | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
7 | Tanker Operatives entering site to remove waste from tanks | All tanker drivers must wear correct PPE at all times whilst on site. Not required to work near the lagoon so they will not need to be secured to the tanker | Being hit by other tankers in operation | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
8 | Removal of plastic balls from lagoon | Balls will be removed using forklift and mesh scoop (allows warter to drain off) . Forklift to only be operated by trained A1 employees. Erect heras fencing to house balls whilst lagoon being drained. Sandbags will be placed at bottom of fencing to prevent balls escaping from holding area | Forklift slipping into lagoon | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
9 | Remove pumping equipment from A1 vehicle | Remove using correct manual handling procedures. Ensure area is clear of employees prior to removal. Erect Heras fencing around equipment. | Damage to limbs / backs if not lifted correctly | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
10 | Setting up pumping equipment | Ensure trip hazards are kept to a minimum and if necessary place signage near exposed hoses. Ensure spillage kits are by pumps at all times | Negligible | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
11 | Remove 7.5 tonne excavator / Fork lift from A1 vehicle | Only trained A1 Group employees are able to use the excavator and forklift. Ensure erect Heras fencing around Excavtor / forklift when not in use. | Being hit by the excavator | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
12 | Ensure safe working environment near and in lagoon | Working near water ensure A1 employees are wearing hi vis jackets, waders, life jackets, hearing protection and gloves whilst in and around lagoon at all times. Erect Heras fencing alongside edge of ramp to prevent employees falling into lagoon | Drowning if fall in basin | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
13 | Remove water and silt from lagoon | Using pumps and cell dredger to remove water into nearby tanks and then transferred into tankers to be disposed securely off site. Erect Heras fecing around the pumps. | Negligible | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
14 | Remove remaining silt from basin | Using the excavator to drag silt to safe area to be pumped to tanker or transferred to lorry for removal off site. Ensure all A1 employee wear correct PPE at all times | Negligible | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
15 | Using high pressure cleaner to jet vacuum lagoon floor | Ensure all A1 employees using hoses are fully trained and wearing correct PPE - Hi Vis jackets, waders, life jackets, gloves and goggles | Being hit by lose material in eyes | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
16 | Using brooms and mops to clean basin floor | Ensure all A1 employees are wearing correct PPE - Hi vis jackets,waders, life jackets, gloves, ear protectors and goggles | Possible strains to limbs / damage to back | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
17 | Exiting site in A1 vehicles | Ensure exiting area is clear of moving traffic and material then use van signals to exit site in a controlled manner | Not using correct signals and vehicle being hit by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
Value | Frequency | Vulnerability | Impact |  |  |  | Risk Value | Meaning | Requirement
5 | Certain | Unmanaged | Catastrophic / Death |  |  |  | 40+ | Very High Risk | Improvement required
4 | Likely | Reactive Management | SLA compromised / Permanent Disability |  |  |  | 31 to 40 | High Risk | Improvement required
3 | May Happen | Workaround Planned | Workaround possible / Serious injury |  |  |  | 21 to 30 | Medium Risk | Improvement opportunity
2 | Unlikely | Developed Management | Easy Workaround / Minor injury |  |  |  | 11 to 20 | Low Risk | No action required
1 | Very unlikely | Negligible | Negligible |  |  |  | 1 to 10 | Very Low Risk | No action required
Note on D7: Type either of the following: a) Initial b) Re-Assessment