## April 2019
A1 Group Health & Safety Meeting Minutes
2nd April 2019
Security and Retention Period: Standard
Meeting Date: Tuesday 2nd April 2019 - 11.00am Wokingham Depot | [6 empty] | Version 1.0
Attendees | Sean Whittle (H&S Advisor), Alan MacGregor - Transport Manager, Chloe Djemal - Office Manager Wokingham, Russell John Pike - Car Spares Manager
Laura White, Office Manager Loo Hire, Clive Owen - Senior Management, Garry Webb, Metal Recycling Manager, Spencer Morgan, Area Manager - Loo Hire Bridgend
Apologies | Michael Pike - Wet Waste Manager, Emily Russell, - Office Administrator
3. Accidents in previous month
Ref No | Open Date | Issue | Owner | Comment/Monthly update | ACTION | Closure Date | Closed
3.1 | 2015-03-24 | no issues to report | All | No accidents across the A1 Group during February / March |  | 2015-03-01 | Closed
3.2 | 2015-04-29 | Car Spars Yard - Accident to member of public | All | A member of the public, climbed on a vehicle in the racking despite numerous Site Rules posted around the site. He was attended to by Chloe Djemal a qualified First Aider, the patient sustained a head injury and an ambulance was called. - All persons visiting the Car Spares site will be issued with a leaflet outlining the site rules/Hi visibility jacket. CO to send leaflet to printers and then distribute to reception areas around site |  | 2015-04-01 | Closed
3.3 | 2015-04-29 | Employee Accident | All | Lukasz Dyskiewicz – Wet Waste Driver, punched himself in the eye after his hand slipped from a tool which he was using to tighten a union joint. |  | 2015-04-01 | Closed
3.4 | 2015-05-27 | 2 Accidents | All | DK hit head and Simon Smith twisted ankle on job neither required time off work. DK to speak to SS remind him to do visual RA when on jobs
3.5 | 2015-07-21 | 2 Accidents | All | 1. LS slipped off back off company vehicle and twisted ankle, attended Dr's and was signed off work. SW reminded all present to ensure all employees are reminded to risk assess areas when on back of company vehicles and also to climb down safely and in a controlled manner. 2. Member of the public whilst walking around the yard slipped over a car jack and bruised the side of her face no further medical attention was required - SW reminded Managers to ensure all equipment used in various operations is not left lying around when not used and stored away correctly. |  | 2015-07-01 | Closed
3.6 | 2015-09-22 | 3 Accidents | All | SH - Pipe hit in mouth. RS opened doors to van and some metal hit knocked him to the ground. BK involved in RTA and required medical treatment. All accidents recorded in the Accident book and no time off taken |  | 2015-09-01 | Closed
3.7 | 2015-11-10 | 2 Accidents | All | AR - caught finger on a tyre. Finger sprained. Accident not reported until following day and has been advised to seek medical advice. Member of the public was removing a spare part from a car in the car spares yard and moved some tyres to reach the part and the fence the tyres were holding up fell on him and cut his head - no treatment required |  | 2015-11-01 | Closed
3.8 | 2016-01-12 | 2 Accidents | All | Jim Ferris – Threw a piece of metal to the ground which bounced back and hit him in the face – Compression applied to cut and sent to AE – Stitches were applied to cut by AE. Daniel Collis – Cut his hand between the fingers on a circular saw, off site but on A1 Property, Taken straight to hospital for treatment.
3.9 | 2016-03-31 | 2 Accidents | All | 1 visitor (oil tanker driver) broke two toes whilst collecting oil from the Wokingham site - allegedly stood on some plastic - ca we try and ensure areas are kept free from materials where possible. This was recorded in our accident book and the client was informed in order that they can investigate and record as necessary. All collection drivers must ensure they wear the appropriate PPE whilst on site. SS burnt arm after Acetylene pipe burst - no RIDDOR but 2 days absence.
3.11 | 2016-05-31 | 4 accidents | All | 3 in Loo Hire and 1 in Car Spares All recorded in Accident book and no time lost from business.
3.1 | 2016-03-31 | Reporting of Accidents | All | SW reminded Committee that ALL accidents need to be recorded in the Accident book. Once then employee returns to work or immediately following the accident the accident investigation form needs to be completed. Along with the WHY analysis. This will help us keep accurate data on accidents and we can then endure we take precautions to prevent re occurrence. It will also help in any possible insurance claims. SW will issue all documents to all committee members who must ensure ALL first aiders are made aware of this process.
3.12 | 2016-08-04 | 1 Accident | All | Dale the car Valeter hit his head on one of the Roll On Roll Off vehicles, he administered an ice pack and require no further first aid.
3.13 | 2016-10-26 | 2 Accidents | All | 23/08/16 - Chris Morse cut his ear when urinal unit being de-stacked, rinsed ear until bleeding stopped. 11/10/16 - Allan Seabourne slipped on the bottom deck of his truck and landed oddly causing a twisted ankle, no treatment at time and he worked the remainder of the week but now has been off work since 17th October.
3.14 | 2016-12-14 | 2 Accidents | All | SH, Wet Waste - on customer site, took hat off and got hit by manhole key, minor cut to head. GR, Loo Hire climbing ladder and broke wrist, in hospital. Will probably become a RIDDOR and must ensure correct documentation and procedure adhered to.
3.15 | 2017-02-22 | 2 Accidents recorded since last meeting | All | LS - Car Spares - Axle on a vehicle when being removed swung round and hit Luke on the back of his head. Reports were that Luke was knocked unconscious and that the car tipped over on the blades almost landing on Luke. He refused medical attention but took 2 days off to recover. Sarah Shephard put details in accident book. AG - Car Spares - Approached the 360 Grab vehicle to gain the attention of the Driver. The Driver of the grab was unaware of Adams’ presence and turned the machine. As it turn Adam was struck by the rear of it and knocked to the floor. He suffered a 6 inch gash to the scalp. First Aid was given to Adam and a Large dressing was applied with pressure to stop any bleeding. He was taken to A&E where they performed a CT Scan (all ok) and Adam was given 5 sutures and the remainder of the wound was glued
3.16 | 2017-05-24 | 2 Accidents recorded since last meeting | All | Car Spares - AM - hurt shoulder whilst pulling hose out of a drain. Loo Hire - MF loading Cross Urinal onto trailer and one corner not on the trailer properly and resulting in hitting MF in neck and resulted in 7 days off work VIPEE – Member of public injured at an event. This person was inebriated with Alcohol, First Aid was given and a witness has given details that backs A1 account of incident
3.16 | 2017-10-03 | 2 Accidents recorded since last meeting | All | Two Wet Waste Accidents - Wayne Bird cut finger through glove and Bruno Moreira hurt shoulder, Bruno went to hospital, both fine and no time off work.
3.16 | 2017-11-28 | 1 Accidents recorded since last meeting | All | Yard employee opened oil burner and slightly burnt side of face. No time off work and no hospital attention required
3.16 | 2018-01-30 | 4 Accidents recorded since last meeting | All | Wet Waste - Luke Vincent, working on customer site opening an access panel which has fallen off and hit him in the face, causing cut to bridge of nose, needed six stiches and glue at A & E. Car Spares - Marek Kaczmarczek WCS staff – While using a Crowbar, it slipped and the middle of the bar hit Marek on the head, First Aid was administered, after 1 hour bleeding was not completely stopped. Taken to A&E where they glued the wound. Marek returned to work the following day Car Spares - Christopher Stanmore Driver – Fell from front ladder of vehicle, approximately 6’ 7” in height. Injuries sustained were, Head injury, Collar Bone fracture and bruising with pain in lower limbs. Hospitalised and placed into induced Coma for approximately 8 days at John Radcliffe Hospital. Has now been moved to Wexham Park with the view of being released home with Rehabilitation going forward. RIDDOR notified immediately and H&S visited 24/7 site and our premises to inspect the vehicle. John the builder dislocated finger, just need the full details from him to record.
3.16 | 2018-02-27 | 0 accidents reported in February | All | Excellent result first month no accidents reported. | No Actions required
3.16 | 2018-04-04 | 0 accidents reported since February | All | Excellent result first month no accidents reported. | No Actions required
3.16 | 2018-05-01 | 0 accidents reported since March | All | Excellent result 2nd month no accidents reported. Following arecent Insurance Claim – SW said all reportable incidents however small must be logged to avoid future claims creating issues where there is nothing on file.Need to ensure all Accidents/vehicle incidents/near misses are reported immediately to CD so she made aware of issues. Accident forms will be completed for ALL issues and then once completed sent to H&S group for information. | CD to ensure all employees are made aware they need to report all incidents
3.16 | 2018-06-05 | 3 accidents reported since March | All | 3 in total, Dave McDermid, Car Spares, Piece of iron hit him on the head from top of skip, no hard hat worn. John Beasley, Wet Waste, tripped on customer site and sprained ankle. Enes Kuzey, member of public, forklift ran over his foot! | Need to ensure all employees reminded to wear PPE at all times including hard hats in yard.
3.16 | 2018-07-03 | 3 accidents reported since May | All | 3 in total, Ian Stacey was run over by forklift and this resulted in a RIDDOR. It has been agreed to paint a hatched area in front of the work area for employees to wait whilst forklift in operation. Will Blazier - did not engage foot brake on forklift and had foot run over- was wearing PPE. Not a RIDDOR but emergency services called. Agreed to purchase stickers for forklifts to remind employees to ensure brake is engaged before they exit the equipment Jack - walked into a machine and was attended to by site First aider and laceration was cleaned and he returned to work | Need to ensure all employees reminded to wear PPE at all times including hard hats in yard.
3.16 | 2018-08-07 | 3 accidents reported since July | All | 6th July - HGV Driver Self-employed from Taplow Logistics Barry Howarth Large cut on forearm from falling over when getting out of lorry, carried out first aid on site. 13th July - Eric Gerrard - Works in Tyre Bay He misjudged when hitting with a hammer and hit his thumb, small cut, no evidence of break, Eric continued working. 30th July - Kevin Rae HGV Driver Car Spares Thumb squashed between car door and safety rails when loading lorry at British Car Auctions site, hospital treatment given, not RIDDOR.
3.17 | 2018-10-02 | 0 accidents reported since August | All | Excellent result
3.17 | 2018-11-06 | 1 accidents reported since October | All | 1 Accident - Michael Summers Smith was loading a vehicle onto lorry when a ratchet strap pinged off and hit his arm. First Aid given, no need for hospital treatment. Accidents at other Depots - need to ensure all other A1 Depots report Accidents at H&S meeting (this will begin at December meeting once new phone system is installed) and also send CD completed Accident report when it occurs
3.17 | 2018-12-04 | 1 accidents reported since October | All | Car Spares had one accident, Steven Sanderson suffered cut to chin whilst using machine in yard. First Aid was given, form completed and no further action needed. Wet Waste had one incident, Steve Shaw injured awaiting Accident form to be sent over.
3.17 | 2019-02-05 | 0 accidents reported since February | All | Pleased to report no Accidents or Near Misses for December or January onsite.
3.17 | 2019-04-02 | 2 accidents reported since March | All | Timothy Evans – Pulled Boom of machine onto his head. Freddie Brown – Twisted ankle awaiting return to work.
4. Incidents / Near Misses in previous month
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
4.1 | 2015-03-24 | No incidents / near misses to report | All | No incidents/ near misses across the A1 Group during February / March. SW reminded H&S Reps that given nature of the business these were likely to be transport issues and that we need to record ALL issues when they come in, even near misses |  | 2015-03-01 | Closed
4.2 | 2015-04-29 | Brakes on yard vehicle were tampered with | All | Employee deliberately tampered with yard vehicles brakes. No accident but action resulted in Wayne Harrison's employment terminated due to Gross Misconduct |  | 2015-04-01 | Closed
4.3 | 2015-05-27 | 7 Incidents involving Company vehicles | All | AM informed attendees that there was a high level of vehicle accidents. SW has been asked to remind employees about right to reclaim excess and SS will send out letters to all employees as our insurance premiums has risen dramatically this year.
4.4 | 2015-07-21 | 9 incidents involving Company vehicles | All | Low level traffic incidents, all incidents reported to Insurance company. No injuries recorded. |  | 2015-07-01 | Closed
4.5 | 2015-09-22 | 2 Incidents | All | MP had accident in Company Van no injuries reported. Gas bottle explosion in Scrap metal area no injuries, incident logged in site diary. Incident involving Third Party colliding with our stationery Trailer and vehicle whilst being recovered by the AA, total loss with possible whiplash for our Driver Barry King |  | 2015-09-01 | Closed
4.6 | 2015-10-01 | 1 Incident | All | GC - tried to drive behind a reversing vehicle and this caused damage to the drivers door. No injuries reported and both vehicles can still be driven. Both Drivers interviewed and told to take more care whilst driving. |  | 2015-11-01 | Closed
4.7 | 2016-01-12 | 1 Incident | All | David Nixon – Damaged tarmac at customers site. He also damaged a car at Wokingham – No injuries sustained at either accident.
4.8 | 2016-03-31 | 6 vehicle Incidents | All | Incidents 4 at fault Road Accidents and 2 non fault – with 1 of the non fault being a possible false claim. Insurance Company dealing with all and no injuries.
4.9 | 2016-05-31 | 2 near misses / 1 motoring Incident | All | 2 Near misses in our yard, our 7.5 t vehicle was being reversed and it hit a parked trailer, damage to our vehicle only no injuries. 1 Motoring incident – WR64 DXS (Car Spares) – Our vehicle hit rear of Third Party, causing the rear window to break and damage to rear tailgate. There was 1 female driver and 2 children in the vehicle, no persons were injured and the incident has been reported to our Insurance company.
4.1 | 2016-08-04 | 1 near misses / 2 motoring Incidents | All | Car fell off Top Rack landing on Fork Lift, the Safety Cage of the Fork Lift took the weight of the vehicle. No injury to any persons and no damage to Forklift. 1st Vehicle Incident, our vehicle was stationery turning right, 2nd car stopped behind our vehicle, 3rd car didn’t stop, hitting 2nd car and pushing that into our vehicle. No injuries to any party and police were involved, non fault. 2nd Vehicle Incident, our vehicle was stationery at our Bridgend Depot, AA recovery vehicle reversed into front bumper of our truck. No injuries and non fault.
4.11 | 2016-10-26 | 0 near misses / 4 motoring incidents | All | ME51 LOO - Hit by TP whilst stationary. WR12 CLZ - Scraped a vehicle at festival. 56LD scraped TP vehicle whilst reversing. OLD80G - Caught roof tiles of a building with toilet block that was strapped on the back of vehicle.
4.12 | 2016-12-14 | 0 near misses / 1 motoring incidents | All | Driver hit TP whilst reversing, didn’t realise he had done it. Drove away from scene, police were involved. They have issued the driver with a warning letter and caution. AM spoke to the driver and warned him that any further incidents would result in disciplinary action being taken.
4.12 | 2017-02-22 | 0 near misses / 0 motoring incidents | All | Nothing to report
4.12 | 2017-05-24 | 0 near misses / 3 motoring incidents | All | WWW – RP11 KES – Hit TP that pulled into gap in front of truck. No injuries LOO – Coventry Depot – Third party hit rear of our vehicle at approximately 35mph minor damage and our Driver is claiming for injuries. WCS – TP hit side of our Truck WR64 DXS – Video showed TP drive into the side of our vehicle as she was in the wrong lane to go straight ahead.
4.12 | 2017-10-03 | 0 near misses / 9 motoring incidents | All | WET WASTE (2) RP11 KES – 17/8/17 – Hit 3rd on Motorway, small injury claim being contested. Driver no longer employed. RX65 AOF – 28/7/17 – Battersea Power station hit drain pipe while manoeuvring Driver was being banked by 3 banksmen. LOO HIRE (5) WR12 CLZ – 19/6/17 – TP tried to overtake Sprinter and Trailer, her lane merged with our Drivers. TP had nowhere to go and collided with our trailer. WX14 JYS – 10/7/17 – Driver turned left onto main road from a tight junction, His trailer stepped out naturally on its turn, but the driver failed to see TP vehicle. Injury claim being contested. RP09 RUS – 10/7/17 – Near miss only, There were 2 vehicle involved and the party that caused the accident claimed our vehicle was involved. The police officers who attended site confirmed that this wasn’t the case. WN09 JGZ – 21/7/17 – Our Driver scraped side of TP on passing RV06 YTE – 22/7/17 – Ratchet strap handle had popped open, passing vehicle slowly causing damage to TP vehicle. There was no claim following as we paid for the TP repairs. CAR SPARES (2) NTS 27 – 26/7/17 – Our driver reversed into a parked Police vehicle in a Police compound. SP17 RUS – 18/9/17 – Our Driver had to reverse down a single track road. Unfortunately hitting an electrical pole. No damage to our vehicle, cost of repair was £1000, no insurance claim made.
4.12 | 2017-11-28 | 0 near misses / 9 motoring incidents | All | YT15 FHR – Barry King 23rd November 2017 – Third Party hit our vehicle at approx. 40-45mph. Our vehicle was parked in front of Network Rail Gates, as Barry was locking the gate the Third Party did not navigate a bend and ploughed straight into our vehicle. Barry received minor injuries but none the less received treatment by Ambulance crew and will be claiming injury. PE17 ZER – TP unattended vehicle hit by our vehicle. WR15 XHD – Bridgend vehicle – passing TP slowly, our driver claims there was no contact made but TP is claiming there was. At time of incident there was no evidence of any contact.
4.13 | 2018-01-30 | 0 near misses / 1 motoring incidents | All | AB16 BOG – Martyn Kirkham – Rear end collision in Birmingham. Damage to our vehicle £2500 estimated, no personal injury.
4.13 | 2018-02-27 | 0 near misses / 1 motoring incidents | All | Van Theft - vehicle recovered with ignition damaged. Ensure all keys are collected when employees leave business. | No Actions required
5.13 | 2018-04-04 | 1 near misses / 1 motoring incidents | All | Van Theft - vehicle recovered with ignition damaged. Ensure all keys are collected when employees leave business. | No Actions required
6.13 | 2018-04-04 | 1 motoring incidents | All | 1 vehicle incident - reported that a load being carried on our low loader trailer hit a low hanging tree branch which resulted in the vehicle behind being hit and its air bags going off. | No Actions required
4.13 | 2018-05-01 | 4 motoring incidents | All | Car Spares – 9th March 2018 - Our Artic clipped a branch of a dead tree with the load on the trailer, resulting in the vehicle behind being allegedly hit setting his airbag off in the car. Reported to our insurance company for information only as we believe the Third Party claim would be against the Council. Car Spares- 28th April 2018 - Our recovery van was hit in the rear as the driver was sat in traffic, minimal damage and we will not be claiming. Car Spares – 10th April 2018 – Our recovery van was on the A329M where a cyclist was riding his bike, his front wheel fell off as our driver was passing him. Resulting in the cyclist being hit by the wing mirror of our van. Reported to insurance for information only as the cyclist wouldn’t pass his details on. Also reported to the police. Loo Hire – Our van was being banked into an entrance where temporary traffic lights were being used. A van came round the back of our van resulting in our van hitting the door of the van. Small dent and reported to insurance company. | No Actions required
4.13 | 2018-06-05 | 0 motoring incidents | All | Excellent result
4.13 | 2018-07-03 | 1 motoring incidents | All | TP clipped wing mirror on our van smashing the lens. WM66 OJK – Loo Hire
4.13 | 2018-08-07 | 2 motoring incidents | All | SA11 YXX - Reversed with trailer denting door. WO17 DKF - Reversed denting bumper
4.14 | 2018-10-02 | 3 motoring incidents | All | Caravan - came off our vehicle PE17 ZER. Resulting in third party vehicle being a total loss. Wing Mirror being damaged on a truck cost £89 paid by us and not going through insurance. Third one advised damage to a VW polo- light and rear quarter. £880 damage not going through insurance.
4.14 | 2018-11-06 | 4 motoring incidents | All | 4th October 2018: AR – RX65 AOF – Turned wheel with full lock, resulting in hitting the wing and wheel arch of Third Party Vehicle. 11th October 2018: CW – Rear end Collision hitting Third Party 24th October 2018: JC – Rear end Collision hitting Third Party sudden stop of traffic. Possible injury claim 6 November 2018: SM – Third Party hit our vehicle.
4.14 | 2018-12-04 | 0 motoring incidents | All | Excellent result to end the year
4.14 | 2019-02-05 | 2 motoring incidents | All | Loo Hire - WV66 ZSP - Tudor Jones Groundhog Trailer hit the pillar of the exit gate. The building is a Grade II listed building, the repairs have been done by the onsite contractor at the time. Our Insurance Broker is now dealing with this. Wet Waste - EA05 NRV – Phil Hogburn TP pulled off slip road after missing junction. TP took the direct path of our Driver, resulting in our Driver colliding with the TP at speed. Video evidence has been given to our insurance company.
4.14 | 2019-04-02 | 2 motoring incidents | All | RP66 RUS – In Wokingham Scrap Yard, Driver sat stationery, Third Party came up beside him and also sat stationery. Both vehicles then moved away, third party stopped and our Driver continued colliding with the Third Party. Bridgend Depot = Vehicle Fire in Yard – Contained on site, vehicle destroyed.
5. Performance Metrics
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
5.1 | 2015-03-24 |  | SW | Monthly statistics will be produced once we have enough data to include
5.2 | 2015-04-29 |  | SW | Monthly statistics will be produced once we have enough data to include
5.3 | 2015-05-27 |  | SW | Monthly statistics will be produced once we have enough data to include
5.4 | 2015-07-21 |  | SW | Accidents since January 2015 Accidents - 7 Near Misses - 3
5.5 | 2015-11-10 |  | SW | Accidents since January 2015 Accidents - 9 Near Misses - 4 |  | 2015-11-01 | Closed
5.6 | 2016-01-12 |  | SW | Accidents since January 2016 Accidents - 2 Near Miss - 1
5.7 | 2016-03-31 |  | SW | Accident/Incidents in 2016 to date - 4 Accidents and 7 Vehicle incidents
5.8 | 2016-05-31 |  | SW | Accident/Incidents in 2016 to date - 8 Accidents and 8 Vehicle incidents
5.9 | 2016-08-04 |  | SW | Accident/Incidents in 2016 to date - 9 Accidents and 10 Vehicle incidents
5.1 | 2016-10-26 | Accident/Incidents in 2016 to date |  | 11 Accidents and 14 Vehicle incidents
5.1 | 2016-12-14 | Accident/Incidents in 2016 to date | SW | 13 Accidents and 15 Vehicle incidents
5.1 | 2017-02-22 | Accident/Incidents in 2017 to date | SW | 13 Accidents and 15 Vehicle incidents in 2016. 2 Accidents to date for 2017
5.1 | 2017-05-24 | Accident/Incidents in 2017 to date | SW | 6 Accidents and 12 vehicle incidents to date for 2017
5.1 | 2017-10-03 | Accident/Incidents in 2017 to date | SW | 6 Accidents and 12 vehicle incidents to date for 2017
5.1 | 2017-11-28 | Accident/Incidents in 2017 to date | SW | 7 Accidents and 15 vehicle incidents to date for 2017
5.1 | 2018-01-30 | Accident/Incidents in 2018 to date | SW | 4 Accidents and x vehicle incidents to date for 2018
5.1 | 2018-02-27 | Accident/Incidents in 2018 to date | SW | 4 Accidents and 5 vehicle incidents to date for 2018
6.1 | 2018-04-04 | Accident/Incidents in 2018 to date | SW | 5 Accidents and 5 vehicle incidents to date for 2018
5.1 | 2018-05-01 | Accident/Incidents in 2018 to date | SW | 5 Accidents and 9 vehicle incidents to date for 2018
5.1 | 2018-06-05 | Accident/Incidents in 2018 to date | SW | 8 Accidents and 9 vehicle incidents to date for 2018
5.1 | 2018-07-03 | Accident/Incidents in 2018 to date | SW | 11 Accidents and 10 vehicle incidents to date for 2018
5.1 | 2018-08-07 | Accident/Incidents in 2018 to date | SW | 15 Accidents and 12 vehicle incidents to date for 2018
5.11 | 2018-10-02 | Accident/Incidents in 2018 to date | SW | 15 Accidents and 15 vehicle incidents to date for 2018
5.11 | 2018-11-06 | Accident/Incidents in 2018 to date | SW | 16 Accidents and 19 vehicle incidents to date for 2018
5.11 | 2018-12-04 | Accident/Incidents in 2018 to date | SW | 18 Accidents and 19 vehicle incidents to date for 2018
5.11 | 2019-02-05 | Accident/Incidents in 2019 to date | SW | 18 Accidents and 19 vehicle incidents to date for 2018 0 accidents and 2 vehicle incidents in 2019
5.11 | 2019-04-02 | Accident/Incidents in 2019 to date | SW | 2 accidents and 7 vehicle incidents in 2019
6/7. Impact of operational infrastructure changes in the last month/next month
Ref No | Open Date | Issue | Owner |  |  | Closure Date | Closed
6.1 | 2015-03-24 | No operational changes happening across the group | All | SW explained that the section was to cover any changes that may be happening at each depot. Maybe building work etc. contractors that may e on site and nature of work being undertaken. SW reminded all reps to communicate this at each meeting for each department and site. This way we can ensure all communication with employees etc. is undertaken.
6.2 | 2015-04-29 | Ground repairs - Tyre Bay - Wokingham Site | SS/GW | Ground repair being carried out to the left of the Tyre Bay, this has been placed in the Site Diary. Employee's to be reminded to be careful in the area whilst work being undertaken
6.2 | 2015-05-27 | Ground repairs - Tyre Bay - Wokingham Site | GW | Concrete by disc bay has been completed |  | 2015-05-01 | Closed
6.3 | 2015-07-21 | No operational changes during June and July | All | No action required
6.4 | 2015-09-22 | Tarmacking at Lambs Lane | NC | NC to arrange Tarmacking for the Lambs lane yard area
6.4 | 2015-11-10 | Tarmacking at Lambs Lane | NC | NC was not present at meeting do no update. |  | 2015-11-01 | Closed
6.4 | 2016-01-12 | No changes during December or due in January | All | Nothing to report
6.5 | 2016-03-31 | Bennetts Yard | DK/SC | DK & SC will be moving to Bennetts Yard by 8th April - SW will send SK an office RA to complete. Once the major refurbishment work at the address is completed then a full site RA will need to be conducted.
6.6 | 2016-05-31 | Bennetts Yard | DK/SC | Move complete but still needs a few issues to be resolved |  | 2016-07-01 | Closed
6.7 | 2016-08-04 | Operational Infrastructure changes previous/forthcoming | All | Nothing to report
6.7 | 2016-10-26 | Operational Infrastructure changes previous/forthcoming | All | Nothing to report
6.7 | 2016-12-14 | Operational Infrastructure changes previous/forthcoming | All | New 700m sewerage pipe being run through back of site - no further details
6.7 | 2017-02-22 | Operational Infrastructure changes previous/forthcoming | All | Work commenced and ongoing
6.7 | 2017-05-24 | Operational Infrastructure changes previous/forthcoming | All | Work commenced on the main office extension
6.7 | 2017-10-03 | Operational Infrastructure changes previous/forthcoming | All | Work continuing on the main office extension. New depot at Thame Oxfordshire - site plan required
6.7 | 2017-11-28 | Operational Infrastructure changes previous/forthcoming | All | Ground floor of new office extension - completed and operational - H&S signage needs to be reviewed including fire escape signs and lighting. 2nd Floor will be completed by end of February (new offices and meeting room) New Oakley, Oxford site now Operational. SW conducted H&S audit at end of October and sent actions to IS Depot Manager - included Signage review / Fire Extinguishers review / Perimeter fencing or window bars to be installed. New crusher in metal recycling yard currently being installed and commissioned due to be completed by end of December
6.7 | 2018-01-30 | Operational Infrastructure changes previous/forthcoming | All | Ground floor of new office extension - H&S signage needs to be reviewed including fire escape signs and lighting. 2nd Floor will be completed by end of February (new offices and meeting room) Loo Hire have moved from Meakins to Bennetts and operational - H&S review required on signage etc. SW to organise.
6.7 | 2018-02-27 | Operational Infrastructure changes previous/forthcoming | All | Ground floor of new office extension - H&S signage needs to be reviewed including fire escape signs and lighting. 2nd Floor will be completed by end of February (new offices and meeting room) Loo Hire have moved from Meakins to Bennetts and operational - H&S review required on signage etc. SW to organise. | SW to complete FRA at Bennetts on 27/2 and issue to PJ Wet Waste and LW -- Loo Hire
7.7 | 2018-04-04 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office refit by end of June Employee canteen by front entrance being refurbished during July - August new H&S Board to be installed Ground floor of new office extension - H&S signage needs to be reviewed including fire escape signs and lighting. 2nd Floor will be completed by end of September (new offices and meeting room)
7.7 | 2018-05-01 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office - TBC need to plan as operationally required Employee canteen by front entrance being refurbished during July - August new H&S Board to be installed Ground floor of new office extension - CD reviewing all site signage - 2nd Floor will be completed by end of July (new offices and meeting room)
7.7 | 2018-06-05 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office - work started and due for completion in June Employee canteen by front entrance being refurbished during July - August new H&S Board to be installed Ground floor of new office extension - CD reviewing all site signage - 2nd Floor will be completed by end of July (new offices and meeting room) Two new cabins are being ordered for the yard, this is to replace the existing porta cabins at the entrance to the main yard.
7.7 | 2018-07-03 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office - almost complete and needs new flooring will be complete by end o July Employee canteen by front entrance - new units have been purchased and need to be installed once other work has been completed New H&S Board has been installed in employee canteen in main office building Site signage - ongoing with new signs now in place around the site. The weekly H&S walkarounds will identify other signage required. 2nd Floor of office extension will be completed by end of July (new offices and meeting room) Excellent progress in all areas around site.
7.7 | 2018-08-07 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office - ongoing Employee canteen by front entrance - ongoing Site signage - ongoing with new signs now in place around the site. The weekly H&S walkarounds will identify other signage required. 2nd Floor of office extension will be completed Excellent progress in all areas around site
7.7 | 2018-10-02 | Operational Infrastructure changes previous/forthcoming | All | Metal Recycling office - complete Employee canteen by front entrance - ongoing Site signage - ongoing with new signs now in place around the site. The weekly Excellent progress in all areas around site
7.7 | 2018-11-06 | Operational Infrastructure changes previous/forthcoming | All | employee canteen by front entrance - ongoing Site signage - ongoing with new signs to be ordered for other Depots New workshop/Paint spraying facility at Bennetts Yard - ongoing
7.7 | 2018-12-04 | Operational Infrastructure changes previous/forthcoming | All | Nothing new in Wokingham site Gas Cage delivered to Bennetts and is due to be built shortly. Signage audit action plans for each site, Oakley site will need looking at as poor signage and lighting at end of the yard area.
7.7 | 2019-02-05 | Operational Infrastructure changes previous/forthcoming | All | • The aim for the main yard is for The Spares office to start renovation around March this year. • The Staff canteen will be looking at starting work towards the end of this year and early 2020. • Tyre shed will be in need of updating at some point, hopeful will be within the year.
7.7 | 2019-04-02 | Operational Infrastructure changes previous/forthcoming | All | Contractors/Building Work Spares Office & Tyre shed. ongoing. Staff Canteen we are looking at starting this in 2020 NB - John the builder to attend future meetings
8. Risk Assessments reviewed last month
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
8.1 | 2015-03-24 | All risk assessments being re written in new format | SW | Following a review of the risk assessment process in operation it was apparent that there was unnecessary duplication of some risk assessments and that generic ones could be created for some areas. There would still be some risk assessments that are site / job specific and these would be completed by either the H&S consultant or the H&S Representative. We will be introducing a new procedure - a rolling completion process over a twelve month period so issue assessments to be completed at the monthly H&S meeting. We would also discuss and issues with ones that have not been completed within the specified timescales. All risk assessments must have a statement regarding they appropriateness for Apprentices.
8.2 | 2015-04-29 | Risk Assessments are on the Back Office | SW | SW to produce a rolling completion process over a twelve month period so issue assessments to be completed at the monthly H&S meeting. We would also discuss and issues with ones that have not been completed within the specified timescales
8.3 | 2015-05-27 | RA for Portsmouth University | DK | DK may require specific RA's for Portsmouth Uni is they are successful with their tender. SW to liaise with DK to assist.
8.3 | 2015-07-21 | RA for Portsmouth University | DK | Ongoing
8.3 | 2015-09-22 | RA for Portsmouth University | DK | Ongoing - Tender submitted in May still awaiting update. DK has a number of tenders outstanding at present and will contact SW if RA's are required for particular jobs
8.4 | 2015-07-21 | RA for DHL in Swindon | DK | Following a recent incident in July 2015 a full Risk Assessment for the work A1 Wet Waste undertake at the Swindon DHL site on behalf of Helistrat was required. SW attended site and undertook RA and has sent this to representatives or Servest and Helistrat. All employees who deliver waste to this site will have full copies in their vehicles at all times and copies are also now held with Helistrat and Servest for reference. Any further occurrences of failure to follow H&S and site rules could result in the termination of the contract. |  | 2015-07-01 | Closed
8.5 | 2015-07-21 | Fire Risk Assessment for Lambs Lane | DK | This is being conducted on the 21/7/15 by SW and will once completed shared with H&S Rep at Lambs Lane and General Manager and placed on back office ahead of the ISO visit on the 29th July |  | 2015-07-01 | Closed
8.6 | 2015-07-21 | Workshop Risk Assessment at Lambs Lane | DK | This is being conducted on 21/7/15 and will be shared with General Manager, H&S Rep and Workshop Engineer and all actions arising will be highlighted along with timescales. It will also be available to view on the back office |  | 2015-07-01 | Closed
8.4 | 2015-11-10 | RA for Portsmouth University | DK | Ongoing
8.4 | 2016-01-12 | RA for Portsmouth University | DK | Nothing to report. DK to chase |  | Closed | 2016-03-01
8.5 | 2015-11-10 | RAMS for BA at LHR | DK | RAMS submitted for BA for drain cleaning and CCTV work. |  | Closed | 2016-02-01
8.6 | 2015-11-10 | RAMS required for BAM Nuttall for LHR T4 underpass | DK | DK requires a RAMS for LHR T4 underpass drain cleaning and CCTV survey. SW to undertake once date known. SS to sort security pass. |  | Closed | 2016-02-01
8.6 | 2016-01-12 | RAMS for BA at LHR | DK/SC | Completed and work commencing on 18/1. RAMS was resubmitted to Norland's by SC. WW have another car park to RA at Heathrow. DK/SC to discuss and if required SW will complete. |  | Closed | 2016-01-01
8.5 | 2016-03-31 | Site RA's | SW | All RA's were reviewed prior to the ISOQAR audit in January 2016. A new system need stop be devised to ensure all RA's are captured, placed on the Back Office and reviewed annually in case of any alterations.
8.6 | 2016-05-31 | Site RA's | SW | All up to date, SC has generated some so new RA's which will be updated and added to the Back Office.
8.7 | 2016-08-04 | Risk Assessments reviewed in July | SW | All up to date are on the Back Office
8.8 | 2016-10-26 | Risk Assessments reviewed in August and September | SW | All up to date are on the Back Office
8.8 | 2016-12-14 | Risk Assessments reviewed in August and September | SW | All up to date are on the Back Office
8.8 | 2017-02-22 | Risk Assessments reviewed since December | SW | All up to date are on the Back Office. Will need to be reviewed in May prior to ISO Audit in July
8.8 | 2017-05-24 | Risk Assessments reviewed since February | SW | All RA's were reviewed in May and placed on the Back Office.
8.8 | 2017-10-03 | Risk Assessments reviewed since May | SW | All RA's were reviewed in May and updated on the Back Office.
8.8 | 2017-11-28 | Risk Assessments reviewed since May | SW | All RA's were reviewed in May and updated on the Back Office. Will be reviewed in January
8.8 | 2018-01-30 | Risk Assessments reviewed since November 2017 | SW | All RA's were reviewed and updated on the Back Office. 5 new RA's to be completed since CS accident
8.8 | 2018-02-27 | Risk Assessments reviewed since January 2018 | SW | All RA's will be reviewed in December and updated on both Back Offices. 3 Revised RA's for Car Transporter/Skip Loader and Hookoader been added to Back offices
8.8 | 2018-04-04 | Risk Assessments reviewed since January 2018 | SW | All RA's reviewed and up to date on Back Office
8.9 | 2018-05-01 | Risk Assessments reviewed since March 2018 | SW | All RA's reviewed and up to date on Back Office
8.9 | 2018-06-05 | Risk Assessments reviewed since March 2018 | SW | All RA's reviewed and up to date on Back Office
8.9 | 2018-07-03 | Risk Assessments reviewed since June 2018 | SW | Forklift truck operation - reviewed
8.9 | 2018-08-07 | Risk Assessments reviewed since July 2018 | SW | SW/CD have reviewed all RA's
8.9 | 2018-10-02 | Risk Assessments reviewed since August 2018 | SW | CD to send SW all revised RA's to place on BO
8.9 | 2018-11-06 | Risk Assessments reviewed since August 2018 | SW | Ongoing - CD to send SW all revised RA's to place on BO
8.9 | 2018-12-04 | Risk Assessments reviewed since August 2018 | SW | Ongoing
8.9 | 2019-02-05 | Risk Assessments reviewed since December 2018 | SW | All RA's were reviewed and updated on 1/1/2019
8.9 | 2019-04-02 | Risk Assessments reviewed since March 2019 | SW | SW completed RA fro Granulator / CD will send SW the SWP to place on Back Office
9. Risk Assessments to be reviewed next month
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
9.1 | 2015-03-24 | A new risk assessment process to be introduced form 1/4/15 | SW | SW to transfer all risk assessments onto "back Office". Once complete any site/ job specific risk assessments will be completed by the H&S Reps with assistance from SW. A rolling 12 month review process will be introduced.
9.1 | 2015-04-29 |  | SW | Ongoing - SW to produce list by next meeting
9.1 | 2015-05-27 |  | SW | Ongoing - SW to produce list by next meeting
10.1 | 2015-07-21 |  | SW | Ongoing - SW to produce list by next meeting in September
9.2 | 2015-09-22 | Risk Assessments | SW | All RA's are now on the Back Office and can be reviewed and printed by any employee. SW will review these prior to the H&S audit from ISO in Jan 2016
9.3 | 2015-11-10 | Risk Assessments | SW | CO to review all RA's and let SW know if any changes and then SW will update dates on BO |  | 2015-11-01 | Closed
9.4 | 2016-01-12 | Risk Assessments | SW | SW has reviewed all RA's / Method Statements and COSHH assessments and has updated on Back office for external audit at the end of January
9.5 | 2016-03-31 | Risk Assessments | SW | No RA's to review. SW needs to develop a new simple system for all RA's to be reviewed over 12 months rather than in one go
9.6 | 2016-05-31 | Risk Assessments | SW | Nothing to report
9.7 | 2016-08-04 | Risk Assessments to review in August/September | SW | All up to date are on the Back Office
9.8 | 2016-10-26 | Risk Assessments to review in November | SW | Environmental RA to be reviewed
9.8 | 2016-12-14 | Risk Assessments to review in December | SW | Ongoing - SW to liaise with CO in new year
9.8 | 2017-02-22 | Risk Assessments to review in March and April | SW | SW to discuss to with CO prior to audit in July
9.8 | 2017-05-24 | Risk Assessments to review in June | SW | All RA's were reviewed in May and placed on the Back Office. SW to discuss with CO re outstanding documentation for Audit in July. SW explained we had recently completed a RA for the Henley regatta in June and the requirements were more detailed than previous expectations. All future alterations need to passed to SW who will complete and liaise with the client
9.8 | 2017-10-03 | Risk Assessments to review in Oct / November | SW | Risk Assessments have been reviewed, need to do more when new building is complete
9.8 | 2017-11-28 | Risk Assessments to review in November | SW | Risk Assessments for new crusher and new building to be completed in January 2018
9.8 | 2018-01-30 | Risk Assessments to review in February | SW | Risk Assessments for Car Transporter, Recovery Vehicle, Skip Lorry, Hook Loader to be completed in February 2018
9.8 | 2018-02-27 | Risk Assessments to review in February | SW | New RA for AWE Burfield - SW to visit site on Monday 5th March with MP to complete and place on Back office. | ACTION - SW to complete AWE Burfield RAMS 5/3
9.8 | 2018-04-04 | Risk Assessments to review in February | SW | All up to date are on the Back Office
9.8 | 2018-05-01 | Risk Assessments to review in May | SW | Crane operations RAMS needs to be completed by Friday 4th May RAMS for portable shower unit at Bennetts | SW to complete both RAMS
9.8 | 2018-06-05 | Risk Assessments to review in June | SW | RAMS for portable shower unit at Bennetts - CO to provide SW with Template | SW to complete both RAMS
9.8 | 2018-07-03 | Risk Assessments to review in July | SW | SW to review all RA's by end of July and ensure factually correct - next review date 1/12019. All employees after watching new Company H&S video in August will read SWP and RA for this r role and sign to acknowledge they are aware how to perform in their role and the risks associated with the role. | SW to complete
9.8 | 2018-08-07 | Risk Assessments to review in August | SW | SW/CD have reviewed all RA's. CD will issue to all employees in respect of the roles they undertake in August
9.8 | 2018-10-02 | Risk Assessments to review in August | SW | Ongoing
9.8 | 2018-11-06 | Risk Assessments to review in November | SW | All up to date next review in January 2019
9.8 | 2018-12-04 | Risk Assessments to review in November | SW | All up to date next review in January 2019
9.8 | 2019-02-05 | Risk Assessments to review in November | SW | All up to date next review in January 2020
9.8 | 2019-04-02 | Risk Assessments | SW | All up to date next review in January 2020
10. Management programs and legal compliance issues arising
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
10.1 | 2015-03-24 | Fire | All | All fire alarms need to be tested regularly at each site to ensure working properly and a drill must taken lace every six months to ensure effectiveness of the fire evacuation procedure. All Risk Assessment must also cover any potential fire risks etc. All vehicles will carry fire extinguishers
10.1 | 2015-04-29 | Fire | All | Fire Alarm at Wokingham site to be reviewed so it can be hear in all areas.
10.1 | 2015-05-27 | Fire | All | All site fire alarms working and staff are aware of muster station should there be a requirement to evacuate site |  | 2015-06-01 | Closed
10.12 | 2015-07-21 | Fire | All | Another Fire alarm needs to be installed at Lambs Lane in the Workshop |  | 2015-07-01 | Closed
10.12 | 2015-09-22 | Fire | All | AM reported still need high post beacons installing in certain area - John the builder sorting
10.2 | 2015-04-29 | Fire Evacuation Process | All | This must be carried out on a more regular basis NMP - CO/SS to review next week as due to be submitted to EA in May
10.2 | 2015-05-27 | Fire Evacuation Process | All | Fire Management plan - map has been completed/ NMP still to be completed by end of May |  | 2015-05-01 | Closed
10.2 | 2015-03-24 | Fire fighting equipment | All | Review each site to ensure all fire fighting equipment is in date and fit for purpose, Ensure employees are training in fighting fires and that correct fire evacuation procedure is displayed in all areas at each site
10.2 | 2015-04-29 | Fire fighting equipment | All | All Fire extinguishers at all sites are in date and recharged |  | 2015-05-01 | Closed
10.2 | 2015-07-21 | Fire Evacuation Process | All | SW has produced and completed a Fire Prevention plan which highlights the evacuation procedures for Wokingham site. This has been shared with the EA and agreed that it is for purpose. The is a small amount of work required to update the site map with the specific fire hazardous material and SW with work with AM t complete. Copies should be held by all Managers and also placed on all noticeboards. If there is an incident on site a copy will be required by the fire services |  | 2015-07-01 | Closed
10.12 | 2015-11-10 | Fire | All | Ongoing - AM to organise high posts for Fire Alarms
10.2 | 2015-09-22 | Fire Evacuation Process | All | No issues to report
10.3 | 2015-03-24 | Noise Assessments | All | Noise assessments for each site must be completed to ensure that we are legally compliant with the Control of Noise at Work Regulations 2005. All H&S Reps to ensure all employees where the correct PPE when undertaking their role including ear defenders where required. SW to liaise with CO re this issue and look to source a local company to undertake individual and business assessments during April
10.3 | 2015-04-29 | Noise Assessments | All | Simplified noise management plan. The EA have agreed key point can be laminated and placed in the appropriate areas. |  | 2015-07-01 | Closed
10.12 | 2016-01-12 | Fire | All | Ongoing
10.13 | 2016-01-12 | Fire | All | 4kg cab fire extinguishers to be ordered - An order has been placed for 25 with a price coming back to AM
10.13 | 2016-03-31 | Fire | All | All vehicles now have 4kg fire extinguishers in cabs for use in emergencies |  | 2016-04-01 | Closed
10.2 | 2015-11-10 | Fire Evacuation Process | All | Am to organise Fire Evacuation before Christmas. We should on all sites conduct two Fire Evacuation drills a year. Tests should be conducted early in morning when most employees present on site.
10.3 | 2015-09-22 | Noise Assessments | All | No issues to report
10.4 | 2015-03-24 | Noise Management Plan | All | The A1 Group Noise Management plan was discussed and no issues were raised. A formal review of the plan will take place at the next meeting
10.4 | 2015-04-29 | Noise Management Plan | All | Ongoing
10.4 | 2015-05-27 | Noise Management Plan | All | Ongoing
10.4 | 2015-07-21 | Noise Management Plan | All | ongoing as above this a requirement by the EA. SW to discuss with CO how to ensure this is produced in the coming weeks |  | 2015-07-01 | Closed
10.5 | 2015-03-24 | Road Safety Management | All | AM is responsible for ensuring all DVSA regulations are both implemented and adhered to. SW reminded all H&S Reps they should support AM in this vital and pivotal role for the business. Non compliance will be dealt with under the Company Disciplinary Policy
10.5 | 2015-04-29 | Road Safety Management | All | Disciplinary Action taken – Verbal Warning issued to employee for failing to adhere to company policy and legal compliance
10.5 | 2015-05-27 | Road Safety Management | All | AM informed attendees that there was a high level of vehicle accidents. SW has been asked to remind employees about right to reclaim excess and SS will send out letters to all employees as our insurance premiums has risen dramatically this year.
10.5 | 2015-07-21 | Road Safety Management | All | AM updated Committee that since last meeting there has been 9 incidents involving Company vehicles including a driver who had licence removed. A driver who hit a member of the publics car and drove off despite witnesses to the incident. AM confirmed a letter was being sent to all employees reminding them to take extra care whilst driving A1 vehicles and that in future depending on the circumstances the excess will be taken from their salaries. Managers need to speak with all employees reminding them to follow road safety rules at all times whilst driving company vehicles and failure to adhere to this procedure could result in disciplinary action
10.2 | 2016-01-12 | Fire Evacuation Process | All | Fire Evacuations still to be conducted on all sites AM to organise in January / February and record evacuation details to discuss at H&S meeting March. 3 Fire Marshals trained on 14/1 and further Fire Marshal training has been arranged.
10.13 | 2016-05-31 | Fire | All | Fire Alarms are being tested every other Monday at or around 0900hrs
10.3 | 2016-03-31 | Fire Evacuation Process | All | A full fire test was completed in February - no issues to report. Fire Alarm Testing is now done on a Bi Weekly basis and a Quarterly Fire Drill/Evacuation will take place, next one due May 2016. Full Wireless System with 1 alarm being set off will set off the all alarms on site.
10.3 | 2015-11-10 | Noise Assessments | All | No issues to report
10.3 | 2016-01-12 | Noise Assessments | All | No issues to report
10.13 | 2016-08-04 | Fire | All | Nothing to report
10.31 | 2016-05-31 | Fire Evacuation Process | AM | Nothing to report
10.14 | 2016-10-26 | Fire | SW | Fire Prevention Plan to be reviewed in line with new recommendations from the EA
10.32 | 2016-06-01 | Fire Evacuation Process | AM | Nothing to report
10.4 | 2016-03-31 | Noise Assessments | CO | We received a complaint regarding an unpleasant odour - we investigated the smell and responded that following site review the odour was not from A1 Site
10.5 | 2015-09-22 | Road Safety Management | CO | No issues to report. AM reported things have settled down and only 3 incidents since July
10.6 | 2015-03-24 | Manual Handling | CO | All manual handling training needs to be reviewed and where necessary refresher training undertaken. SS will review all training files across the group and produce a spreadsheet of all training requirements
10.6 | 2015-04-29 | Manual Handling | CO | Training DVD’s have been purchased and DVD’s will be played on a projector screen, Projector/DVD player to be purchased. All employees to undertake the training
10.6 | 2015-05-27 | Manual Handling | CO | Ongoing
10.5 | 2015-11-10 | Road Safety Management | CO | No issues to report
10.5 | 2016-01-12 | Road Safety Management | CO | No issues to report
10.41 | 2016-05-31 | Noise/Assessments | CO | 12th May complaint received - CO commented with the recent price in scrap going up and that the business was inundated and working to clear the back log. This is short term issue.
10.5 | 2016-03-31 | Noise/Assessments | CO | Drivers of A1 Loo Hire and A1 Wokingham Car Spares have been given a letter stating that after the 1st accident at fault any further at fault accidents or if found to be negligent, there will be up to £450 excess deducted from their salary. This is in line with Company Policy and will be investigated thoroughly. If driver is under 25 it will be £450 if over 25 it will be £250 or a sum up to these limits. |  | 2016-04-01 | Closed
10.14 | 2016-12-14 | Fire | SW | Fire Prevention Plan reviewed in line with new recommendations from the EA no issues to report
10.33 | 2016-10-26 | Fire Evacuation Process | AM | Fire Alarm tests conducted - nothing to report
10.42 | 2016-08-04 | Noise/Assessments | CO | Nothing to report
10.51 | 2016-05-31 | Road Safety Management | AM | AM sorting front facing camera's for all Company Vehicles.
10.6 | 2015-07-21 | Road Safety Management | AM | Ongoing - AM has to book training courses for all employees to undertake training once summer season has been completed
10.6 | 2015-09-22 | Road Safety Management | AM | Ongoing. SS/AM reported all MH training undertaken for employees on M&S collection jobs
10.6 | 2015-11-10 | Road Safety Management | AM | Mark Pelzer to go through Manual Handling training
10.6 | 2016-01-12 | Road Safety Management | AM | All training completed and up to date
10.6 | 2016-03-31 | Road Safety Management | AM | Ongoing
10.14 | 2017-02-22 | Fire | SW | Nothing to report
10.33 | 2016-12-14 | Fire Evacuation Process | AM | Fire Alarm tests conducted - nothing to report
10.43 | 2016-10-26 | Noise Assessments | CO | Noise Assessments to be conducted in Spring 2017
10.52 | 2016-08-04 | Road Safety Management | CO/AM | Clive looking at when needs renewing Road Safety Management - Alan still doing cameras in vehicles
10.6 | 2016-05-31 | Manual Handling | AM | All up to date no issues
10.14 | 2017-05-24 | Fire | SW | SW to check Fire Risk Assessment
10.33 | 2017-02-22 | Fire Evacuation Process | AM | Fire Alarm tests conducted - nothing to report
10.43 | 2016-12-14 | Noise Assessments | CO | No issues to report since last meeting and project ongoing
10.52 | 2016-10-26 | Road Safety Management | CO/AM | Installation of Cameras ongoing. Will take approximately 3 months across the company.
10.6 | 2016-08-04 | Manual Handling | AM | All up to date no issues
10.14 | 2017-10-03 | Fire | SW | SW to check Fire Risk Assessments for Bridgend, Thame and Coventry and review update Wokingham and Meakins
10.33 | 2017-05-24 | Fire Evacuation Process | AM | Fire Alarm tests conducted - nothing to report next one due at end of June
10.43 | 2017-02-22 | Noise Assessments | CO | Ongoing
10.52 | 2016-12-14 | Road Safety Management | CO/AM | All camera on Wet Waste vehicles nearly complete and Loo Hire and Car Spares will be completed in Q1 2017
10.7 | 2016-10-26 | Manual Handling | AM | All manual handling training up to date All new employees to receive induction to contain site evacuation and manual handling assessment. All employees to receive MH and FE refresher training annually
10.14 | 2017-11-28 | Fire | SW | SW completed in October Fire Risk Assessments for Bridgend, Oxford and Coventry and reviewed update Wokingham and Meakins in November - Meakins will be closing in end of December and all operations will be conducted from Bennetts Yard. Revised Site H&S audit will be conducted/ revised site map placed on Back Office and new RA's will be completed
10.33 | 2017-10-03 | Fire Evacuation Process | AM | Fire Alarm tests conducted - 2 not operational and being repaired on 15/10
10.43 | 2017-05-24 | Noise Assessments | CO | Ongoing
10.52 | 2017-02-22 | Road Safety Management | CO/AM | Ongoing. No other issues to report
10.7 | 2016-12-14 | Manual Handling | AM | All complete. All employees receive induction MH, Site Evacuation. Ensure all Agency employees also receive induction.
10.14 | 2018-01-30 | Fire | SW | Fire Prevention plan needs to be reviewed as new building now operational.
10.33 | 2017-11-28 | Fire Evacuation Process | AM | Fire Alarm tests conducted no issues
10.43 | 2017-10-03 | Noise Assessments | CO | Ongoing
10.52 | 2017-05-24 | Road Safety Management | CO/AM | All cameras now fitted and are working in the vehicles for accidents
10.7 | 2017-02-22 | Manual Handling | AM | All MH up to date and recorded
10.14 | 2018-02-27 | Fire | SW | Fire Prevention plan to be reviewed and updated before 15/3 | SW to review FPP and upload to Back office and issue to CO
11.14 | 2018-02-28 | Fire | SW | Fire Prevention plan to be reviewed and updated before 15/4 | SW to review FPP and upload to Back office and issue to CO
12.14 | 2018-03-01 | Fire | SW | Fire Prevention plan to be reviewed and updated before 15/5 | SW to review FPP and upload to Back office and issue to CO
13.14 | 2018-03-02 | Fire | SW | Fire Prevention plan to be reviewed and updated before 15/6 | SW to review FPP and upload to Back office and issue to CO
14.14 | 2018-03-03 | Fire | SW | Fire Prevention plan to be reviewed and updated before 15/7 | SW to review FPP and upload to Back office and issue to CO
10.14 | 2018-04-04 | Fire | SW | Fire Prevention plan to be reviewed and updated. SW working with Russell Gascoyne to produce Site Fire Folder with zoned areas. RG to provide employee training on use of site Fire Engine and also recommend equipment for Fire Fighters. CD to provide names of employees to attend Fire Training | SW to produce site Fire Folder
10.33 | 2018-02-27 | Fire Evacuation Process | AM | Car Spares & office don't have working alarms Fire alarms need installing at Bennetts - SW to include in FRA. Alarms have come from Meakins and need to be installed outside Loo Hire and Wet Waste Offices and one in Workshop | AM to organise immediate review of Fire alarms at Wokingham and ensure working by 5/3 SW to complete FRA for Bennetts AM to arrange all sites to conduct Fire Evacuation before next meeting
11.33 | 2018-02-28 | Fire Evacuation Process | AM | Car Spares & office don't have working alarms Fire alarms need installing at Bennetts - SW to include in FRA. Alarms have come from Meakins and need to be installed outside Loo Hire and Wet Waste Offices and one in Workshop | AM to organise immediate review of Fire alarms at Wokingham and ensure working by 5/3 SW to complete FRA for Bennetts AM to arrange all sites to conduct Fire Evacuation before next meeting
12.33 | 2018-03-01 | Fire Evacuation Process | AM | Car Spares & office don't have working alarms Fire alarms need installing at Bennetts - SW to include in FRA. Alarms have come from Meakins and need to be installed outside Loo Hire and Wet Waste Offices and one in Workshop | AM to organise immediate review of Fire alarms at Wokingham and ensure working by 5/3 SW to complete FRA for Bennetts AM to arrange all sites to conduct Fire Evacuation before next meeting
13.33 | 2018-03-02 | Fire Evacuation Process | AM | Car Spares & office don't have working alarms Fire alarms need installing at Bennetts - SW to include in FRA. Alarms have come from Meakins and need to be installed outside Loo Hire and Wet Waste Offices and one in Workshop | AM to organise immediate review of Fire alarms at Wokingham and ensure working by 5/3 SW to complete FRA for Bennetts AM to arrange all sites to conduct Fire Evacuation before next meeting
10.14 | 2018-05-01 | Fire | SW | Fire Prevention plan to be updated. SW sent Site zones and hotspots to Russell Gascoyne - need to complete Site Fire Folder - CD to provide RG with employee names and then RG to provide employee training on use of site Fire Engine and also recommend equipment for Fire Fighters. | CD to provide names of employees to attend Fire Training
10.33 | 2018-04-04 | Fire Evacuation Process | AM | All Fire alarms working and tested. New alarm fitted on Baler/shearer
10.43 | 2018-02-27 | Noise Assessments | CO | Ongoing will be undertaken once new crusher installed. | CO to organise revised noise tests for Wokingham
11.43 | 2018-02-28 | Noise Assessments | CO | Ongoing will be undertaken once new crusher installed. | CO to organise revised noise tests for Wokingham
12.43 | 2018-03-01 | Noise Assessments | CO | Ongoing will be undertaken once new crusher installed. | CO to organise revised noise tests for Wokingham
10.14 | 2018-06-05 | Fire | SW | Fire Prevention plan to be updated in June . Fire Engine and fire training - ongoing. SW sent Site zones and hotspots to Russell Gascoyne - need to complete Site Fire Folder - CD to provide RG with employee names and then RG to provide employee training on use of site Fire Engine and also recommend equipment for Fire Fighters. | CD to provide names of employees to attend Fire Training
10.14 | 2018-07-03 | Fire | SW | Fire Prevention plan to be updated in July. Fire Engine and fire training - completed. SW sent Site zones and hotspots to Russell Gascoyne - need to complete Site Fire Folder
10.33 | 2018-05-01 | Fire Evacuation Process | AM | All Fire alarms working and tested at Wokingham Depot - Site evacuation test to be undertaken in next two months. Bennetts - no fire Alarm operational / 2 Fire Marshals required Fire Marshall Training will be commenced at Waterloo Road with 3 people being trained for the site - CD organised | AM to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
10.43 | 2018-04-04 | Noise Assessments | CO | Ongoing - need to review the new crusher by end of April prior to EA visit | CO to organise revised noise tests for Wokingham
10.52 | 2018-02-27 | Road Safety Management | CO/AM | Changes in MOT tests re emissions CCTV on vehicles in some instances is not working | AM to update business on MOT testing AM to conduct random checks on CCTV in vehicles. If not operational contact supplier.
11.52 | 2018-02-28 | Road Safety Management | CO/AM | Changes in MOT tests re emissions CCTV on vehicles in some instances is not working | AM to update business on MOT testing AM to conduct random checks on CCTV in vehicles. If not operational contact supplier.
10.33 | 2018-06-05 | Fire Evacuation Process | AM | All Fire alarms working and tested at Wokingham Depot - Site evacuation test to be undertaken in next two months. Bennetts - no fire Alarm operational / 2 Fire Marshals required | AM to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
10.43 | 2018-05-01 | Noise Assessments | CO | Ongoing - need to review the new crusher by end of April prior to EA visit | CO to organise revised noise tests for Wokingham
10.52 | 2018-04-04 | Road Safety Management | CO/AM | Ultra low emissions/MOT’s – HGV’s can be done online now, Trailers now subject to MOT reminders
10.7 | 2018-02-27 | Manual Handling | AM | All Manual Handling up to date. Need to review induction process to ensure all H&S training captured on first day of employment. | SW to devise new induction programme for all new employees
10.14 | 2018-08-07 | Fire | SW | Fire Prevention plan to be updated in September now office extension work complete. Fire Engine and fire training - completed. SW has uploaded documents to Back Office and need to print out hard copies
10.14 | 2018-10-02 | Fire | SW | Fire Prevention plan - complete.
10.14 | 2018-11-06 | Fire | SW | Fire Prevention plan - for other depots to be completed by SW and placed on Back Office and given to Depot Managers.
10.14 | 2018-12-04 | Fire | SW | Fire Prevention plan - SW to complete for all other Depots in January and placed on Back Office and given to Depot Managers.
10.33 | 2018-07-03 | Fire Evacuation Process | AM | All Fire alarms working and tested at Wokingham Depot - Site evacuation test to be undertaken in next two months. Bennetts - no fire Alarm operational / 2 Fire Marshals required | AM to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
10.43 | 2018-06-05 | Noise Assessments | CO | Ongoing - CO to complete in June | CO to organise revised noise tests for Wokingham
10.52 | 2018-05-01 | Road Safety Management | CO/AM | Nothing to report
10.53 | 2018-04-04 | Manual Handling | CD | All Manual Handling up to date however, some new starters slipping through the net - need to ensure no employee who starts with A1 Group misses important H&S training during induction. SW to speak with CD re H&S training to ensure captured on first day of employment. CD reviewing the induction process and developing new A1 Group induction video. SM to source SAGE HR which will provide Training package to record all data on employee training | CD devise new induction programme for all new employees
10.33 | 2018-08-07 | Fire Evacuation Process | AM | Ongoing - Marshals still required for Bennetts | AM to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
11.33 | 2018-08-08 | Fire Evacuation Process | AM | Ongoing
12.33 | 2018-08-09 | Fire Evacuation Process | AM | Ongoing
13.33 | 2018-08-10 | Fire Evacuation Process | AM | Ongoing
10.33 | 2018-10-02 | Fire Evacuation Process | AM | Fire drill completed, main office can't hear the alarm and not sure that down the back in Car Spares can either - AM to review and sort issue. Test completed at Bridgend. From next meeting in November - Coventry and Bridgend will dial into meeting and will report issues
10.43 | 2018-08-07 | Noise Assessments | CO | Ongoing - CO to complete in July | CO to organise revised noise tests for Wokingham
11.43 | 2018-08-08 | Noise Assessments | CO | Ongoing - CO to complete in July
12.43 | 2018-08-09 | Noise Assessments | CO | Ongoing - CO to complete in July | CD devise new induction programme for all new employees SM to purchase Sage HR
10.33 | 2018-11-06 | Fire Evacuation Process | AM | Fire Alarm at Bennetts needs installing by 21st November and Fire Marshals trained. Lighting needs to be in place at bottom of site at Bennetts From next meeting in November - Coventry and Bridgend will dial into meeting and will report issues | AM to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
10.43 | 2018-10-02 | Noise Assessments | CO | Ongoing - CO waiting for William to come and advise
10.52 | 2018-08-07 | Road Safety Management | CO/AM | Nothing to report
11.52 | 2018-08-08 | Road Safety Management | CO/AM | Nothing to report | CD devise new induction programme for all new employees
10.14 | 2019-02-05 | Fire | SW | Fire Prevention plan - SW completed Bridgend and will upload to BO and inform SM. Coventry and Bennetts is to be done, Thames needs to be booked in , preferably by the end of March. Sean and Chloe are looking at a suitable date in March to go over, speak with Ivor and Martyn also. Looking at getting an audit iPad put in place for there as well. Date tbc.
10.33 | 2018-12-04 | Fire Evacuation Process | AM | Bennetts still awaiting fire alarm system to be installed but actions now in place to move this along and to get this installed as soon as possible. Also Laura and Chloe organising training if the Fire Marshalls for the site. | CO to sort Fire Evacuation Test LW / MP to sort Fire Marshals for Bennetts
10.43 | 2018-11-06 | Noise Assessments | CO | Ongoing - CO waiting for report from William
10.52 | 2018-10-02 | Road Safety Management | CO/AM | DVSA - Traffic Commissioner - all offences will be issued to the driver
11.52 | 2018-08-08 | Road Safety Management | CO/AM | Nothing to report | CD devise new induction programme for all new employees
10.33 | 2019-02-05 | Fire Evacuation Process | AM | Laura has set up Fire Training for Monday 11th, Coventry, Bridgend, Bennett representatives will be there. Bennetts Fire systems are due to be put on site Week commencing 18th February.
10.43 | 2018-12-04 | Noise Assessments | CO | Ongoing - CO waiting for report from William
10.52 | 2018-11-06 | Road Safety Management | CO/AM | Road Safety - Traffic Commissioner has problems with FORS. FORS - AM completing Bronze in the next few days and then Silver in January.
10.14 | 2019-04-02 | Fire | SW | Fire Prevention plan - Coventry, Oxford and Bennetts is to be done
10.43 | 2019-02-05 | Noise Assessments | CO | CO has report form William to p[ass to SW to upload to BO
10.52 | 2018-12-04 | Road Safety Management | CO/AM | FORS - Currently at a Bronze level but working towards Silver. Alan is sorting list for management to go out to all relevant managers. This should be out by the 7th December. Everything should then be completed by end December to get to Silver rating.
10.33 | 2019-04-02 | Fire Evacuation Process | AM | Nothing to report
10.43 | 2019-03-05 | Noise Assessments | CO | Ongoing - CO still to send report form William to place on BO
10.52 | 2019-04-02 | Road Safety Management | CO/AM | David Nixon – Self Employed Driver, pulled out on a vehicle who was approaching at approximately 40mph. CD brought up the use of mobile phones when driving, this was more related to using the phone as a SatNav and holding it whilst driving. CD will be investing in SatNavs for van drivers as the HGV’s already have equipment installed.
11. Issues in performance of contracted Third Parties
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
11.1 | 2015-03-24 | All contractors must provide method statement and insurance documentation prior to commencing any work on any A1 site | All | Following a review of contractors on site it was apparent that no formal procedure was in place to ensure they either competent or insured.
11.1 | 2015-05-27 |  | All | Process in place to review all Contractors insurance and competency |  | 2015-06-01 | Closed
11.2 | 2015-04-29 | Public Liability insurance | CO/SW | John Rushton and Olly Haynes to check for Public Liability Insurance with the Third Parties working on site.
11.2 | 2015-05-27 |  | CO/SW | Ongoing
11.2 | 2015-07-21 |  | CO/SW | Ongoing
11.2 | 2015-09-22 |  | CO/SW | Ongoing - Insurers attending Wokingham site Car Spares on 29/9
11.2 | 2015-11-10 |  | CO/SW | Ongoing - Insurers attended site and rejected Public Liability insurance application. SP is currently appealing the decision |  | 2015-11-01 | Closed
11.3 | 2016-01-12 | Contractors Performance | All | Nothing to report
11.4 | 2016-03-31 | Contractors Performance | All | Nothing to report
11.4 | 2016-05-31 | Contractors Performance | All | Nothing to report
11.4 | 2016-08-04 | Contractors Performance | All | Nothing to report
11.4 | 2016-10-26 | Contractors Performance | All | All Contractors to provide insurance documentation prior to undertaking any activity at any A1 Group site. All contractors must ensure they complete Contractors Assessment and provide RAMS before any work conducted at A1 Group site
11.4 | 2016-12-14 | Contractors Performance | All | Nothing to report
11.4 | 2017-02-22 | Contractors Performance | All | Nothing to report
11.4 | 2017-05-24 | Contractors Performance | All | Ensure that the builder for the office extension completes and RAMS and contractors questionnaire
11.4 | 2017-10-03 | Contractors Performance | SS | Need to get Insurance details etc. from the Contractors who are working on the new office
11.4 | 2017-11-28 | Contractors Performance | SS | Need to ensure all contractors complete Contractor Agreement and Contractor Questionnaire prior to undertaking any work with A1 Group - SW to provide SM with all new documentation
11.4 | 2018-01-30 | Contractors Performance | SS | SW provided all documentation required for Contractors to complete prior to undertaking work
11.4 | 2018-02-27 | Contractors Performance | SS | No issues to report
11.4 | 2018-04-04 | Contractors Performance | SS | No issues to report
11.4 | 2018-05-01 | Contractors Performance | SS | No issues to report
11.4 | 2018-06-05 | Contractors Performance | SS | Need to ensure all contractor accidents are recorded
11.4 | 2018-07-03 | Contractors Performance | SS | CD reported all contractors now complete RAMS/Contractor questionnaire and provide insurance cover documentation prior to undertaking any work on any site.
11.4 | 2018-08-07 | Contractors Performance | SS | Nothing to report
11.4 | 2018-10-02 | Contractors Performance | SS | Nothing to report
11.4 | 2018-11-06 | Contractors Performance | SS | Nothing to report
11.4 | 2018-12-04 | Contractors Performance | SS | Nothing to report
11.4 | 2019-04-02 | Contractors Performance | All | Nothing to report
12. Legislation & HSE Updates
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
12.1 | 2015-03-24 | Drug Driving | SW | SW updated Reps on revised legal changes drug driving. AM will be sending out to all H&S Reps and Managers a full explanation on this issue and the penalty's for non compliance. The business has purchased drug testing kits and Managers need to use these if they suspect an employee may be under the influence of drugs especially if they are driving on behalf of the business
12.1 | 2015-04-29 | Drug Driving | AM/SW | Wet Waste Drivers meeting covered the key points, further meetings will be arranged for Car Spares/Metal Recycling and Loo Hire Drivers. The tests will be carried out as soon as possible. SW to create a staff MEMO.
12.1 | 2015-05-27 | Drug Driving | All | DK will commence Drug testing of random employees during June. This process will be rolled out to rest of business in due course. All staff will be informed by means of internal memo.
12.1 | 2015-07-21 | Drug Driving | All | Due to heavy workload DK has not undertaken this project to date. This will be rolled out in the coming month. All employees still need to be reminded off this via email
12.1 | 2015-09-22 | Drug Driving | SS | SS to order new Drug testing kits for Group. PP an employee was tested by DVSA recently and was all clear. No action required.
12.1 | 2015-11-10 | Drug Driving | SS | SS to look at ordering new Drug testing kits as current ones are now out of date. DK was recently tested by Screensafe and it was agreed to look at these as DK found easy to complete and gave instant results.
12.1 | 2016-01-12 | Drug Driving | SS | SS has found suitable drug kits which will be ordered and used when necessary.
12.1 | 2016-03-31 | Drug Driving | SS | We are experiencing a high volume of clients who either require drug tests or are completing these themselves. We need to order some kits and become proactive and randomly/regular test the drivers especially if we have suspicions regarding possible drug use. This should be across the whole business. If employees fail the test then this could lead to disciplinary action including suspension. We must not knowingly allow employees who we suspect of taking drugs either drive or operate machinery under the H&S at Work Act. SS to purchase new kits for use internally.
12.1 | 2016-05-31 | Drug Driving | SS | SS purchased new kits if required. SW commented that recent figures that there were almost 8,000 arrests last year for drug driving in England and Wales. The statistics from 35 of the 43 forces showed that 7,796 people were arrested between March 2015 and April 2016. In March 2015 new legislation was brought in covering legal driving limits for 17 illegal and prescription drugs. Under the old laws, police had to show driving was impaired by drugs to prosecute however, the new drug driving laws in England and Wales made it a specific offence to drive after having certain drugs above prescribed levels. Those caught face a minimum 12-month driving ban, up to six months in prison, an unlimited fine and a criminal record.
12.1 | 2016-08-04 | Drug Driving | All | Drugs testing will take place randomly across the Group. Multi use equipment will be sourced and purchased. The period will be over the next 6 months after discussion at the table.
12.1 | 2016-10-26 | Drug Driving | All | Test kits purchased and a number of random tests will be completed before next H&S meeting in December
12.1 | 2016-12-14 | Drug Driving | AM | Tests kits purchased but no tests as yet completed. AM to organise random tests in January
12.1 | 2017-02-22 | Drug Driving | AM | A number of random drugs tests were untaken in Wet Waste and the process was successful and will now progress to the whole of the A1 Group.
12.1 | 2017-05-24 | Drug Driving | AM | Agreed to conduct a further random test in next few months following a drivers meeting
12.1 | 2017-10-03 | Drug Driving | AM | Loo Hire Meakins - Martyn Kirkham’s staff have been tested - no issues to report
12.1 | 2017-11-28 | Drug Driving | AM | No actions taken place in October / November. SW reiterated the need to complete random tests across the group especially for Drivers and Yard employees operating machinery. Agreed to look at randomly testing one employee per month
12.1 | 2018-01-30 | Drug Driving | AM | New random tests to be undertaken by AM/MP at next drivers meeting
12.1 | 2018-02-27 | Drug Driving | AM | New random tests to be undertaken by AM/MP at next drivers meeting | MP to organise random test at next Managers meeting - SS to ensure we have enough in date kits
12.1 | 2018-04-04 | Drug Driving | AM | Random tests undertaken by AM/MP - no issues to report
12.1 | 2018-05-01 | Drug Driving | AM | Nothing to report
12.1 | 2018-06-05 | Drug Driving | AM | Nothing to report
12.1 | 2018-07-03 | Drug Driving | AM | Nothing to report
12.1 | 2018-08-07 | Drug Driving | AM | Nothing to report
12.1 | 2018-10-02 | Drug Driving | AM | Drink/Drug driving - test was carried out on one member of staff which was negative Need to look at doing random tests in coming months
12.1 | 2018-11-06 | Drug Driving | AM | Drink/Drug driving - Alan tested one of the drivers as he smelt alcohol on his breath, he was just under the limit! AM to conduct a number of "random" tests in coming month
12.1 | 2018-12-04 | Drug Driving | AM | Test one employee which was positive and employee was dismissed
12.1 | 2019-04-02 | Drug Driving | AM | Ongoing - need to complete 2 random tests before next meeting AM to organise | AM to organise
13. On-going operational or project-based issues
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
13.1 | 2015-03-24 | Line painting at A1 Group sites | SW | SW updated the committee on a recent H&S case re having correct employee walkways around sites etc. A review of each site need s to be undertaken and plan produced of the work required which will be undertaken in house using the appropriate materials
13.1 | 2015-04-29 | Line painting at A1 Group sites | GW | GW Purchased line painting equipment, unfortunately the equipment wasn’t fit for purpose. Other options to be looked at to ensure a Walking area is marked out on sites for Public and Employees. Suggestion of using Speedy Hire was mentioned by NC
13.1 | 2015-05-27 | Line painting at A1 Group sites | GW | Ongoing
13.1 | 2015-07-21 | Line painting at A1 Group sites | GW | Ongoing GW was unable to attend meeting
13.1 | 2015-09-22 | Line painting at A1 Group sites | GW | Completed at all sites |  | 2015-07-01 | Closed
13.2 | 2015-11-10 | No projects currently being undertaken | All | Nothing to report
13.2 | 2016-01-12 | No projects currently being undertaken | All | Nothing to report
13.2 | 2016-03-31 | Bennetts Yard | DK | A plan to redevelop the new Wet Waste Office at Bennetts Yard will be undertaken in the coming months.
13.2 | 2016-05-31 | Bennetts Yard | DK | Move complete but still needs a few issues to be resolved
13.2 | 2016-08-04 | Bennetts Yard | DK | Bennetts - Paul James only one in at the moment
13.2 | 2016-10-26 | Bennetts Yard | DK | All operational - site signage needs to be reviewed and purchased where necessary
13.2 | 2016-12-14 | Bennetts Yard | DK | ongoing |  | 2017-02-22 | Closed
13.3 | 2017-02-22 | Projects currently being undertaken | DK | Nothing to report
13.3 | 2017-05-24 | Projects currently being undertaken | MP | Nothing to report
13.3 | 2017-10-03 | Projects currently being undertaken | MP | SW conducted H&S Audit of Bennett's Yard. SW to conduct further audits at Bridgend, Coventry and Thames with revised audits at Meakins and Wokingham to be completed by end of October and reports and actions plans placed on Back Office
13.3 | 2017-11-28 | Projects currently being undertaken | MP | SW conducted H&S Audit at Bridgend, Coventry and Oxford with revised audits at Meakins and Wokingham also completed. Al reports and actions plans placed on Back Office. All actions also added to the Company Action plan which is also on Back Office.
13.3 | 2018-01-30 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW to conduct Business Risk Register/ re write job descriptions/introduce weekly H&S walkaround audits at Wokingham (CD to undertake). CD to visit business in Bristol to see H&S programme in March. H&S Communication needs overhaul - SW to provide guidance. Monthly H&S meetings to be instigated, All H&S training to be reviewed. Training matrix will b moved onto new HR system ( SM is looking at a package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire
13.3 | 2018-02-27 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW devised Business Risk Register. All employees will be issued with revised job descriptions in March. New process maps to be instigated for all operations introduce weekly H&S walkaround audits at Wokingham (CD to undertake) following a visit business in Bristol to see H&S programme on 12th March. H&S Communication needs overhaul - SW to provide guidance. Monthly H&S meetings to be instigated, All H&S training to be reviewed - new training matrix to be moved onto new HR system - SM purchased package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire | SW/CD ongoing
13.3 | 2018-04-04 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW devised Business Risk Register to discuss with NH. All employees will be issued with revised job descriptions in July. CD/SW to devise new process maps to be instigated for all operations Weekly H&S walkaround audits at Wokingham (CD to undertake) in May once IPADS and IAuditor purchased H&S Communication needs overhaul - SW to provide guidance. All H&S training to be reviewed - new training matrix to be moved onto new HR system - SM to purchase package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire | SW/CD ongoing
13.3 | 2018-05-01 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW devised Business Risk Register to discuss with NH. All employees will be issued with revised job descriptions in July following Appraisals. CD/SW to devise new process maps to be instigated for all operations Weekly H&S walkaround audits at Wokingham (CD to undertake) in May once IPADS and IAuditor purchased H&S Communication needs overhaul - SW to provide guidance. All H&S training to be reviewed - new training matrix to be moved onto new HR system - SM to purchase package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire | SW/CD ongoing
13.3 | 2018-06-05 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW devised Business Risk Register to discuss with NH. All employees will be issued with revised job descriptions in July CD/SW to devise new process maps to be instigated for all operations Weekly H&S walkaround audits at Wokingham (CD to undertake) in May once IPADS and IAuditor purchased H&S Communication needs overhaul - SW to provide guidance. All H&S training to be reviewed - new training matrix to be moved onto new HR system - SM to purchase package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire PPE - agreed to source new Hi Viz T shirts for all employees as this will eliminate all issues with employees not wearing HI Viz clothing | SW/CD ongoing
13.3 | 2018-07-03 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW to complete Business Risk Register during July and send to NH. All employees will review the new Company Induction video in August and be issued with revised job descriptions CD/SW to devise new process maps to be instigated for all operations Weekly H&S walkaround audits at Wokingham are now in operation in all areas on site and reports are sent to CD to review actions H&S Communication - new H&S notice board has been installed in office canteen near Wet Waste Office All H&S training to be reviewed on 12/7 - all training records will be moved onto new SAGE HR system in August. CE will be custodian of Training system and will have function to highlight when refresher training is required or when certificates expire PPE - new Hi Viz T shirts for all employees - reviewed costs and 4x cost of Hi Viz jackets so not purchasing | SW/CD ongoing
13.3 | 2018-08-07 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW to complete Business Risk Register All employees will review the new Company Induction video in August and be issued with revised job descriptions CD/SW to devise new process maps to be instigated for all operations All H&S training to be reviewed on 12/7 - all training records will be moved onto new SAGE HR system in August. CE will be custodian of Training system and will have function to highlight when refresher training is required or when certificates expire PPE - H&S Reps to remind all employees PPE to be worn at all times whilst on site | SW/CD ongoing
13.3 | 2018-10-02 | Projects currently being undertaken | SW | ISO Accreditation. New format for gaining ISO Accreditation being implemented. SW completed Business Risk Register, issued to Management and placed on BO Ongoing - all employees reviewing new Company Induction video in and being issued with revised job descriptions Ongoing - CD/SW to devise new process maps to be instigated for all operations All H&S training - all training records now on Sage HR Training. CE will be custodian of Training system and will have function to highlight when refresher training is required or when certificates expire | SW/CD ongoing
13.3 | 2018-11-06 | Projects currently being undertaken | SW | ISO Accreditation. completed and passed with no issues Ongoing - all employees reviewing new Company Induction video and all employees have received revised job descriptions Ongoing - CD/SW to devise new process maps to be instigated for all operations | SW/CD ongoing
13.3 | 2018-12-04 | Projects currently being undertaken | SW | ISO Accreditation - ISO next audit is in March 2019. Sean and Chloe will get together in February to go through all points in preparation for Audit the following month. | SW/CD ongoing
13.3 | 2019-04-02 | Projects currently being undertaken | SW | ISO Accreditation - ISO audit is 14th / 15th March at Wokinghmam completed and no issues to report. Achillies Audit - Bennetts 24th / 3rd May SW to attedn on 24th to show Auditor Back Office and Steve Cummings will be there on 3rd May 2019 Bennetts Yard - Building work is ongoing PAT testing on site is now out of date and needs to be sorted as soon as possible
14. H&S Training Requirements
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
14.1 | 2015-03-24 | Incomplete training records for some employees | SS | SS will be reviewing all employee training files to ensure all training requirements are actioned
14.1 | 2015-04-29 | Incomplete training records for some employees | SS | ongoing
14.1 | 2015-07-21 |  | SS | ongoing
14.2 | 2015-03-24 | First Aiders | All | Review each depot and ensure we have correct number of first aiders available at all times. All H&S Reps to source local courses and send employees on either full first aid course or refresher courses during April
14.2 | 2015-04-29 | First Aiders | AM | First Aid training has taken place and additional training will be booked by AM for the remainder required. Namely – Kevin Silvers McCaw, RJP and Tony Harper. Colin King, John Durant & Stephen O'Loughlin are also qualified but expired March 2014 so need refresher courses
14.2 | 2015-05-27 | First Aiders | AM | First Aid – Emergency at work training booked for 4 members of staff on the 16th July 2015 |  | 2015-06-01 | Closed
14.1 | 2015-09-22 |  | SS | ongoing
14.1 | 2015-11-10 |  | SS | SS now has completed the matrix will all employees now on the spreadsheet and will now go through to ensure all employees have correct Training records.
14.1 | 2016-01-12 | New training Matrix will be devised | SS | SS will work with KJ from HRBS to develop a new training matrix for the A1 Group as the current spreadsheet is too large to be printed and read.
14.1 | 2016-03-31 |  | SS | SW/KJ have devised a new training matrix for all three businesses and this is now in operation and SS is completing the detail for all employees this is available on the Back Office. Going forward ANY training undertaken will be recorded on the training matrix and copies of certificates will be on employee HR files |  | closed | 2016-03-01
14.2 | 2015-11-10 | Training Certificates | SS | DK asked if we could place all employee Training Certificates on Back Office. SS to look this project with help from KJ at HRBS. This will allow all Managers easy access so we can then forward to clients when required.
14.2 | 2016-01-12 |  | SS | Training and issuing of Certificates will be arranged for use on all equipment. |  | closed | 2016-02-01
14.3 | 2015-05-27 | Health & Safety at Work refreshers | AM | Training for Health and Safety at work will be progressing shortly, audio visual equipment has been purchased.
14.3 | 2015-07-21 |  | AM | Ongoing
14.3 | 2015-09-22 |  | AM | ongoing
14.3 | 2015-11-10 |  | AM | Mark Pelzer for Tail Lift Training, 8 other members of staff trained on Tele Handler and Counter Balance Fork Lift.
14.3 | 2016-01-12 |  | SW | SW looking into Manual Handling and Safe Loading Train the Trainer
14.4 | 2015-11-10 | Training Course Costs | SS | SS to ensure all Managers let her know when employee booked on course so they can then sign a letter regarding repayment of course costs if they leave the business within 12 months of the course. We have issue where employees taking courses and then leaving. |  | 2015-11-01 | Closed
14.4 | 2016-03-31 |  | SW | Nothing to report SW will discuss with AM before next meeting
14.4 | 2016-05-31 | Health & Safety at Work refreshers | SW | Nothing to report ongoing. AM to continue to conduct All H&S training on site
14.4 | 2016-08-04 | Health & Safety at Work refreshers | SW | Nothing to report ongoing. AM to continue to conduct All H&S training on site
14.4 | 2016-10-26 | Health & Safety at Work refreshers | SW | All employees to receive Company induction prior to starting new role. AM to arrange
14.4 | 2016-12-14 | Health & Safety at Work refreshers | AM | All Agency staff will be trained on Manual Handling upon arrival at site along with induction.
14.4 | 2017-02-22 | Health & Safety at Work refreshers | AM | All up to date and nothing to report
14.4 | 2017-05-24 | Health & Safety at Work refreshers | AM | All up to date and nothing to report
14.4 | 2017-10-03 | Health & Safety at Work refreshers | AM | All up to date and nothing to report
14.4 | 2017-11-28 | Health & Safety at Work refreshers | AM | All up to date and nothing to report
14.4 | 2018-01-30 | Health & Safety at Work refreshers | AM | AM to review all RAMS for the following operations to ensure all employees are trained - Car Transporter, Recovery Vehicle, Skip Lorry, Hook Loader
14.4 | 2018-02-27 | Health & Safety at Work refreshers | AM | AM to review all ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles
15.4 | 2018-04-04 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Am to devise a practical assessment of all Operators and ensure sign to confirm training provided. AM to purchase wrist safety hooks for all employees to ensure clipped on whilst working at height | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles AM to purchase Safety Wrist support for all employees
15.4 | 2018-05-01 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Am to devise a practical assessment of all Operators and ensure sign to confirm training provided. AM has sourced wrist safety hooks for all employees to ensure clipped on whilst working at height SW to provide Crane Operation - RAMS | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles AM to purchase Safety Wrist support for all employees
15.4 | 2018-06-05 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. AM to devise a practical assessment of all Operators and ensure sign to confirm training provided. Wrist safety hooks for all employees to ensure clipped on whilst working at height - ongoing | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles AM to purchase Safety Wrist support for all employees
15.4 | 2018-07-03 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. AM to devise a practical assessment of all Operators and ensure sign to confirm training provided. | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles
15.4 | 2018-08-07 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. AM to devise a practical assessment of all Operators and ensure sign to confirm training provided. | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles
15.4 | 2018-10-02 | Health & Safety at Work refreshers | AM | Ongoing - part complete AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. AM to devise a practical assessment of all Operators and ensure sign to confirm training provided. | AM to ensure all Car Transporter, Skip Lorry, Hook Loader drivers view RA's and SWP. Copies to be signed and kept as record of training and set to be placed in all appropriate vehicles | 2018-10-01 | Closed
15.4 | 2018-11-06 | Health & Safety at Work refreshers | AM | Nothing to report
15.4 | 2019-02-05 | Health & Safety Training | AM | Nothing to report
15.4 | 2019-04-02 | Health & Safety Training | AM | CSCS Training - ongoing | CD ongoing
15. Any other business
Ref No | Open Date | Issue | Owner | Comment/Monthly update |  | Closure Date | Closed
15.1 | 2015-03-24 | Risk Assessments for Tenders | All | Tenders – need to be more organised when they come in, have all the method statements/Risk assessments already there so everyone can access them. Not to leave it to the last minute!
15.1 | 2015-04-29 | Risk Assessments for Tenders | SW | SW has identified 2 outstanding and will liaise with DK/CO
15.1 | 2015-05-27 | Risk Assessments for Tenders | SW | Dean Knott mentioned a requirement for RA and MS to be done on new jobs coming through, this is being dealt with by CO and SW. |  | 2015-06-01 | Closed
15.2 | 2015-03-24 | Fit for work | All | Manual operators – are they fit to do their job, preventing accidents before they happen. Recording accidents for each division.
15.2 | 2015-04-29 | Fit for work | SW | Paul James is listed as long term sick SW to liaise with Manger to look at sending to Occupational Health for Assessment
15.2 | 2015-05-27 | Fit for work | SW | Need to look at bringing long term sick employees back into work on light duties. Need to use Occupational Health provider to make assessment |  | 2015-06-01 | Closed
15.3 | 2015-03-24 | Penalties | All | Ensure we are fully legally compliant in all areas to prevent legal action and risk heavy penalties
15.3 | 2015-04-29 | Penalties | All | All in place - complete |  | 2015-05-01 | Closed
15.4 | 2015-03-24 | CSCS | All | SW discussed possible changes to the CSCS card. More sites now require drivers to have CSCS card before they are allowed on site. CO mentioned NSQ that all Loo Hire employees should have completed the on line training. SS to check
15.4 | 2015-04-29 |  | SW/CO | SW discussed this in depth and NSQ will hopefully be updated to show the CSCS symbol, also discussed was the possibility of putting drivers through PST training however, this is a sponsored program which will be looked into.
15.4 | 2015-05-27 |  | SW/CO | SW gave meeting update and is meeting with CITB on 3/6 to discuss further and report back at next meeting
15.5 | 2015-03-24 |  | AM | Trucco - Is essentially working, Drivers need to place notes on Defects that have been repaired - By whom and what date, this will allow me to close the defect as completed
15.5 | 2015-04-29 |  | AM | AM, investigated this and found that there is no option available to the Driver to mark the defect repaired. AM will contact the Driver to check the results and close each open defect |  | 2015-05-01 | Closed
15.4 | 2015-07-21 |  | SW/CO | Ongoing - SW gave update on process of this project on behalf of the PSE and that it was not likely to become an NVQ programme - this project will be commenced in September 2015
15.4 | 2015-09-22 |  | SW/CO | Ongoing. IP of the PSE and SW met with CITB and PSE are currently looking at costs to ensure the NSQ training programme is able to fir with CITB framework
15.4 | 2015-11-10 |  | SW/CO | Ongoing. IP of PSE will be updating the PSE Committee on 18/11. DK is still sending his employees on CSCS labourer courses until further notice. SW to update H&S committee at next meeting in January 2016
15.4 | 2016-01-12 |  | SW/CO | Ongoing. SW gave committee update from PSE - NSQ/NVQ develop project. Agreed that in meantime A! Group will where necessary ensure employees who require CSCS card undertake CSCS test.
15.4 | 2016-03-31 |  | SW/CO | SW updated Committee on the progress of NVQ course via the PSE. DK reported that all WW employees apart form AM now have CSCS cards.
15.4 | 2016-05-31 | CSCS | SW/CO | SW updated Committee on the progress of NVQ course via the PSE. A1 Group will be used to create new video's from employers to use as part on the new NVQ programme.
15.4 | 2016-08-04 | CSCS | SW/CO | CSCS - SW discussed Telematics in training further details will be announced in early 2017
15.4 | 2016-10-26 | CSCS | SW/CO | SW gave Committee update re new training videos which have now been completed. New NVQ to be launched in Spring 2017. A1 Group to ensure employees undertake course.
15.4 | 2016-12-14 | CSCS | SW/CO | Ongoing
15.4 | 2017-02-22 | CSCS | SW/CO | HY Loo Hire will undertake the Assessor course on behalf of the A1 Group at the end of March. Once course has been approved and rolled out HY will be the A1 Group internal Assessor
15.4 | 2017-05-24 | CSCS | SW/CO | HY Loo Hire completed the Assessor course in March and is now A1 Group internal Assessor. New PSE NVQ will be launched at the end of the summer and A1 will put a number for Operators through the pilot programme
15.5 | 2015-05-27 | Temporary barrier car spares | RJP/MP | talked about getting a temporary strap system to close off area when cars being taken off the rack, Clive going to look into this and purchase
15.5 | 2015-07-21 | Temporary barrier car spares | RJP/MP | Ongoing. AM asked if the tinges on the Forklifts could dislodge cars on other side of the Rack CK confirm the tings were not long enough to touch cars on the other side of rack as only protruded 6 inches other side of vehicle being lifted
15.5 | 2015-09-22 | Temporary barrier car spares | RJP/MP | Agreed to place posts at end of each rack and have a strap system attached which can be operated across the aisle when a forklift is removing a car from the rack
15.5 | 2015-11-10 | Temporary barrier car spares | RJP/MP | It has now been agreed to place permanent posts at the end of the car racks as temporary posts could be moved or damaged - CO has asked Ollie to sort this issue. A chain or strap system will then be placed across whilst a forklift is removing a car for a customer from the rack. We will also need to ensure signage in place to warn public not to enter the area.
15.5 | 2016-01-12 | Temporary barrier car spares | RJP/MP | Nothing to report
15.5 | 2016-03-31 | Temporary barrier car spares | RJP/MP | Nothing to report
15.6 | 2015-11-10 | Temporary barrier car spares | RJP/MP | CO raised issue that if we order new chemicals then we need to send data sheet off to Sypol to obtain full COSHH assessment. We should not be using chemicals without full COSHH assessments.
15.6 | 2016-01-12 | Temporary barrier car spares | RJP/MP | All COSHH Assessment / Data Sheet reviews have been completed and new documents have been placed on the Back Office to ensure in line with requirements from ISOQAR |  | Closed | 2016-01-01
15.5 | 2016-05-31 | Temporary barrier car spares | RJP/MP | Racking in Car Spares - need to get some sort of racking procedure and system in place to prevent members of the public walking down the aisles when looking for car spares and whilst forklift in Operation, discussed various ways of doing this. CO mentioned this had also been raised by our insurers - ongoing
15.7 | 2016-01-12 | Temporary barrier car spares | RJP/MP | A1 Back office which houses all A1 Group H&S information will be developed in order that we have two separate logins. 1 for staff and one for customers. This will allow customers to access important information such as RA's, Method statements and Accreditation details directly and print if necessary.
15.7 | 2016-03-31 | Temporary barrier car spares | RJP/MP | A1 have chosen the domain name for the clients back office which will now be purchased. SW will develop a new "client" back office which will house all client related documents. When required A1 can simply issue the login in details for clients to access the informative documentation which will save time in contacting A1 employees to ask for certain documentation like accreditations etc. |  | 2016-05-01 | Closed
15.8 | 2016-01-12 | Temporary barrier car spares | RJP/MP | NC reported top end yard lighting at Lambs Lane depot was inadequate and CO will speak to John Rushton to complete necessary work to make safe |  | closed | 2016-02-01
15.5 | 2016-08-04 | Temporary barrier car spares | RJP/MP | Temporary car barriers - ordered not fitted, Ollie on holiday so will be done when he's back.
15.5 | 2016-10-26 | Temporary barrier car spares | RJP/MP | Temporary car barriers were erected however not functional therefore chain to be purchased to be placed across bay ends prior to cars being removed from racking.
15.7 | 2016-05-31 | Lifting of Engines | RJP/MP | Russel John raised the issue of lifting engines, we will be looking to purchase purpose built lifting chains/straps.
15.7 | 2016-08-04 | Lifting of Engines | AM | AM to investigate what we can use. Update: Straps/chains for lifting of engines to be purchased. We will be getting quotes for this and looking at what would be the best option.
15.8 | 2016-05-31 | Towing of trailers on motorways and safe servicing of toilets | SW/CO | This will fall under Chapter 8. CO to action |  | 2016-07-01 | Closed
15.5 | 2016-12-14 | Temporary barrier car spares | RJP/MP | Chain Barriers for Car spares are now in place, however we have had to re-order chains as they have now gone missing. Actioned and should be in place within 1 week.
15.7 | 2016-10-26 | Lifting of Engines | AM | Chains purchased for lifting engines now operational |  | 2016-11-01 | Closed
15.9 | 2016-08-04 | Yard PPE | GW | GW talked about PPE in the yard and some of the Loo Hire employees not wearing anything when they are in yard. SW to have a word with all staff to make sure they wear their PPE. Failure to comply will result in potential disciplinary action
15.9 | 2016-10-26 | Yard PPE | GW | All employees reminded to wear PPE via notices
15.5 | 2017-02-22 | Temporary barrier car spares | RJP/MP | Completed |  | 2017-03-01 | Closed
15.9 | 2016-12-14 | Yard PPE | GW | PPE - On site are wheelie bins that contain Hi Viz Tabards and Hard Hats, these are for customers who are instructed to wear this prior to going down to the scrap metal part of the site. |  | 2017-02-22 | Closed
15.6 | 2017-02-22 | Fork Lift driving | GW | GW will attend a Train the Trainer course and will be in the internal Fork Lift trainer. This will ensure NO employee is able to drive a fork lift without the correct licence. All licences MUST be checked prior to ANY employee being able to drive a forklift.
15.4 | 2017-10-03 | CSCS | SW/CO | A1 to be used at guinea pig for PSE NVQ trials in November - CO to organise
15.6 | 2017-05-24 | Fork Lift driving | GW | Ongoing - GW / AM will attend a Train the Trainer course and will be in the internal Fork Lift trainer. This will ensure NO employee is able to drive a fork lift without the correct licence. All licences MUST be checked prior to ANY employee being able to drive a forklift.
15.4 | 2017-11-28 | CSCS | SW/CO | New PSE NVQ slightly delayed and will be tested in January / February - CO to ensure A1 Group are part of the trials
15.4 | 2018-01-30 | CSCS | SW/CO | New PSE NVQ to begin trials in early March and launch to PSE membership in May.
15.4 | 2018-02-27 | CSCS | SW/CO | Ongoing to be launch to PSE members in late spring | SW to liaise with LW/SM/CO re ensuring all Loo Hire Operators undertake course in 2018
16.4 | 2018-04-04 | CSCS | SW/CO | Ongoing to be launch to PSE members in late spring. Trails taking place in April and May | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.6 | 2017-10-03 | Fork Lift driving | GW | Ongoing - AM will attend a Train the Trainer course and will be in the internal Fork Lift trainer. CO and SM will also undertake training All fork lift training is currently up to date
15.7 | 2017-05-24 | Employee Contracts | All | SW mentioned we have a number of employees who commence work without any documentation. All Managers when they offer a job to new employee MUST ensure SS is made aware so a contract/offer letter and new employee information pack is produced on first day. Given recent events in Manchester it is likely we will be required to complete detailed CRB checks for all employees prior to start/allowing then on certain client sites. SS to look at CRB requirements and costs. SW stated maybe be beneficial to look at becoming umbrella CRB centre in order to reduce time for checks to be completed. SW to discuss with CO
15.6 | 2017-11-28 | Fork Lift driving | GW | Ongoing - AM to book onto a Train the Trainer course and will be in the internal Fork Lift trainer. All fork lift training is currently up to date
15.7 | 2017-10-03 | Employee Contracts | All | SW reported significant improvements in this area and nearly all contracts were issued on first day of new employee starting |  | 2017-10-01 | Closed
15.6 | 2018-01-30 | Fork Lift driving | GW | Ongoing - AM and MP to book onto course in February
15.6 | 2018-02-27 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
16.6 | 2018-02-28 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
17.6 | 2018-03-01 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
18.6 | 2018-03-02 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
19.6 | 2018-03-03 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
20.6 | 2018-03-04 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
21.6 | 2018-03-05 | Fork Lift driving | GW | Ongoing | AM to book onto course in March include Telehandler
15.4 | 2018-05-01 | PSE NVQ | SW/CO | Ongoing to be launch to PSE members in late spring. Trails taking place in April and May | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
22.6 | 2018-04-04 | Fork Lift driving | GW | Ongoing | AM to booked onto train the trainer course in April course to include Telehandler
15.8 | 2018-02-27 | Hepatitis Injections | PJ | SW devised employee letter to request if employees wish to have vaccination | LW/PJ/MK to collate list and pass to SM who will book vaccinations for all those who require them
16.8 | 2018-02-28 | Hepatitis Injections | PJ | SW devised employee letter to request if employees wish to have vaccination | LW/PJ/MK to collate list and pass to SM who will book vaccinations for all those who require them
17.8 | 2018-03-01 | Hepatitis Injections | PJ | SW devised employee letter to request if employees wish to have vaccination | LW/PJ/MK to collate list and pass to SM who will book vaccinations for all those who require them
18.8 | 2018-03-02 | Hepatitis Injections | PJ | SW devised employee letter to request if employees wish to have vaccination | LW/PJ/MK to collate list and pass to SM who will book vaccinations for all those who require them
15.4 | 2018-06-05 | PSE NVQ | SW/CO | Ongoing to be launch to PSE members in late Summer. Trials taking place in July with two PSE Operator Members | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.6 | 2018-05-01 | Fork Lift driving | CD | Look at external provider (Belle / BAM) to ensure all Operators have valid licence Refresher Courses for Forklift, Counter Balance and 360 Grab will be rolled out over 2 weeks | CD to organise external training
19.8 | 2018-04-04 | Hepatitis Injections | PJ | ongoing - 50 employees booked in for injections during April |  | March | Closed
15.4 | 2018-07-03 | PSE NVQ | SW/CO | Ongoing - to be launch to PSE members in late Summer. Trials taking place in July with two PSE Operator Members | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.6 | 2018-06-05 | Fork Lift driving | CD | Being completed w/c 4/6/18 | CD to organise external training
15.4 | 2018-08-07 | PSE NVQ | SW/CO | Ongoing - to be launch to PSE members at Showman's Show in Newbury in mid Oct. Trials taking place in August with two PSE Operator Members | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.6 | 2018-07-03 | Fork Lift driving | CD | Completed however, if employee is using Forklift on daily basis then no refresher training required. | CD to organise external training
15.9 | 2018-02-27 | DVSA and Environment Agency | SW | Legislation changes – Currently Highways England, DVSA and Police now have powers to stop by request of DVSA. EA - Fire Prevention plan needs to be reviewed | SW to review FPP
16.9 | 2018-04-04 | DVSA and Environment Agency | SW | EA - Fire Prevention plan needs to be reviewed | SW to review FPP
15.1 | 2018-01-30 | Audits | CO | ISOQAR audit due in March's Accreditation. New format for gaining ISO Accreditation being implemented. SW to conduct Business Risk Register/ re write job descriptions/introduce weekly H&S walkaround audits at Wokingham (CD to undertake). CD to visit business in Bristol to see H&S programme in March. H&S Communication needs overhaul - SW to provide guidance. Monthly H&S meetings to be instigated, All H&S training to be reviewed. Training matrix will b moved onto new HR system ( SM is looking at a package that runs off Sage so it will have the correct staff on there and you will be able to see when certificates expire
15.11 | 2017-11-28 | COSHH | CO | CO completed all COSHH data sheets and associated documentation and now on both Staff and Client Back Offices.
15.1 | 2018-02-27 | Audits | CO | ISOQAR audit due 3rd September at Wokingham March's Accreditation. | SW/CD/CO to ensure all actions completed
16.1 | 2018-02-28 | Audits | CO | ISOQAR audit due 3rd September at Wokingham March's Accreditation. | SW/CD/CO to ensure all actions completed
15.9 | 2018-05-01 | DVSA and Environment Agency | SW | EA - Fire Prevention plan needs to be reviewed | SW to review FPP
17.1 | 2018-04-04 | Audits | CO | ISOQAR audit undertaken in March - no major non conformances to report and only recommendations. Need to ensure we are ready for next Audit on September 4th as will be under new ISO format | SW/CD/CO to ensure all actions completed
15.11 | 2018-02-27 | COSHH | CO | CO to review all COSHH is currently up to date | SW to ensure all COSHH Assessments are in date on back office
15.9 | 2018-06-05 | DVSA and Environment Agency | SW | Ongoing - SW to complete in June | SW to review FPP
15.1 | 2018-05-01 | Audits | CO | Nothing to report
16.11 | 2018-04-04 | COSHH | CO | All COSHH Assessments are up to date and on Back Office
15.9 | 2018-07-03 | DVSA and Environment Agency | SW | SW has reviewed document and updated to reflect Operational and Site changes will upload to Back Office
15.1 | 2018-06-05 | Audits | CO | ISO Audit 3rd September
15.11 | 2018-05-01 | COSHH | CO | All up to date - ongoing as and when new products are purchased
15.4 | 2018-10-02 | PSE NVQ | SW/CO | Ongoing - to be launched to PSE members at Showman's Show in Newbury in mid Oct. | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.9 | 2018-08-07 | DVSA and Environment Agency | AM | Nothing to report
15.1 | 2018-07-03 | Audits | CO | ISO Audit - SW / CD working to ensure all documentation and training completed
15.11 | 2018-06-05 | COSHH | CO | All up to date - ongoing as and when new products are purchased
15.4 | 2018-11-06 | PSE NVQ | SW/CO | Ongoing - launched to PSE members at Showman's Show in Newbury in mid Oct. SW report a number of administration issues still need to be resolved with Human Focus. | SW to liaise with LW/SM/CO re ensuring all Loo Hire /Wet Waste Operators undertake course in 2018
15.9 | 2018-10-02 | DVSA and Environment Agency | AM | Nothing to report
15.1 | 2018-08-07 | Audits | CO | ISO Audit - SW / CD working to ensure all documentation and training completed by 3rd September
15.11 | 2018-07-03 | COSHH | CO | Need to ensure CO reviews any outstanding COSHH documents required on Alcumus and these are uploaded / updated on Back Office
15.9 | 2018-11-06 | DVSA and Environment Agency | AM | DVLA - Portal to check records are up to date, they also don't like FORS as they think it's a money making exercise.
15.1 | 2018-10-02 | Audits | CO | ISO Audit - September - passed Audit with two minor non conformances - excellent result. Next Audit in March 2019 SW to contact all Site to arrange to conduct annual external H&S audit during Oct and Nov
15.4 | 2019-04-02 | PSE NVQ | SW/CO | ongoing | SW/LW ongoing
15.11 | 2018-11-06 | COSHH | CO | Nothing to report
15.12 | 2018-10-02 | H&S Training | SS | Training Database now live with all employee training recorded. Demonstrated during ISO audit and positive comments received.
15.13 | 2018-02-27 | Driver Vehicle Folder | SS | Driver Vehicle folder to be created for all operational vehicles – | AM &SW to organise new driver folders to be keep in all vehicles
15.13 | 2018-04-04 | Driver Vehicle Folder | SS | Ongoing
15.14 | 2018-02-27 | Banks person - Wokingham | MP | MP raised issued that with large volume of traffic now entering Wokingham site should look to have permanent Banks person operating as vehicles do reverse onto weigh bridge and possible accident could occur | MP to discuss with GW report back at next meeting
15.13 | 2018-05-01 | Driver Vehicle Folder | SS | Ongoing
16.14 | 2018-04-04 | Banks person - Wokingham | MP | 3 employees on site to act as Banks person and AM to organise short training session as training video now on Back Office | AM to ensure all Banks Person training completed
15.13 | 2018-06-05 | Driver Vehicle Folder | SS | Ongoing
15.14 | 2018-05-01 | Banks person - Wokingham | AM | 3 employees on site to act as Banks person and AM organised training session with BAM | AM to ensure all Banks Person training completed | closed | 2018-05-01
15.9 | 2019-04-02 | DVSA and Environment Agency | AM | Nothing to report
15.1 | 2019-04-02 | Audits | CO | ISO Audit - completed no isues to report H&S Documentation - ongoing Achillies Audit - Bennetts 24th / 3rd May SW to attedn on 24th to show Auditor Back Office and Steve Cummings will be there on 3rd May 201
15.11 | 2019-04-02 | COSHH | CO | Ongoing - nothing to report
15.16 | 2018-11-06 | Forklift checks | All | CD stated needs all forklifts to undergo a weekly check and reports sent to her. Even if forklift no been used check still needs be completed - suggested every Friday at Bennetts.
15.16 | 2018-12-04 | Forklift checks | All | Completed and now part of weekly Depot process | Completed in December 2018 | closed
15.12 | 2019-04-02 | HSE | CD | Nothing to report
15.17 | 2018-12-04 | IAuditor | CD | CD has explained process to all Depots apart from Thame. Currently devising reports for each depot will be live in January 2019
15.18 | 2018-11-06 | H&S Notice Boards - Other Depots | Cd | CD has ordered new H&S boards for Coventry and Bennetts and will be visiting Bridgend and Thame in coming weeks to sort.
15.18 | 2018-12-04 | H&S Notice Boards - Other Depots | Cd | Boards no in place all Depots apart from Thame
15.15 | 2019-04-02 | FORS Silver/Gold | AM | ongoing
15.17 | 2019-04-02 | IAuditor | CD | All Depots now have IAuditor operational
15.18 | 2019-04-02 | H&S Notice Boards - Other Depots | CD | All Depots now have all Notice boards up to date and operational
15.19 | 2019-04-02 | Employee Appraisals | CD | All Apprialsa will take place in September 2019 Poster and small business card, ongoing - credit card size for all employee will detail back office login and contents - to be placed on all notice boards at all Sites - onging | SW to divise poster
15.2 | 2019-04-02 | AOB | SW | Nothing to report
16. Date of next meeting
Tuesday 7th May 2019