## Blank Template
A1 Group Risk Assessment Form
CCTV Surveying/Traverse Entry
Date: |  | 2018-07-01 | [8 empty] | Security and Retention Period: Standard
Assessment Type : |  | Re-Assessment | Conducted By: |  | Sean Whittle H&S Advisor | [5 empty] | Version 1.0
A | B | C | D |  | E | F | G | H | I | J | K
Ref No. | Activity / Task / Equipment | Controls currently in place | Threat / Hazard | Frequency | Value 1-5 | Vulnerability | Value 1-5 | Impact | Value 1-5 | Risk Value (ExGxl) | Corrective Action requirement
1 | Park A1 Group Vehicle | Park vehicle on road and close to the working area/manhole. Ensure Traffic Management vehicle is in place before exiting A1 Vehicle | Being hit by other vehicles daily | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
2 | Place out safety barriers around working area/manhole | Safety barriers erected in area around manhole | Manual handling of barriers | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
3 | Exit Vehicle wearing Hi visibility Jacket | Hi visibility jackets provided and worn at all times | No wearing jackets not being seen by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
4 | Lift manhole cover using manhole keys | Two employees use manhole keys to lift manhole cover using correct manual handling techniques | Lifting heavy items - damage to back | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
5 | Place manhole cover away from working area | Place away from working area safe working distance away | Dropping manhole on feet/ trip hazard | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
6 | Allow to ventilate for 15 minutes. | Operation conducted by trained A1 Group employees | Negligible | Very unlikely | 1 | Developed Management process in place | 2 | Negligible | 1 | 2 | Not required
7 | Lower Gas monitor to invert and leave for 5 minutes | If no alarm is sounded work may proceed. If gas monitor indicates hazardous gases the client’s responsible person will be notified and work will not proceed - Operation only perfromed by fully trained A1 group employees | being overcome by gases | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
8 | The gas monitor will be used to provide constant monitoring of the working environment. One engineer will be the designated top man, who will control the equipment on the surface and report to the charge hand. If the manhole is less than 3 meters deep, a winch is required with one man on top. If the manhole is over 3 meters deep, 3 men are needed on top with 1 man entering. He will also have a 10mm B.A. escape set. | If the gas monitor signals an alarm, the engineer working in the confined space will don his escape set and immediately leave the confined space. | being overcome by gases | Very unlikely | 1 | Developed Management process in place | 2 | Catastrophic / Death | 5 | 10 | Not required
| The CCTV surveying work will then be carried out as required by the client’s specification for a particular contract. For this contract, all CCTV surveying work will be carried out in accordance with the “MODEL CONTRACT DOCUMENT FOR SEWER CONDITION INSPECTION” (May 1994). | Operation conducted by trained A1 Group employees |  | Very unlikely
9 | Replace manhole cover | Using manhole keys and using correct manual handling procedure | Lifting heavy items - damage to back / dropping manhole on feet | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
10 | Remove barriers from working area | Safely store barriers in A1 Group van using correct manual handling techniques. | Damage to back | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
11 | Store barriers on vehicle | Lift barriers onto vehicle using correct manual handling techniques and ensure stored safely in vehicle | Lifting heavy items - damage to back/damage to feet | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
12 | Exit Pavement in vehicle | Ensure road is clear of moving traffic using van signals to exit pavement in a controlled manner | Not using correct signals and vehicle being hit by other traffic | Very unlikely | 1 | Developed Management process in place | 2 | Workaround possible / Serious injury | 3 | 6 | Not required
Value | Frequency | Vulnerability | Impact |  |  |  | Risk Value | Meaning | Requirement
5 | Certain | Unmanaged | Catastrophic / Death |  |  |  | 40+ | Very High Risk | Improvement required
4 | Likely | Reactive Management | SLA compromised / Permanent Disability |  |  |  | 31 to 40 | High Risk | Improvement required
3 | May Happen | Workaround Planned | Workaround possible / Serious injury |  |  |  | 21 to 30 | Medium Risk | Improvement opportunity
2 | Unlikely | Developed Management | Easy Workaround / Minor injury |  |  |  | 11 to 20 | Low Risk | No action required
1 | Very unlikely | Negligible | Negligible |  |  |  | 1 to 10 | Very Low Risk | No action required
Note on D7: Type either of the following: a) Initial b) Re-Assessment