## Actions and Improvements
Action and Improvement Log 2022
Last Review date |  | 2022-11-21
ALL SITES
WOKINGHAM
LAMBS LANE
BRIDGEND
BENNETTS YARD
OXFORD
COVENTRY
PORTSMOUTH
Action No. | Date Raised | Depot | Audit Identification | Process improvement issue | Corrective action (fix at source) | Preventive Action (prevent re-occurrence) | Action to be undertaken by | Date Closed
42 | 2017-07-21 | Wokingham | EAA | Areas of concrete at the north end of the site in and around the “Main vehicle crushing and recycling area” are deteriorating and becoming broken and damaged. These areas are in the vicinity of areas where un-depolluted ELVs are stored and treated and where compaction of ELVs takes place. (Drainage to the depollution shed appears blocked meaning spillages could run into these areas.) | CO to resolve | Ongoing | Clive Owen | ongoing
185 | 2018-03-06 | Oakley | H&S | Lone working | Introduce lone working policy | Review lone working arrangements regulary and adapt policy or training to suit | Ivor Swatton | ongoing
186 | 2018-03-06 | Oakley | H&S | Yard Pot holes large pots holes collecting water which could freeze | Fill 2 pot holes in yard | Monitor yard flooring and fill in any pot holes - this could be added to the IAuditor report | Ivor Swatton | ongoing
208 | 2019-03-14 | All | EAA | Provide evidence of action plans and targets to support the objectives they have set within their integrated management system | Devise targets to support the objectives within integrated management system | Enusre this is reviewed monthly | Clive Owen | ongoing
209 | 2019-03-14 | All | EAA | Consider the lifecycle approach within the operational processes of the organisation and supporting aspects and impacts | Continualy review processes to ensure in line with required outcome | Enusre this is reviewed monthly | Clive Owen | ongoing
235 | 2020-10-15 | Bennets Yard | H&S | Gas Spray ventilation | Ensure current fan is not covered and also consider additional secondary fan in 2nd spray area. | Review on weekly walkrounds | Paul James / Laura White | Ongoing
269 | Jan - Sept | Due to COVID 19 no actions have been identified and all those above are ongoing
271 | 2020-12-01 | Oakley | H&S | Lone Working At times only one employee on site at time | Introduce lone working policy | Review on weekly walkrounds | Martyn Kirkham | Ongoing
305 | 2020-12-01 | Bridgend | H&S | Storage Files on Mezzanine Floor | Purchase lockable fireproof cabinets to store files or place boxes in fireproof container | Review on weekly walkrounds | Spencer Morgan | Ongoing
315 | 2021-05-01 | Wokingham | H&S | Apprenticeship Scheme | Contact local colleges for details | Review at Future H&S meetings | H&S Administrator | Ongoing
316 | 2021-09-01 | All | H&S | Fire Evacuations Tests | H&S Reps to undertake before end of 2021 | Review at Future H&S meetings | Depot H&S Reps | Ongoing
317 | 2021-10-01 | All | H&S | Review all H&S Actions and ensure completed | SW to contact H&S Reps for update from 2020 Actions | Review at Future H&S meetings | Depot H&S Reps | Ongoing
319 | 2021-12-01 | Bridgend | H&S | Roller shutter roof | Neeed to repair broken roof | Review at Future H&S meetings | Depot H&S Reps | Ongoing
320 | 2022-01-01 | Bridgend | H&S | Emergency lighting check | Ensure annual tests for emergency lighting - contact A1 Group Electrician | Review at Future H&S meetings | Depot H&S Reps | Ongoing
331 | 2022-01-01 | Coventry | H&S | Emergency lighting check | Ensure annual tests for emergency lighting - contact A1 Group Electrician | Review at Future H&S meetings | Kathryn James | Ongoing
332 | 2022-01-01 | Coventry | H&S | Emergency exit from Kitchen leads out with step on other side of door | Ensure area is hash marked to prevent vehicles parking and blocking fire exit and warning signs | Review at Future H&S meetings | Kathryn James | Ongoing
333 | 2022-01-01 | Coventry | H&S | Gas Bottle Storage | Ensure all bottles are locked in cage at back of yard | Review at Future H&S meetings | Kathryn James | Ongoing
334 | 2022-01-01 | Oakley | H&S | Yard Pot hole | Review pot holes and fill with gravel | Review on weekly walkrounds | Emma Pomroy | Ongoing
335 | 2022-01-01 | Oakley | H&S | First Aiders/Fire Marshals | Ensure correct number of employees are trained on site | Review on weekly walkrounds | Emma Pomroy | Ongoing
336 | 2022-01-01 | Oakley | H&S | Fire Extingushers left on floor | Ensure all visable and hooked on wall | Review on weekly walkrounds | Emma Pomroy | Ongoing
337 | 2022-01-01 | Oakley | H&S | Tyres stored under stairs | Create Tyre bay away from stairwell | Review on weekly walkrounds | Emma Pomroy | Ongoing
338 | 2022-01-01 | Oakley | H&S | Emergency lighting check | Ensure annual tests for emergency lighting - contact A1 Group Electrician | Review on weekly walkrounds | Emma Pomroy | Ongoing
339 | 2022-01-01 | Portsmouth | H&S | First Aiders/Fire Marshals | Ensure correct number of employees are trained on site | Review on weekly walkrounds | Matt Doody/James Nicklin | Ongoing
346 | 2022-03-01 | Portsmouth | H&S | Some site signage missing | Conduct site signage audit | Review on weekly walkrounds | Matt Doody/James Nicklin | Ongoing
347 | 2022-04-01 | Wokingham | H&S | Pot Holes need filling | Engage local builder to complete | Review on weekly walkrounds | Garry Webb / John Stubbs | Ongoing
348 | 2022-04-01 | Al Depots | H&S | Complete Fire Evacuation tests | All Depots Reps to arrange Fire Test | Review on weekly walkrounds | All Depot Managers | Ongoing
349 | 2022-11-01 | Bennets Yard | H&S | Gas Spray garage - full review of equipment / PPE and ventilation | Current porcess dangerous as limitted ventialtion / equipment not checked and PPE not worn all solvents etc left out and using gas heater to heat area with solvent fumes present | Review on weekly walkrounds | Dean Corbin | Ongoing
350 | 2022-11-01 | Bennets Yard | H&S | Flammable liquids storage | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Paul James / Laura White | Ongoing
351 | 2022-11-01 | Oakley | H&S | Yard Pot hole | Review pot holes and fill with gravel | Review on weekly walkrounds | Emma Pomroy | Ongoing
352 | 2022-11-01 | Oakley | H&S | First Aiders/Fire Marshals | Ensure correct number of employees are trained on site | Review on weekly walkrounds | Emma Pomroy | Ongoing
353 | 2022-11-01 | Oakley | H&S | Fire Extingushers left on floor | Ensure all visable and hooked on wall | Review on weekly walkrounds | Emma Pomroy | Ongoing
354 | 2022-11-01 | Oakley | H&S | Tyres stored under stairs | Create Tyre bay away from stairwell | Review on weekly walkrounds | Emma Pomroy | Ongoing
355 | 2022-11-01 | Oakley | H&S | Emergency lighting check | Ensure annual tests for emergency lighting - contact A1 Group Electrician | Review on weekly walkrounds | Emma Pomroy | Ongoing
Note on D16: Sean Whittle: Either H&S = Health & Safety ISOQAR EAA

## Closed
Closed Actions
ALL SITES
WOKINGHAM
LAMBS LANE
BRIDGEND
BENNETTS YARD
Oxford
COVENTRY
Action No. | Date Raised | Depot | Audit Identification | Process improvement issue | Corrective action (fix at source) | Preventive Action (prevent re-occurrence) | Action to be undertaken by | Date Closed
1 | 2015-07-21 | Wokingham | H&S | Barriers at end of Car racks to prevent public access when working | A barrier system needs installing | All outstanding actions completed | Garry Webb | 2016-12-01
2 | 2015-09-22 | Wokingham | H&S | Fire Prevention Plan | Devise Fire Prevention plan of site | Completed by H&S Consultant | Sean Whittle | 2015-10-01
3 | 2015-09-22 | Wokingham | H&S | Full integrated Fire Alarm system at Wokingham site | CO to source supplier of system and arrange for purchase and installation | All outstanding actions completed | Alan McGregor | 2016-03-01
5 | 2015-10-26 | All | ISOQAR | Risk assessments for the Company require a review | Risk assessments to be issued to individuals for review. | All outstanding actions completed | Clive Owen | 2016-01-01
6 | 2015-10-26 | All | ISOQAR | COSHH assessments are due a review | Sypol site visited | All outstanding actions completed | Clive Owen | 2016-01-01
7 | 2015-10-26 | All | ISOQAR | Training matrix needs to be reviewed and updated. | KJ & SS working on new training matrix and will complete by end of February | All outstanding actions completed | Sarah Sheppard | 2016-04-01
8 | 2016-01-06 | All | H&S | New Back office for Customers | KJ to build new Back Office for Customers to access certain relevant documents | Completed by H&S Consultant | Sean Whittle | 2016-05-01
9 | 2016-04-04 | All | ISOQAR | Business Continuity Plan | CO/SW to disucss on 31/5 | Ongoing | Sean Whittle / Clive Owen | 2018-06-01
10 | 2016-05-10 | All | ISOQAR | Quality Policy needs to be reviewed and updated | CO/SW to disucss on 31/5 | Ongoing | Sean Whittle | 2017-09-01
11 | 2016-05-10 | All | ISOQAR | Create site vist form which will need to be completed upon ANY site vist including internal sites. This will then be scanned and uploaded to B/O | CO to inform SW of what to include and SW to ask KJ to complete | Ongoing | Sean Whittle | 2017-10-01
12 | 2016-04-17 | Lambs Lane | H&S | Plasters need to be replaced in the office | SS to audit fist aid kits | All outstanding actions completed | Laura White | 2016-04-01
13 | 2016-04-17 | Lambs Lane | H&S | Eye wash needs to be replaced after incident where someone had something blown into their eye. | SS to audit fist aid kits | All outstanding actions completed | Laura White | 2016-04-01
14 | 2016-04-17 | Lambs Lane | H&S | Fire alarm; cannot be heard in office areas when set off in the workshop. | AM to resolve | All outstanding actions completed | Martyn Kirkham | 2016-04-01
15 | 2016-04-17 | Lambs Lane | H&S | Work equipment; is it inspected by the insurers? (Compressor, welding regulators, lifting items, fork lift) | AM to resolve | Fork Lift only remainer checked internally | Martyn Kirkham | 2016-04-01
16 | 2016-04-17 | Lambs Lane | H&S | Fire exit in workshop is blocked | General housekeeping and remnd employees not to block | All outstanding actions completed | Laura White | 2016-04-01
17 | 2016-04-17 | Lambs Lane | H&S | COSHH assessments required for the vehicle maintenance products | CO to review and KJ to place on BO | All outstanding actions completed | Clive Owen | 2016-04-01
18 | 2016-04-17 | Lambs Lane | H&S | Storage of oils need to be sorted; put into bunds and placed inside rather than outside. | LW to sort | All outstanding actions completed | Laura White | 2016-04-01
19 | 2016-04-17 | Lambs Lane | H&S | Waste streams still need to be segregated; waste filters, batteries, oily rags etc. | CO to sort | All outstanding actions completed | Laura White | 2016-04-01
20 | 2016-04-17 | Lambs Lane | H&S | Waste note required for recycling from Woodside | CO to resolve | All outstanding actions completed | Laura White | 2017-01-01
21 | 2016-04-17 | Lambs Lane | H&S | Risk assessment for the workshop doesn't cover the Use Of the vehicle pit, vehicle movement in the yard, office areas etc. | SW to review and complete new RA | All outstanding actions completed | Sean Whittle | 2017-01-01
22 | 2017-01-24 | All | ISOQAR | COSHH; these all need to be reviewed. Where is the one for the Deb instant foam? | CO to review | All outstanding actions completed | Clive Owen | 2017-01-01
23 | 2017-01-24 | All | H&S | PAT testing; has this all been completed | Completed CO to send KJ copies to place on BO | Wokingham on BO - remainder ongoing | Clive Owen | 2017-11-01
24 | 2017-01-24 | All | H&S | Fire risk assessment for BOTH sites needs to be reviewed – | SW to review with CO | All outstanding actions completed | Sean Whittle | 2017-01-01
25 | 2017-01-24 | Wokingham | ISOQAR | Download weighbridge and non-ferrous calibration certificates | CO to complete and send to KJ | Ongoing | Alan McGregor
26 | 2017-01-24 | All | H&S | Update fire marshall list on back office | SS and AM to complete | All outstanding actions completed | Sarah Sheppard | 2017-01-01
27 | 2017-01-24 | All | H&S | Undertake fire evacuation form for the evacuations taken | AM to undertake | All outstanding actions completed | Alan McGregor | 2017-01-01
28 | 2017-01-24 | All | H&S | Check first aid kits and make sure all are stocked; check the eye wash in the de-pollution area | SS to audit fist aid kits | All outstanding actions completed | H&S Reps | 2017-01-01
29 | 2017-01-24 | All | H&S | Review Health and safety action plan – is this up to date | SW To update | updated still ongoing | Clive Owen/NH | 2017-10-01
30 | 2017-01-24 | Lambs Lane | ISOQAR | Loo hire site; all work equipment records up to date. Compressor? Vehicle maintenance | AM to complete | All outstanding actions completed | Laura White | 2017-01-01
31 | 2017-02-01 | Wokingham | ISOQAR | Fire extinguishers in the non-ferrous stores had not been serviced in line with the planed schedule. | AM to complete | Ongoing | Clive Owen | 2017-10-01
32 | 2017-02-01 | Wokingham | ISOQAR | Unibond sealant (in use in workshop)– anti mould 300ml – Not on COSHH listings/Register | CO to complete and send to KJ | COSHH Assessment on Back Office | Clive Owen | 2017-10-01
33 | 2017-02-01 | Wokingham | ISOQAR | Adblue to also be added to the COSHH assessment listings as discussed | CO to complete and send to KJ | COSHH Assessment on Back Office | Clive Owen | 2017-10-01
34 | 2017-02-01 | Wokingham | ISOQAR | Safeshield 50 5L (located in the stores area – Not on COSHH listings/Register | CO to complete and send to KJ | All outstanding actions completed | Clive Owen | 2017-10-01
35 | 2017-02-22 | All | H&S |  | AM to complete | All outstanding actions completed | Alan McGregor | ongoing
36 | 2017-02-22 | All | H&S | Drug Tesign kits to be purchased | SS to purchase new kits | SS purchased new drug testing kits A number of Random tests completed | Sarah Sheppard | 2017-02-01
37 | 2017-02-22 | All | H&S | Fork lift training - agreed to send employee to become internal trainer | AM to organise training | Ongoing | Alan McGregor | 2018-07-01
38 | 2017-05-24 | All | H&S | Review all RA's | SW to review all RA's | All RA's reviewed and updated and uploaded to both staff and customer Back Offices | Sean Whittle | 2017-05-01
39 | 2017-05-24 | Wokingham | H&S | Extend main office | CO to organise office extension | work commenced to extend main office area July 17 completion due Nov 2017 | Clive Owen | 2017-10-01
40 | 2017-05-01 | All | H&S | Vehicle cameras | Am to organise fitting of new cameras to all vehicles | All outstanding actions completed | Alan McGregor | 2017-05-01
41 | 2017-05-01 | All | H&S | Employee Contracts - some employee not receiving contracts when the start | SS to ensure Managers let her know of all new starters on or before start date | All outstanding actions completed | Sarah Sheppard | 2017-05-01
44 | 2017-10-17 | Wokingham | ISOQAR | October 2017 follow up from minor non-conformance raised in surveillance 4 audit Feb 2017– fire extinguishers in the non- ferrous sheds were inspected as part of the site walk. It was noted that the extinguishers in this area (aswell as other areas) showed last service dates of 2015/2016 and had not been serviced in line with legal/regulatory requirements over this period. This issue has been raised to a major non-conformance issue. | CO to resolve | External compnay have replaced all out of date extingushers and a map of all extingushers locations being devised | Clive Owen | 2017-10-01
45 | 2017-09-08 | Bennets Yard | H&S | In workshop store area – there are items over 20kgs stored above head height | Tidy workshop shelves and place heavy items on lower shelves | Review completed and items moved | Paul James | 2017-11-01
46 | 2017-09-08 | Bennets Yard | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals details on notice boards | Conduct a full assessment of the legal documentation required and the H&S signage required at various locations around the site. This will include the following: Clearly identified emergency evacuation area Create separate H&S Board and display signed H&S Policy, insurance details Pictures and contact details for both first aiders and fire marshals PPE usage signage Speed limit signs on main entrance and arounds site Reception signage Visitor sign in book in general office Site H&S leaflet handed to all visitor | Ongoing | Paul James | 2018-07-01
47 | 2017-09-08 | Bennets Yard | H&S | The canteen near the Offices has no PAT testing completed | Engage external PAT testing competent person | all PAT testing completed by competant person | Paul James | 2017-11-01
48 | 2017-09-08 | Bennets Yard | H&S | No record of legionella test conducted on shower near canteen area | Engage external legionella testing competent person | Ongoing | paul James | 2018-07-31
49 | 2017-09-08 | Bennets Yard | H&S | Only one first kit on display | Purchase another first aid kit for general office | Ongoing | Paul James | 2018-12-01
50 | 2017-09-08 | Bennets Yard | H&S | There was no area for employees to store clothing and bags | Purchase 6 lockers for employees to store clothing | Ongoing | Paul James | 2018-12-01
51 | 2017-09-08 | Bennets Yard | H&S | Fire extinguisher checks needs to be conducted and replaced if required | Contact Fire Extinguisher company that provide for rest of A1 group to conduct audit and supply correct equipment | Ongoing | Paul James | 2018-06-30
52 | 2017-09-08 | Bennets Yard | H&S | There was no evidence of employees having been trained in fire extinguisher usage | Contact Fire Extinguisher company that provide for rest of A1 group to provide basic employee training | Ongoing | Paul James | 2018-06-01
53 | 2017-09-08 | Bennets Yard | H&S | Fire signage evacuation process and site should be visible in canteen and general office. | Devise site visitor booklet Devise sign evacuation posted with exit routes | Ongoing | Paul James | 2019-01-01
54 | 2017-09-08 | Bennets Yard | H&S | No separate visitor parking area | Devise two spaces next to main office | Ongoing | Paul James | 2018-05-01
55 | 2017-09-08 | Bennets Yard | H&S | No road markings / designated walkways / staff parking area | These should be relocated in far end of yard or removed from or limited on site | Employee parking area has been tarmaced and signage placed in area | Paul James | 2018-02-01
56 | 2017-09-08 | Bennets Yard | H&S | No visitor sign in process / no H&S information given to visitors on site / no PPE for visitors | Ensure PPE purchased including visitor PPE jackets and bump caps Contact signage company to conduct audit of site and supply and erect signage | Ongoing | Paul James | 2019-01-01
57 | 2017-09-08 | Bennets Yard | H&S | Smoking area is immediately outside office. No smoking signs present on site | Smoking area needs relocating on site and ashtray purchased to dispose of cigarette ends. No smoking signage needs to be purchased and placed at various locations on site | Ongoing | Paul James | 2019-01-01
58 | 2017-10-17 | Bridgend | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals details on notice boards | A copy of the A1 H&S Policy need to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details | Ongoing | Spencer Morgan | 2017-10-01
59 | 2017-10-17 | Bridgend | H&S | A number of flammable products in workshop and cleaning equipment in drying room were not stored correctly | A lockable cupboard should be purchased to store all flammable liquids and cleaning products when not in use and key held by responsible person | Ongoing | Spencer Morgan | 2018-06-01
60 | 2017-10-17 | Bridgend | H&S | Smoking area is immediately outside staff canteen but employee smoke outside main office. | Remind employees to smoke in designated areas only. | Ongoing | Spencer Morgan | 2017-10-01
61 | 2017-10-17 | Bridgend | H&S | Some cleaning materials were in various open locations around the site. | A lockable cupboard should be purchased to store all potentially hazardous material when not in use and key held by responsible person | Ongoing | Spencer Morgan | 2018-06-01
62 | 2017-10-17 | Bridgend | H&S | Some depot fire extinguishers were stored on the floor and labels were illegible | Fire extinguisher tests whilst conducted some of the labels have become un readable and the extinguishers should ideally be stored off the floor and on a wall with signage to indicate their location and use. | Ongoing | Spencer Morgan | 2017-10-01
63 | 2017-10-17 | Bridgend | H&S | At present there is only one trained first aiders. Additional person needs to be trained to provide cover | Arrange first aid training for another site employee 0 course booked for Dave in Nov 17 | Ongoing | Spencer Morgan | 2018-12-01
64 | 2017-10-17 | Bridgend | H&S | PAT testing not present on any electrical equipment on site | Competent person to conduct PAT testing on all electrical equipment | Ongoing | Spencer Morgan | 2018-12-01
65 | 2017-10-17 | Bridgend | H&S | No record of legionella test conducted on shower in canteen area | Competent person to conduct legionella test in shower and ensure conducted at regular intervals | Ongoing | Spencer Morgan | 2018-12-01
66 | 2017-10-17 | Bridgend | H&S | Road markings / designated walkways / staff parking area were beginning to ware and need to be re painted | RE paint all defined walkways | Ongoing | Spencer Morgan | 2018-12-01
67 | 2017-10-17 | Bridgend | H&S | Side door to yard area was unsecured and moves in the wind and could hit either employees exiting Workshop | Ensure gate is secured at all times or closed and place sign to remind employees to check at all times | Ongoing | Spencer Morgan | 2017-10-01
68 | 2017-10-17 | Bridgend | H&S | Low access via office roofs and via climbing up window bars | Place fragile roof signs around the building to warn employees and contractors. | Ongoing | Spencer Morgan | 2018-11-01
69 | 2017-10-17 | Bridgend | H&S | Area untidy / hoses could be trip hazards / wearing PPE | Tidy area / store hoses and all employees to wear PPE at all times / consider cordoning off area to prevent water entering other area | Ongoing | Spencer Morgan | 2017-10-01
70 | 2017-10-24 | Coventry | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals details on notice boards | A copy of the A1 H&S Policy need to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details | Ongoing | Casey Owen | 2017-04-01
71 | 2017-10-24 | Coventry | H&S | A number of flammable products in workshop and cleaning equipment in drying room were not stored correctly | A lockable cupboard should be purchased to store all flammable liquids and cleaning products when not in use and key held by responsible person | All aresols are in the lockablew cupboard | Casey Owen | 2017-11-01
72 | 2017-10-24 | Coventry | H&S | Annual gas boiler in main Warehouse needs to be tested and arrange for annual test | Arrange with Certified Gas Boiler service company to provide certificate of safety | Being Carried out next week. | Casey Owen | 2017-11-01
73 | 2017-10-24 | Coventry | H&S | Smoking area is immediately outside staff canteen but employee smoke outside main office. | Remind employees to smoke in designated areas only. | Have text employees and made note for our next meeting | Casey Owen | 2017-11-01
74 | 2017-10-24 | Coventry | H&S | Some depot fire extinguishers were stored on the floor and labels were illegible | Fire extinguisher tests whilst conducted some of the labels have become un readable and the extinguishers should ideally be stored off the floor and on a wall with signage to indicate their location and use. | Fire saftey inspection has been carried out. | Casey Owen | 2017-11-01
75 | 2017-10-24 | Coventry | H&S | At present there is only one trained first aiders. Additional person needs to be trained to provide cover | Picture and contact details of First Aiders at Depot | Will be compleate by next week | Casey Owen | 2018-04-01
76 | 2017-10-24 | Coventry | H&S | No Fire Evacuation procedures visible around site | Print of fire evacuation plan and place in Officers / Canteens and Workshop / Warehouse’s | Need to obtain one of these?Can you provide? | Casey Owen | 2018-04-01
77 | 2017-10-24 | Coventry | H&S | No record of legionella test conducted on shower in canteen area | Competent person to conduct legionella test in shower and ensure conducted at regular intervals | This is now carried out weekly by our cleaners | Casey Owen | 2017-10-01
78 | 2017-10-24 | Coventry | H&S | Side door to yard area was unsecured and moves in the wind and could hit either employees exiting Workshop | Ensure gate is secured at all times or closed and place sign to remind employees to check at all times | Gate is now secured into the ground to provent moving in the wind. | Casey Owen | 2017-11-01
79 | 2017-10-24 | Coventry | H&S | Beam expose in archive area on Mezzanine floor | Place yellow warning tape and bump protection around beam and place warning signage in area and on beam | Done | Casey Owen | 2017-11-01
80 | 2017-10-24 | Coventry | H&S | Water coming into Warehouse and Workshop and falling onto live electrical socket | Repair hole in roof and seal/treat and repaint all walls affected | Done | Casey Owen | 2017-11-01
81 | 2017-10-24 | Coventry | H&S | Area untidy / hoses could be trip hazards / wearing PPE | Tidy area / store hoses and all employees to wear PPE at all times. Consider cordoning off area to prevent water entering other areas Secure hose pipe that runs along back of Warehouse/Workshop to wall | Done | Casey Owen | 2017-11-01
82 | 2017-10-24 | Coventry | H&S | No salt and grit for site to be used in freezing conditions | Purchase salt and grit bin and place outside Workshop. To be used in freezing conditions in yard areas. | Now have supply | Casey Owen | 2017-11-01
85 | 2017-10-12 | Lambs Lane | H&S | A number of Butane / Propane Gas bottles stored at various locations around the depot | A lockable cage should be purchased to store all gas bottles when not in use and key held by responsible person | Ongoing | Laura White | N/A
87 | 2017-10-12 | Lambs Lane | H&S | Some cleaning materials were in various open locations around the site. | A lockable cupboard should be purchased to store all potentially hazardous material when not in use and key held by responsible person | Ongoing | Laura White | N/A
88 | 2017-10-12 | Lambs Lane | H&S | All depot fire extinguishers were stored on the floor and labels were illegible | Fire extinguisher whilst conducted some of the labels have become un readable and the extinguishers should ideally be stored off the floor and on a wall with signage to indicate their location and use. | Ongoing | Laura White | N/A
89 | 2017-10-12 | Lambs Lane | H&S | At present there is only one trained first aiders. Additional person needs to be trained to provide cover | Arrange first aid training for another site employee - course booked for Dave in Nov 17 | Following move to Bennetts Yard now sufficient First Aiders on site | Laura White | 2017-10-01
91 | 2017-10-12 | Lambs Lane | H&S | No record of legionella test conducted on shower in canteen area | Competent person to conduct legionella test and ensure conducted at regular intervals | Ongoing | Laura White | N/A
92 | 2017-10-12 | Lambs Lane | H&S | Road markings / designated walkways / staff parking area were worn and need to be re painted | RE paint all defined walkways | Ongoing | Laura White | 2018-07-31
93 | 2017-10-12 | Lambs Lane | H&S | Main depot gate was unsecured and moves in the wind and could hit either employees or vehicles entering the site | Ensure gate is secured | Ongoing | Laura White | N/A
94 | 2017-10-12 | Lambs Lane | H&S | Part of Warehouse roof was hanging off and could hit employees who use the walkway to access back yard area | Remove loose material and ensure roof secure | Ongoing | Laura White | N/A
95 | 2017-10-12 | Oakley | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals details on notice boards | A copy of the A1 H&S Policy needs to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details | Ongoing | Ivor Swatton | 2019-03-01
97 | 2017-10-12 | Oakley | H&S | A smoking area needs to be devised away from main building (minimum 4 mtrs) and not close to flammable materials. | Remind employees to smoke in designated areas only. | Completed and smoking now outside main gate | Ivor Swatton | 2017-10-01
98 | 2017-10-12 | Oakley | H&S | Some depot fire extinguishers were stored on the floor, out of date and in some places wall brackets were missing extinguishers. Annual checks need to be set in place with a local company | Fire extinguisher tests whilst conducted some of the labels have become un readable and the extinguishers should ideally be stored off the floor and on a wall with signage to indicate their location and use. | External fire compnay has completed Fire Extingushers tests | Ivor Swatton | 2017-11-01
99 | 2017-10-12 | Oakley | H&S | There will need to be at minimum two trained first aiders on site. | Picture and contact details of First Aiders at Depot | Booked in for April | Ivor Swatton | 2017-11-01
100 | 2017-10-12 | Oakley | H&S | No smoke detectors in Kitchen | Install smoke detectors in office / kitchen area | Purchased and installed | Ivor Swatton | 2017-11-01
101 | 2017-10-12 | Oakley | H&S | Doors leading outside that open outwards will need to be secured or closed as they can move in the wind and could hit employees | Ensure doors are secured at all times or closed and place sign to remind employees to check at all times Two main gates to site need to be locked in place when open to prevent movement | Completed and all doors open inwards | Ivor Swatton | 2017-11-01
102 | 2017-10-12 | Oakley | H&S | Need to ensure all hoses area hung up when not in use as could be trip hazards / Ensure all employees working in this area are wearing appropriate PPE | Tidy area / store hoses and all employees to wear PPE at all times. Consider cordoning off area to prevent water entering other areas | Completed and hooks purchased to hang hoses when not in use | Ivor Swatton | 2017-11-01
103 | 2017-10-12 | Oakley | H&S | No salt and grit for site to be used in freezing conditions | Purchase salt and grit bin and place outside Workshop. To be used in freezing conditions in yard area. | Looking to purchase salt and grit bin in April | Ivor Swatton | 2018-05-01
106 | 2017-10-12 | Oakley | H&S | Workshop pit | Ensure Workshop pit is covered when not in use and signage is in place to warn employees and visitors of open pit | Pit now covered when not in use and signage displayed to warn employees of possible dangers | Ivor Swatton | 2017-10-01
109 | 2018-11-28 | Wokingham | H&S | H&S Policy to be displayed around site on notice boards | A copy of the A1 H&S Policy needs to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details | Ongoing | Chloe Djemal | DONE
110 | 2018-11-28 | Wokingham | H&S | General house keeping | Introduce Iaditor App by end of March | Ongoing | All | DONE
111 | 2018-11-28 | Wokingham | H&S | Flammable liquids | Purchase lockable cabinet for cleaning products | Ongoing | Garry Webb | DONE BY GARRY
112 | 2018-11-28 | Wokingham | H&S | Smoking Area | Remind employees to smoke in designated areas only. | Ongoing | Chloe Djemal | DONE
113 | 2018-11-28 | Wokingham | H&S | Fire Extinguishers | Ideally be stored off the floor and on a wall with signage to indicate their location and use. | Ongoing | Garry Webb | DONE AND ON AUDIT TO MAINTAIN
114 | 2018-11-28 | Wokingham | H&S | Fire Evacuation plan | Print of fire evacuation plan and place in Officers / Canteens and Workshops | Ongoing | Sean Whittle | DONE
115 | 2018-11-28 | Wokingham | H&S | Defined Walkways | Repaint all defined walkways | Ongoing | Garry Webb | DONE AND ON AUDIT TO MAINTAIN
116 | 2018-10-17 | Wokingham | H&S | Pedestrian walkways were segregated from traffic though road markings were no longer clear | Repaint lines around site and refresh walkways | THIS HAS BEEN BOOKED IN FOR THE BEGINNING OF MARCH. | Garry Webb | DONE AND ON AUDIT TO MAINTAIN
117 | 2018-10-17 | Wokingham | H&S | Full and empty gas cylinders were segregated and stored correctly apart from an old unidentified BOC gas cylinder between the non-ferrous metals buildings | Store gas cylinders separately | THESE HAVE NOW BEEN REMOVED. OPERATIVE PLACED THERE WITH NO INSTRUCTION TO. INSPECTIONS TO TAKE PLACE GOING FORWARD TO IDENTIFY WHEN THIS HAPPENS AGAIN. | Garry Webb | 2017-10-01
118 | 2018-10-17 | Wokingham | H&S | There was evidence of spillage on site (oily substance leaking from skip outside non-ferrous metals building) and granules had been applied but not removed | Purchase pill kits and train operatives in their use | SPILLAGE WAS CLEARED AND PERMANENT SPILL KITS PLACED IN THAT AREA. | Garry Webb | 2017-10-01
119 | 2018-10-17 | Wokingham | H&S | In the vehicle storage, yard the fencing surrounding the interceptor had been damaged (possibly by vehicle collision) and, as a result, protruding metal supports present a health and safety hazard | Replace damaged fence | REPLACEMENT FENCE FITTED ON DAY OF AUDIT. INSPECTIONS TO TAKE PLACE GOING FORWARD TO MONITOR THIS. | Garry Webb | 2017-10-01
120 | 2018-10-17 | Wokingham | H&S | Bunding beneath the diesel pump in the ‘loo-hire’ yard area was full and the main spill kit bin was found to be empty - GM | Arragne to be emptied on regular basis and replace spill kit | THIS WAS EMPTIED BY WET WASTE, A WEEKLY EMPTY TIMETABLE HAS BEEN IMPLEMENTED. SPILL KITS WERE REPLACED. INSPECTIONS TO TAKE PLACE GOING FORWARD TO IDENTIFY WHEN THIS HAPPENS AGAIN. | Garry Webb/Michael Pike | 2017-10-01
121 | 2018-10-17 | Wokingham | H&S | At the bottom of the yard a gulley which traps excess rainwater for pumping and disposal appeared vey oily and contamination of surrounding land looked possible in extreme weather conditions. At the end of the gulley was a rusting tank (‘Selwood No.20177) full of water/sludge with no proper lid. Piping from the tank passed through the fence to a storage area where wood pallets and metal radiators were stored. The pipe was left open to the air but was held at such a height that no liquid was escaping | Arrange to have gully cleaned and monitor regularly on weekly walkaround | GULLEY WAS CLEANED. GULLEY TO LAND SEGREGATION WAS COMPLETED TO PREVENT SPILLAGE ONTO THE LAND. RUSTING TANK HAS BEEN REMOVED | Garry Webb | 2017-10-01
122 | 2018-10-17 | Wokingham | H&S | It was noted that the water tank located in the loo hire washing station was leaking. It was noted that the metal frame holding the tank could be prone to rust as a result of this, posing a threat to the strength/stability of the structure (tank above head height) – WB | Replace tank | TANK WAS REPLACED | Garry Webb | 2017-10-01
123 | 2018-10-17 | Wokingham | H&S | 3 x 5L bottles of safeshield were observed on the floor in the loo cleaning area - WB | Purchase lockable cabinet for cleaning products | THE PRODUCT COSHH INFROMATION WAS REVIEWED; THIS WAS CONSIDERED TO NOT BE A PROBLEM. THEY WERE IN USE AT THE TIME AND ARE PUT AWAY OF A NIGHT | Garry Webb | 2017-10-01
124 | 2018-10-17 | Wokingham | H&S | The Company’s weekly check sheet do not document site inspections or audits in detail and operate more as a tick sheet exercise, it may benefit the company to review this process to ensure areas are reviewed in greater detail - DOS | Purchase I Auditor and IPAD and train Managers to undertake weekly walkarounds/ produce weekly report and share with employees | INSPECTIONS TO TAKE PLACE GOING FORWARD TO ON A WEEKLY BASIS BY SENIOR MANAGEMENT TEAM. | Garry Webb | DONE
126 | 2018-10-17 | Wokingham | H&S | It may benefit the company to ensure preventive actions, records of further training and any communications relating to accidents/incidents/near misses are fully recorded | Add section on Actions to H&S meetings | DISCUSSED AND MINUTED AT THE MEETINGS; THESE ARE NOW MONTHLY. TO BE DISCUSSED AT THE NEXT MEETING FOR CLARIFICATION | Garry Webb | ONGOING
127 | 2018-10-17 | Wokingham | H&S | It was noted that there was a leak on the bund near the engine export storage, with oil leaking onto pavement – WB | Repair bund | CURRENTLY BEING LOOKED AT AND UNDER REVIEW. | Garry Webb | DONE
128 | 2018-10-17 | Wokingham | H&S | it was noted that there was a fire point signage on the outside of the strip out area/workshop. There were no extinguishers/fire fighting equipment evident | Devise Fire Extingusher map for site so can be used when auditing and being tested and replaced | FIRE EXTINGUISHERS ARE ALL BEING REVIWED AND PLANS DRAWN UP. | Clive Owen | DONE
129 | 2018-10-17 | Wokingham | H&S | it was noted that there are panels hanging off various workshops/areas (non ferrous sheds) and there is also a makeshift drip pipe hanging down which could pose a potential fall hazard | Replace panels | ALL WERE IMMEDIATELY RECTIFIED. | Garry Webb | 2017-10-01
130 | 2018-10-17 | Wokingham | H&S | It was noted that there is no fire fighting equipment or spill kits located near the diesel gas oil tank | Purchase fire equipment and spill kits (see point 125) | SPILL KIT PLACEMENT AND FIRE PREVETNION PLAN HAVE BEEN REVIEWED. FIRE EXTINGUISHERS ARE ALL BEING REVIWED AND PLANS DRAWN UP. | Garry Webb | 2018-12-01
131 | 2018-10-17 | Wokingham | H&S | As part of the site walk, it was noted that there are areas of surface water/oily sludge in located at the bottom of the yard. This could pose a slip hazard | Purchase I Auditor and IPAD and train Managers to undertake weekly walkarounds/ produce weekly report and share with employees | THIS AREA IS CONTINIOUSLY MONITORED AS PART OF THE EA AUDIT, GULLEY AND DRAINAGE SYSTEM IN PLACE IS CLASSED AS MORE THAN ADEQUATE CONSIDERING THE SCALE OF THE OPERATION IN THE AREA. | Garry Webb | 2018-12-01
132 | 2018-10-17 | Wokingham | H&S | there were two unidentified drums of oily sludge/water located by the gas oil tank | Remove drums | IDENTIFIED, REMOVED AND DISPOSED. | Garry Webb | 2017-10-01
133 | 2018-10-17 | Wokingham | H&S | The manhole cover for the pipe leading into the interceptor was open at all times - WB | Close manhole | MAN HOLE CLOSED AT THE SAME TIME AS DEALING WITH THE FENCE NOTED IN 4. | Garry Webb | 2017-10-01
134 | 2018-10-17 | Wokingham | H&S | extra drip trays could be used in the strip out area where spill granules had been used on a regular basis to soak up oil spills/residue – WB | Purchase extra drip trays | THESE HAVE BEEN PURCHASED AND IMPLEMENTED | Garry Webb | 2017-10-01
135 | 2018-10-17 | Wokingham | H&S | a review of areas that require bunds is required | Purchase new bunds | THESE HAVE BEEN PURCHASED AND IMPLEMENTED | Garry Webb | 2017-10-01
136 | 2018-10-17 | Wokingham | H&S | ladder between the non-ferrous metals buildings was not identified and had no indication of inspection. The same was found for a ‘Youngman’ step ladder in the building adjacent to the ‘loo-hire’ cleaning area. Ladders/steps no. 20420 referenced an inspection tag of Feb 17 with and expiry date of Aug 17. There was no evidence that this set of ladders had been inspected in line with the planned schedule. THESE LADDERS COME INTO THE SITE IN SCRAP VANS AND ARE REMOVED FROM THESE | When ladders are brough on site dispose of immediately - CO to disucss with GW | THESE LADDERS COME INTO THE SITE IN SCRAP CARS AND ARE REMOVED FROM THESE PENDING DISPOSAL SO ARE STORED ON SITE WAITING DISPOSAL. THERE IS NO NEED FOR LADDERS ON SITE BUT WE NEED TO GET INTO A HABIT OF TRAINIGN STAFF TO REMOVE AND DESTROY THESE GOING FORWARD. | Garry Webb | done
137 | 2018-10-17 | Wokingham | H&S | Spill kits were observed by the fuel pump near the crusher and in the welding shed, but there was no clear signage or spill kit provision in other areas. 20 NEW SPILL KITS WERE ORDERED TO DEAL WITH ANY SPILLAGES AND ARE IN PLACE. | Purchase new spill kits | 20 NEW SPILL KITS / BINS WERE ORDERED TO DEAL WITH ANY SPILLAGES AND ARE IN PLACE. | Garry Webb | 2017-10-01
138 | 2018-10-17 | Wokingham | H&S | The Company have not provided suitable receptacles for the disposal of sanitary waste, this is in breach of the Statutory Instrument 1992 No.3004 and Workplace (Health, Safety and Welfare) Regulations 1992 regulation 20 and 21. THIS IS STILL UNDERWAY; TRYING TO SOURCE A LOCAL SUPPLIER FOR THIS. | Purchase sanitary waste recepticles and place in ladies toilets | THIS IS STILL UNDERWAY; TRYING TO SOURCE A LOCAL SUPPLIER FOR THIS. | Garry Webb | DONE
139 | 2018-10-17 | Wokingham | H&S | October 2017 follow up from minor non-conformance raised in surveillance 4 audit Feb 2017– fire extinguishers in the non- ferrous sheds were inspected as part of the site walk. It was noted that the extinguishers in this area (as well as other areas) showed last service dates of 2015/2016 and had not been serviced in line with legal/regulatory requirements over this period. This issue has been raised to a major non-conformance issue. SITE MAP TO BE PRINTED; MAP OF FIRE EXTINGUISHERS TO BE PUT TOGETHER AND EXTINGUISHERS NUMBERED IN AN ATTEMPT TO PRVEENT THIS FROM HAPPENING AGAIN. | Devise Fire Extingusher map for site so can be used when auditing and being tested and replaced | SITE MAP TO BE PRINTED; MAP OF FIRE EXTINGUISHERS TO BE PUT TOGETHER AND EXTINGUISHERS NUMBERED IN AN ATTEMPT TO PRVEENT THIS FROM HAPPENING AGAIN. | Garry Webb | DONE
140 | 2018-03-15 | Wokingham | H&S | Access to the eye wash station in the maintenance area was partially blocked. The company should ensure this remains clear and accessible (Resolved during audit) | Clear itesm t oallow access to eye wash | Ensure all eye wash and first aid points are not blocked | Clive Owen | Closed 15/3
141 | 2018-03-15 | Wokingham | H&S | The issues raised at the H&S audits are managed using the Company Improvement log, it would be beneficial to discard the Action Plan sheet as this is not being used. | Remove individual depot reports from Back Office | Going forward just send individual reports to Depot Managers and all actions to be placed on Action improvement log | Sean Whittle | Closed 15/3
142 | 2018-03-15 | Wokingham | H&S | The company would benefit from installing a spill kit on the site as a precautionary measure. | Purchase spill kit | GW to arrange for spill kit to be placed on site | Garry Webb | DONE
143 | 2018-03-15 | Wokingham | H&S | The company would benefit from updating the fire risk assessment for the site ensuring it incorporates the new loo hire offices. | Include new offices on Fire Risk Assessment | Sean Whittle to update FRA | Sean Whittle | 2018-11-01
144 | 2018-03-15 | Wokingham | H&S | The business would benefit from reviewing their aspects and impacts register to ensure it takes into account the Wet Waste and Loo Hire site. | CO to review aspects and impact register | SW/CO to complete Risk Register for Loo Hire and Wet Waste | Sean Whittle | Closed 21/8
145 | 2018-03-15 | Wokingham | H&S | It was noted that some of the vehicles in the yard area were displaying the incorrect logos for their certification. Eg. Vehicle Reg No. POO2JET had the ISOQAR Logo with UKAS Tick on, which is not permitted. | Immediately removed from a further 10 vehicles. Going forward A1 Group valeting team, who wash all vehicles weekly, have had the instruction to remove this decal from all other vehicles when washing. | Ensure all accreditation stickers are apporved before palcing on any compnay vehicles | Clive Owen | 2018-12-01
146 | 2018-11-06 | Wokingham | H&S | 4 gas bottled in Non Ferrous area not locked away | Ensure all lose gas bottles are placed in lockable cage |  | Garry Webb | 2018-12-01
147 | 2018-11-05 | Wokingham | H&S | A smoking area needs to be devised away from main building (minimum 4 mtrs) and not close to flammable materials. | Remind all visistors and employees to smoke in designated areas |  | Garry Webb | 2018-12-01
148 | 2018-11-06 | Wokingham | H&S | One fire extinguisher stored on the floor. | Ensure Fire Extingusher is placed on wall hook |  | Garry Webb | 2018-12-01
149 | 2018-11-06 | Wokingham | H&S | Some walkways become worn/New walkway to be identified from reception to Car Spares office / tyre bay | Organise for all lines to be cleaned and repainted where necessary |  | Garry Webb | 2018-12-01
150 | 2018-11-06 | Wokingham | H&S | Ladder in Car Spares yard but depollution area and leant on wall | Secure Ladder to wall whn not in use |  | Garry Webb | 2018-09-01
151 | 2018-11-01 | Bennets Yard | H&S | Limited H&S documentation was visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals’ details on notice boards | Create separate H&S Board and display signed H&S Policy, insurance details Pictures and contact details for both first aiders and fire marshals Speed limit signs on main entrance and arounds site Reception signage Visitor sign in book in Loo Hire office Site H&S leaflet handed to all visitors |  | Paul James | 2018-11-01
152 | 2018-11-01 | Bennets Yard | H&S | No Fire Alarm operational | Ensure operational Fire Alarm in place and employees undertake fire Evacuation |  | Paul James | 2018-11-01
153 | 2018-11-01 | Bennets Yard | H&S | The canteen near the Offices has no PAT testing completed | Engage external PAT testing competent person |  | Paul James | 2018-11-01
154 | 2018-11-01 | Bennets Yard | H&S | Fire signage evacuation process and site should be visible in canteen and general office. | Devise site visitor booklet Devise sign evacuation posted with exit routes |  | All | 2018-11-01
155 | 2018-11-01 | Bennets Yard | H&S | There was no signage at the main entrance to the site warning visitors or customers of the hazards that may be present or requesting they wear PPE | Contact signage company to conduct audit of site and supply and erect signage |  | Chloe Djemal | 2018-11-01
156 | 2018-11-01 | Bennets Yard | H&S | There was no signage at the main entrance to the site warning visitors or customers of site speed limit | Order new main sign for Depot |  | Chloe Djemal | 2018-11-01
157 | 2018-11-01 | Bennets Yard | H&S | Smoking Area | Smoking area needs relocating on site and ashtray purchased to dispose of cigarette ends. No smoking signage needs to be purchased and placed at various locations on site |  | Paul James | 2018-11-01
158 | 2018-11-01 | Bennets Yard | H&S | Gas bottled in various locations around site | Purchase two gas cages – indicate full and empty and ensure locked at all times when not in use |  | Paul James | 2018-11-01
161 | 2018-11-01 | Bennets Yard | H&S | Air conditioning unit at time of audit was covered in leaves and could be potential fire hazard | As part of IAuditor weekly walkaround ensure Air conditioning unit if free from potential fire risks i.e. Leaves |  | Laura White | 2018-11-01
164 | 2018-11-07 | Bridgend | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals’ details on notice boards | A copy of the A1 H&S Policy need to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details |  | Spencer Morgan | 2018-11-01
165 | 2018-11-07 | Bridgend | H&S | Employees leave clothing/ materials scrap rubbish / equipment / hoses / leads etc around site which can create trip hazards etc | Daily H&S walk around. Remind employees of H&S responsibilities and what action to take. |  | Spencer Morgan | 2018-11-01
166 | 2018-11-07 | Bridgend | H&S | PAT testing not present on any electrical equipment on site | Competent person to conduct PAT testing on all electrical equipment |  | Spencer Morgan | 2018-11-01
167 | 2018-11-07 | Bridgend | H&S | A number of flammable products in workshop and cleaning equipment in drying room were not stored correctly | A lockable cupboard should be purchased to store all flammable liquids and cleaning products when not in use and key held by responsible person |  | Spencer Morgan | 2018-11-01
168 | 2018-11-07 | Bridgend | H&S | Some cleaning materials were in various open locations around the site. | A lockable cupboard should be purchased to store all potentially hazardous material when not in use and key held by responsible person |  | Spencer Morgan | 2018-11-01
169 | 2018-11-07 | Bridgend | H&S | Some depot fire extinguishers were stored on the floor | Fire extinguisher tests whilst conducted some of the extinguishers should ideally be stored off the floor and on a wall with signage to indicate their location and use. |  | Spencer Morgan | 2018-11-01
171 | 2018-11-07 | Bridgend | H&S | Road markings / designated walkways / staff parking area were beginning to ware and need to be re painted | RE paint all defined walkways |  | Spencer Morgan | 2018-11-01
172 | 2018-11-07 | Bridgend | H&S | Boxes on top of floor of mezzanine | To be moved to shelving and archive area |  | Spencer Morgan | 2018-11-01
173 | 2018-10-30 | Coventry | H&S | No H&S policies posters were visible on notice boards or around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals’ details on notice boards | A copy of the A1 H&S Policy need to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details |  | Casey Owen | 2018-11-01
174 | 2018-10-30 | Coventry | H&S | A number of flammable products in workshop and cleaning equipment in drying room were not stored correctly | A lockable cupboard should be purchased to store all flammable liquids and cleaning products when not in use and key held by responsible person |  | Casey Owen | 2018-11-01
175 | 2018-10-30 | Coventry | H&S | Smoking area is immediately outside staff canteen but employee smoke outside main office. | Move smoking area and remind employees to smoke in designated areas only. |  | Casey Owen | 2018-11-01
176 | 2018-10-30 | Coventry | H&S | Some cleaning materials were in various open locations around the site. | A lockable cupboard should be purchased to store all potentially hazardous material when not in use and key held by responsible person |  | Casey Owen | 2018-11-01
177 | 2018-10-30 | Coventry | H&S | No Fire Evacuation procedures visible around site | Print of fire evacuation plan and place in Officers / Canteens and Workshop / Warehouse’s |  | Casey Owen | 2018-11-01
178 | 2018-10-30 | Coventry | H&S | Side door to yard area was unsecured and moves in the wind and could hit either employees exiting Workshop | Ensure gate is secured at all times or closed and place sign to remind employees to check at all times |  | Casey Owen | 2018-11-01
179 | 2018-10-30 | Coventry | H&S | Whilst area was tidy / hoses could be trip hazards / ensure wearing PPE including goggles | Store hoses and all employees to wear PPE at all times. Consider cordoning off area to prevent water entering other areas |  | Casey Owen | 2018-11-01
180 | 2018-10-30 | Coventry | H&S | No salt and grit for site to be used in freezing conditions | Purchase salt and grit bin and place outside Workshop. To be used in freezing conditions in yard areas. |  | Casey Owen | 2018-11-01
181 | 2018-10-30 | Coventry | H&S | No equipment appeared to have been PAT tested | Ensure all items over 1 year old are PAT tested – this could be completed internally by competent person |  | Casey Owen | 2018-11-01
182 | 2018-10-30 | Coventry | H&S | No record of Compressor being serviced | Arrange for Compressor in storage unit at back of yard to be serviced by competent person |  | Casey Owen | 2018-11-01
184 | 2019-03-06 | Oakley | H&S | No Fire Alarm present on site | Purchase manual Fire Alarm bell and communicate to all employees |  | Ivor Swatton | 2018-12-01
192 | 2018-11-13 | Oakley | H&S | No salt and grit for site to be used in freezing conditions | Purchase salt and grit bin and place outside Workshop. To be used in freezing conditions in yard area. |  | Ivor Swatton | 2018-12-01
193 | 2018-11-13 | Oakley | H&S | There are security bars on all workshop windows but not on windows to general office and there is low level wall without security barbed wire. | Extend the barbed wire along the outside wall of the site to prevent access over the wall. Consider bars on the 4 windows to the office and a metal roller shutter to close off the general office at night. |  | Ivor Swatton | 2018-12-01
196 | 2019-10-02 | All | H&S | Introduce IAuditor Across all sites | Will assisrt with day to day H&S |  | Chloe Djemal | closed March 2019
197 | 2019-10-02 | All | H&S | Enusre H&S Boards updated at all sites | Inform employees of H&S issues |  | Chloe Djemal | closed March 2019
201 | 2019-10-02 | Wokingham | H&S | Fire Evacuation plan - review and update where necessry | Ensure compliant |  | Sean Whittle | 2019-01-01
203 | 2019-10-02 | All | H&S | Review all RAMS for the Group | Ensure compliant |  | Sean Whittle | 2019-01-01
204 | 2019-02-05 | Wokingham | H&S | Noise Assessments for Wokingham | Ensure compliant |  | Clive Owen | 2019-03-01
200 | 2019-10-02 | All | H&S | Manual Handling Training for all employees of the Group | Ensure compliant | Ensure that all manual handling is reviewed on annual basis by competent Trainer | Alan McGregor | 2019-08-06
4 | 2015-10-26 | Wokingham | H&S | Review of storage requirements for the equipment maintenance records | Moved from workshop to spare office in meeting room | Ongoing | Clive Owen | closed
83 | 2017-10-12 | Lambs Lane | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals details on notice boards | A copy of the A1 H&S Policy need to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals with contact details | Ongoing | Laura White | Moved site in January 2018 - Actions now transerred to Bennetts Yard
84 | 2017-10-12 | Lambs Lane | H&S | Signage around site was good but additional review should be undertaken for entrance visitor information | A number of signs would assist in reminding employees and visitors of the site H&S procedures. | Ongoing | Laura White | Moved site in January 2018 - Actions now transerred to Bennetts Yard
86 | 2017-10-12 | Lambs Lane | H&S | Smoking area is immediately outside staff canteen but employee smoke outside main office. | Remind employees to smoke in designated areas only. | Same problem at Bennetts needs to be moved | Laura White | Moved site in January 2018 - Actions now transerred to Bennetts Yard
90 | 2017-10-12 | Lambs Lane | H&S | PAT testing not present on any electrical equipment on site | Competent person to conduct PAT testing on all electrical equipment | Ongoing | Laura White | Moved site in January 2018 - Actions now transerred to Bennetts Yard
96 | 2017-10-12 | Oakley | H&S | A number of Butane / Propane Gas bottles stored at various locations around the depot Some cleaning materials were in various open locations around the site. | A lockable cage should be purchased to store gas cylinders in when not in use and key held by responsible person | Ongoing | Martin Kirkham | 2019-05-01
107 | 2017-10-12 | Oakley | H&S | Fire Evacuation warning signage | Consider emergency lighting and warning lights above all exits | Ongoing | Martin Kirkham | 2019-05-01
108 | 2017-10-12 | Oakley | H&S | Site signage review | Consider all site signage and where it is currently placed. Some signage is hidden and will need to be relocated when site operational. | Ongoing | Martin Kirkham | 2019-05-01
160 | 2018-11-01 | Bennets Yard | H&S | Ensure Fire Exit from Loo Hire office not blocked | Construct two steps from both Fire Exits in Loo Hire Offices as the drop currently is too high to exit safely | Add to the Weekly IAuditor walkaround check | Laura White | 2018-11-01
162 | 2018-11-02 | Bennets Yard | H&S | Ladder in workshop not stored correctly | Ensure ladder is fixed to wall when not in use | Ensure all ladders are chained to wall if not in use and all have beeen checked prior to use | Paul James | 2018-11-01
183 | 2019-03-06 | Oakley | H&S | No H&S policies posters were visible on notice boards around site. Employees not therefore reminded of H&S responsibilities. No first aider / fire marshals’ details on notice boards | A copy of the A1 H&S Policy needs to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals (when trained) with contact details | Review all H&S Documentation on annual basis and all policies and documents requiring signature must be signed and displayed on notice boards | Ivor Swatton | 2019-03-01
188 | 2019-03-06 | Oakley | H&S | Flammable liquids | A lockable cupboard should be purchased to store aerosols and flammable products when not in use and key held by responsible person | Ensure all liquids are palced in cupboard and add to IAuditor Walkround | Ivor Swatton | 2019-03-01
190 | 2019-03-06 | Oakley | H&S | First Aiders | Arrange for at least one employee to be first aid trained - picture and contact details of First Aiders at Depot | Have First Aider picture on H&S notice baoards and report any leavers and replace or train new employee to undertake first aide duties | Ivor Swatton | 2019-03-01
191 | 2019-03-06 | Oakley | H&S | Fire Evacuation plan | Print of fire evacuation plan and place in Officers / Canteens and Workshop / Warehouse | Review on monthly basis prior to H&S Meeting | Ivor Swatton | 2019-03-01
194 | 2019-03-06 | Oakley | H&S | Yard lighting - bottom of yard house employee caravan – no lighting | Consider lighting at bottom of yard area to be used in winter months | Invesigate possibility on permanent lighting from main office | Ivor Swatton | 2019-03-01
195 | 2019-03-06 | Oakley | H&S | Site signage - fork lift in operation | Consider additional site signage including Fork Lift operational and where it is currently placed | Review on weekly basis that all signage is in place and report any missing using Iauditir reporting function | Ivor Swatton | 2019-03-01
203 | 2019-03-14 | Wokingham | H&S | No Risk Assesment of Granulator | Ensure all Opertors read prior to Operating Machine | Ensure part of Opertice induction programme | Sean Whittle | 2019-03-14
206 | 2019-03-14 | All | H&S | further information on Action Improvement Log | Provide further information in the corrective / preventive action columns on the Action Improvement Log | Enusre this is reviewed on 6 month basis | Sean Whittle | 2019-03-14
213 | 2019-05-07 | All | H&S | PAT Tests | Ensure we complete PAT testing at all depots | Ensure process occurs annually | Chloe Djemal | 2019-07-01
221 | 2020-10-01 | Wokingham | H&S | Revise the Accident reporting Procedure | Ensure corrective actions are implemented | Ensure this is reviewed at Monthly H&S meeting | Sean Whittle | 2019-10-01
224 | 2020-09-29 | Wokingham | H&S | Review Business Continuity plan | Ensure all up to date | Review on monthly basis | Sean Whittle | 2019-10-01
225 | 2020-09-30 | Wokingham | H&S | Review Legal Register | Ensure all up to date | Review on annual basis | Sean Whittle | 2019-10-01
43 | 2017-07-21 | Wokingham | EAA | Noise Management Plan The current version of the noise management plan is 1.7, dated February 2016. An annual review is due – to be completed by 29 September 2017. | CO to resolve | Ongoing | Clive Owen | 2020-09-01
125 | 2018-10-17 | Wokingham | H&S | It may benefit the company to review the wording on their website, currently indicating them as having “ISO 14001 - 9001 Accreditation and OHSAS 18001 Accreditation ISO | Review Web site | THIS NEEDS TO BE CLARIFIED AS WE WERE UNABLE TO LOCATE ON THE WEBSITE. | Clive Owen | 2020-01-01
163 | 2018-11-03 | Bennets Yard | H&S | DSE training | Ensure all PC users complete annual DSE training / refresher and have system to report issues | Ensure that all DSE training is reviewed on annual basis by competent Trainer | All | 2020-01-01
188 | 2018-03-06 | Oakley | H&S | Flammable liquids | A lockable cupboard should be purchased to store aerosols and flammable products when not in use and key held by responsible person | Ensure all liquids are palced in cupboard and add to IAuditor Walkround | Ivor Swatton | 2019-03-01
189 | 2018-03-06 | Oakley | H&S | A smoking area needs to be devised away from main building (minimum 4 mtrs) and not close to flammable materials. | Move smoking area to 4mtrs away from building and purchase ashtray - remind employees to smoke in designated areas only. | Ensure employees only smoke in designated area | Ivor Swatton | 2020-03-01
198 | 2018-10-02 | All | H&S | Obtain FORS Silver accreditation | Ensure compliant | Ensure progress is reported at monthly H&S meeting and place as agenda item | Alan McGregor | 2020-08-01
199 | 2018-10-02 | All | H&S | DSE traiing for all workstation based employees of the Group | Ensure compliant | Ensure that all DSE training is reviewed on annual basis by competent Trainer | Emily Russell | 2020-01-01
202 | 2018-10-02 | All | H&S | Fire Evacuation plan - roll out across all sites iew and update where necessry | Ensure compliant | Enusre this is reviewed on 6 month basis | Sean Whittle | 2020-01-01
204 | 2019-03-14 | All | H&S | Storage of Gas cyllinders | Tidy up of their gas storage cage to ensure cylinders are stored appropriately | Enusre this is reviewed as part of the weekly H&S walkaround | Chloe Djemal | 2020-01-01
205 | 2019-03-14 | All | H&S | Meeting review dates | Adding a date onto the minutes of their management review meeting | Enusre this is reviewed on 6 month basis | Chloe Djemal | 2020-01-01
207 | 2019-03-14 | All | H&S | Ensure COSHH sheets are availalble on Back Office | Transfer over the updated COSHH assessments from Sypol over to their back-office system. | Enusre this is reviewed on 6 month basis | Clive Owen | 2020-01-01
211 | 2019-04-04 | All | H&S | CSCS Card for Wet Waste employees | To ensure Wet Waste Employees have CSCS card to enable them to access customer sites if requested for CSCS Card | Ensure all new starters attend CSCS course within 6 months of starting with Wet Waste | Chloe Djemal | Discussed and sorted Sept 20
212 | 2019-05-07 | All | H&S | Drug Driving tests | Ensure we take a numbe of random tests every three month of employees | Ensure process occurs every three months | Stuart Cawthorne | 2020-08-01
214 | 2019-05-07 | Wokingham | H&S | Hot Works Assessments | Esnure we complete Hot Works Assessment on weekly walkaround | Ensure Assessment captured on Iauditor walkaround | Sean Whittle | 2020-01-01
222 | 2020-10-01 | All | Alcumus | Emergency lightng test records | Contact electrician to conduct annual tests | Review on annual basis and upload report onto Back Office | Clive Owen | 2020-03-01
223 | 2020-09-28 | All | Alcumus | Invite others to Management review meetings to JC Consultants | Contact A! Group Management to invite to March meeting | Ensure completed 6 monthly | Clive Owen | 2020-03-01
226 | 2020-10-01 | All | Alcumus | Review Spill procedures and organise training | Ensure all relevnt staff trained and up to date | Ensure completed in February 20 | Sean Whittle | 2020-03-01
227 | 2020-10-02 | All | Alcumus | Review COSH Assessments and create COSHH Register | Ensure all up to date | Review on monthly basis | Sean Whittle | 2020-09-01
228 | 2020-10-03 | All | Alcumus | Capture new upstairs floor in Wokingham site office block in all Fire Risk Assesments / Audits | Ensure all up to date | Review on monthly basis | Sean Whittle | 2020-03-01
229 | 2020-10-15 | Bennets Yard | H&S | Move Smoking area | Smoking area needs relocating on site | Review on weekly walkrounds | Paul James / Laura White | 2020-03-01
230 | 2020-10-15 | Bennets Yard | H&S | Gas Bottle storage | We have purchased gas cages so they need to be used | Review on weekly walkrounds | Paul James / Laura White | 2020-03-01
234 | 2020-10-15 | Bennets Yard | H&S | Site signage | Review all site signage – mainly in Garage workshop area and front entrance to site | Review on weekly walkrounds | Paul James / Laura White | 2020-03-01
236 | 2020-10-15 | Bennets Yard | H&S | Illuminiated Fire signage | Ensure these are tested annually by qualified electrician | Review on weekly walkrounds | Paul James / Laura White | 2020-03-01
239 | 2020-10-22 | Bridgend | H&S | Gas Bottle storage | We have purchased gas cages so they need to be used | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
240 | 2020-10-22 | Bridgend | H&S | Fire Exiting Warning signage | Need to repaing warning signage | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
241 | 2020-10-22 | Bridgend | H&S | Wastewater | Repair down pipe to prevent water all over entrance which could freezre in wintery conditions | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
242 | 2020-10-22 | Bridgend | H&S | Git Bin | Purchase more Grit for winter months | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
243 | 2020-10-22 | Bridgend | H&S | Illuminiated Fire signage | Ensure these are tested annually by qualified electrician | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
244 | 2020-10-22 | Bridgend | H&S | Vehicle Hoist | Service required | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
245 | 2020-10-22 | Bridgend | H&S | Fire Assembly area | Cars blocking area and need to move and signage placed to remind employees | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
246 | 2020-10-22 | Bridgend | H&S | Move Smoking area | Smoking area needs relocating on site | Review on weekly walkrounds | Spencer Morgan | 2020-11-01
253 | 2020-10-31 | Wokingham | H&S | Illuminiated Fire signage | Ensure these are tested annually by qualified electrician | Review on weekly walkrounds | Garry Webb | 2020-11-01
254 | 2020-10-31 | Wokingham | H&S | Chains Across car spare isels | Ensure the chain system is operational when a forklift is being used to remove vehicles from racks and ensure Hi Viz clothing worn by all customers | Review on weekly walkrounds | Garry Webb | 2020-11-01
255 | 2020-10-31 | Wokingham | H&S | Fire Extingushers |  | Review on weekly walkrounds | Garry Webb | 2020-11-01
256 | 2020-10-31 | Wokingham | H&S | Ladder storage | Ensure ladders are fixed to wall when not in use and is fit for purpose – dispose pf any that or not | Review on weekly walkrounds | Garry Webb | 2020-11-01
257 | 2020-10-31 | Wokingham | H&S | Hoses and Reels | Place on hooks when not in use | Review on weekly walkrounds | Garry Webb | 2020-11-01
258 | 2020-10-31 | Wokingham | H&S | PPE | Ensure ear defenders are available and worn in area where they are required | Review on weekly walkrounds | Garry Webb | 2020-11-01
247 | 2020-10-23 | Coventry | H&S | Flammable liquids storage | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Casey Owen | 2020-11-01
248 | 2020-10-23 | Coventry | H&S | Cleaning materials | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Casey Owen | 2020-11-01
249 | 2020-10-23 | Coventry | H&S | Pressure Wash Area | Store hoses and all employees to wear PPE at all times. | Review on weekly walkrounds | Casey Owen | 2020-11-01
250 | 2020-10-23 | Coventry | H&S | Grit Bin | Purchase more Grit for winter months | Review on weekly walkrounds | Casey Owen | 2020-11-01
251 | 2020-10-23 | Coventry | H&S | Fire Extingushers | Move equipment so extinguishers can be reached easily in time of emergency. | Review on weekly walkrounds | Casey Owen | 2020-11-01
252 | 2020-10-23 | Coventry | H&S | Ladder storage | Ensure ladders are fixed to wall when not in use and is fit for purpose – dispose pf any that or not | Review on weekly walkrounds | Casey Owen | 2020-11-01
262 | 2020-11-22 | Oakley | H&S | Move Smoking area | Smoking area needs relocating on site | Review on weekly walkrounds | Martyn Kirkham | 2020-11-01
263 | 2020-11-22 | Oakley | H&S | First Aiders | Picture and contact details of First Aiders displayed on notice boards around Depot | Review on weekly walkrounds | Martyn Kirkham | 2020-11-01
264 | 2020-11-22 | Oakley | H&S | Compressor | Arrange for service to be conducted by competent person and record kept and booked from 12 months’ time | Review on weekly walkrounds | Martyn Kirkham | 2020-11-01
269 | 2020-11-22 | Oakley | H&S | Exposed beams on mezzanine floor | Purchase impact protection foam and highlight beams to warn employees | Review on weekly walkrounds | Martyn Kirkham | 2020-11-01
213 | 2019-07-02 | Bennets Yard | H&S | Purchase new Fuel Tanks at Bennetts | LW to purchase tanks | Review fuel storage as part of Iauditor walkaround | Laura White | 2020-11-01
214 | 2019-08-13 | Bennets Yard | H&S | Power supply bottom of Bennetts Yard | CO to look at the power supply where tanks are needed in Bennetts yard | Ongoing review of pwer needs at all sites | Clive Owen | 2020-11-01
215 | 2020-09-25 | All | H&S | COSHH | Ensure all up to date | Review on monthly basis | Sean Whittle | 2020-12-01
216 | 2020-09-25 | Wokingham | H&S | FORS Bronze | Ensure all up to date | Review on monthly basis | Stuart Cawthorne | 2020-09-01
231 | 2020-10-15 | Bennets Yard | H&S | Yard lighting | Erect two portable lighting towers for bottom of yard to be used in winter months – possible solar powered to meet environmental requirements | Review on weekly walkrounds | Paul James / Laura White | 2020-11-01
232 | 2020-10-15 | Bennets Yard | H&S | Ladder storage | Ensure ladders are fixed to wall when not in use and is fit for purpose – dispose pf any that or not | Review on weekly walkrounds | Paul James / Laura White | 2020-10-01
233 | 2020-10-15 | Bennets Yard | H&S | Open Pit in Workshop | consider placing a chain across the entrance the areas at the front of the workshop. Place flooring warning hash block around pit | Review on weekly walkrounds | Paul James / Laura White | 2020-10-01
238 | 2020-10-15 | Bennets Yard | H&S | Trailing Hoses | Purchase more hooks to hang hoses | Review on weekly walkrounds | Paul James / Laura White | 2020-10-01
268 | 2020-11-22 | Oakley | H&S | Ladder storage | Ensure ladders are fixed to wall when not in use and is fit for purpose – dispose pf any that or not | Review on weekly walkrounds | Martyn Kirkham | 2020-10-01
104 | 2017-10-12 | Oakley | H&S | There are security bars on all workshop windows but not on windows to general office and there is low level wall without security barbed wire | Extend the barbed wire along the outside wall of the site to prevent access over the wall. Consider bars on the 4 windows to the office and a metal roller shutter to close off the general office at night. | Ongoing | Martin Kirkham | 2018-12-12
105 | 2017-10-12 | Oakley | H&S | Defined Walkways need devising | Devise a walkway from main building to employee parking area and also to Wash down area | Ongoing | Martin Kirkham | 2018-12-12
187 | 2018-03-06 | Oakley | H&S | Employees tend to leave clothing/ materials scrap rubbish / equipment / hoses / leads etc around site which can create trip hazards etc | Daily H&S walk around – IAuditor being introduced in Dec 2018 | Ensure all general housekeeping is captured on IAuditor weekly check | Ivor Swatton | 2018-12-12
217 | 2020-09-25 | All | H&S | Employee Apprisals | Ensure all up to date | Review on monthly basis | Sean Whittle | 2021
261 | 2020-11-22 | Oakley | H&S | Flammable liquids storage | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
265 | 2020-11-22 | Oakley | H&S | Forklift Truck | Arrange for service to be conducted by competent person and record kept and booked from 12 months’ time | Review on weekly walkrounds | Martyn Kirkham | 2021-01-01
266 | 2020-11-22 | Oakley | H&S | Tyre Stores under stairs | If there was a fire it could burn stairwell no items to be stored under stairs | Review on weekly walkrounds | Martyn Kirkham | 2021-01-01
267 | 2020-11-22 | Oakley | H&S | Grip on stairs | Purchase some grip matting to stick to stairs | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
270 | 2020-12-01 | Oakley | H&S | H&S Documentation | A copy of the A1 H&S Policy needs to be signed and printed and displayed in various locations around the depot. Devise posters of all first aider and fire marshals (when trained) with contact details | Review on weekly walkrounds | Martyn Kirkham | 2021-10-14
273 | 2020-12-01 | Oakley | H&S | General Housekeeping | Ensure weekly check of site conducted and issued disucsed and actioned | Review on weekly walkrounds | Martyn Kirkham | 2021-10-14
274 | 2020-12-01 | Oakley | H&S | Flammable liquids storage | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
276 | 2020-12-01 | Oakley | H&S | Fire Evacuation Plan | Ensure displayed around site | Review on weekly walkrounds | Martyn Kirkham | 2021-10-14
277 | 2020-12-01 | Oakley | H&S | Fire Extingushers | Purchase hooks to store off the ground | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
278 | 2020-12-01 | Oakley | H&S | Workshop Stairs | Ensure grip is purchased to prevent slips | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
279 | 2020-12-01 | Oakley | H&S | Fire Exits Employee Canteen / rear General Office | Review Fiere Exits on site and purchase corect fire excit locks for doors | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
280 | 2020-12-01 | Oakley | H&S | Office lighting | Review office lighting and purchase correct lamls where required | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
281 | 2020-12-01 | Oakley | H&S | Mezzanine Beam | Purchase bump foam and repalce signage | Review on weekly walkrounds | Martyn Kirkham | 2021-08-13
283 | 2020-12-01 | Coventry | H&S | Hoses in Pressure Wash Area | Store hoses correctly and all employees to wear PPE at all times. | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2020-12-12
284 | 2020-12-01 | Coventry | H&S | Fire Extinguhers | Purchase fire extinguisher usage identification labels Purchase door stops | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2020-12-12
285 | 2020-12-01 | Coventry | H&S | Ladder storage | Ensure ladder is secured at all times to wall when not in use and check it is fit for purpose | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2020-12-12
286 | 2020-12-01 | Coventry | H&S | Gas Boiler | Ensure boiler is serviced annually by competent gas engineer and certification of safety obtained | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2020-12-12
287 | 2020-12-01 | Coventry | H&S | Fork Lift Truck service | Ensure forklift truck is serviced annually by competent engineer and certification of safety obtained | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2021-01-01
288 | 2020-12-01 | Coventry | H&S | Compressor Service | Ensure compressor is serviced annually by competent engineer and certification of safety obtained | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2021-01-05
289 | 2020-12-01 | Coventry | H&S | Smoking on site | Ensure the fireproof vessel to discard cigarettes is used and not plastic bucket | Review on weekly walkrounds | Clive Owen / Workshop Supervisor | 2020-12-12
291 | 2020-12-01 | Bridgend | H&S | H&S Documentation | Create specific H&S Notice Board in canteen and ensure documents are in date – they should be checked weekly as part of H&S walk round | Review on weekly walkrounds | Spencer Morgan | 2020-12-14
292 | 2020-12-01 | Bridgend | H&S | Fire Marshals | Ensure we have minimum of 2 Fire Marshals and 2 First aiders at all times on site | Review on weekly walkrounds | Spencer Morgan | 2020-12-14
293 | 2020-12-01 | Bridgend | H&S | Boiler | Boiler needs service to ensure safe for purpose | Review on weekly walkrounds | Spencer Morgan | 2021-01-05
294 | 2020-12-01 | Bridgend | H&S | Ladder storage | Ensure all ladders are stored on site and secured to wall | Review on weekly walkrounds | Spencer Morgan | 2020-12-14
296 | 2020-12-01 | Bridgend | H&S | First Aid Box | This should be secured to wall | Review on weekly walkrounds | Spencer Morgan | 2020-12-14
299 | 2020-12-01 | Bridgend | H&S | Fire Exit out to front of building via Workshop | Consider closing as fire exit in case either door or barred gate locked | Review on weekly walkrounds | Spencer Morgan | 2020-12-14
301 | 2020-12-01 | Bridgend | H&S | Emergency Lighting | Use competent electrical engineer to conduct emergency lighting check and provide fit for purpose certificate | Review on weekly walkrounds | Spencer Morgan | 2021-01-05
303 | 2020-12-01 | Bridgend | H&S | Compressor Service | Arrange to have serviced by competent person and inspection certificate obtained | Review on weekly walkrounds | Spencer Morgan | 2021-01-05
304 | 2020-12-01 | Bridgend | H&S | Fire Assembly Area - Car blocking area | Arrange to relocate to side of building away from the Depot (to the right of the building) | Review on weekly walkrounds | Spencer Morgan | 2021-12-14
308 | 2020-12-01 | Wokingham | H&S | Fire Extingushers | Ideally be stored off the floor and on a wall with signage to indicate their location and use. | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2020-12-14
309 | 2020-12-01 | Wokingham | H&S | Flammable liquids storage | Ideally be stored in lockable area and away from ignition sources | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2020-12-14
310 | 2020-12-01 | Wokingham | H&S | Housekeeping | Ensure employees do not leave rubbish in area used for forklift operations / store butane in cages / replace broken signage – use IAuditor to identify issues weekly | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2020-12-14
311 | 2020-12-01 | Wokingham | H&S | Ladder storage | Secure ladder to wall when not in use | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2020-12-14
313 | 2020-12-01 | Wokingham | H&S | Steps | Get grip covers placed on steps – ensure gritted in cold conditions | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2020-12-14
314 | 2021-04-01 | Wokingham | H&S | Mobile Phone Use in Yard Area | Stop with immeidate effect | Memo to all employees | Car Spares and Yard Manager | 2021-04-21
316 | 2021-06-01 | Wokingham | H&S | Weekly Audits not being completed | ER to discuss with JS | Review at Future H&S meetings | H&S Administrator | 2021-10-14
318 | 2021-11-01 | Wokingham | H&S | Review Car Spares Procedure / Public Access to Yard | SW / RJ Pike | Devise new system wherby public don’t access areas with forklift trucks | SW/ RJ | 2021-11-01
237 | 2020-10-15 | Bennets Yard | H&S | Flammable liquids storage | purchase two lockable flame proof cabinets. | Review on weekly walkrounds | Paul James / Laura White | 2021-12-01
238 | 2020-10-15 | Bennets Yard | H&S | Trailing Hoses | Purchase more hooks to hang hoses | Review on weekly walkrounds | Paul James / Laura White | 2021-12-01
282 | 2020-12-01 | Oakley | H&S | Electrical Fuse Board. Exposed Electrical wires | Replace cover on junction box to enclose exposed wires/ building fuse board covering and place lock on outside so only designated electrical engineer has access | Review on weekly walkrounds | Martyn Kirkham | 2021-12-01
295 | 2020-12-01 | Bridgend | H&S | Cleaning Products | An additional lockable cupboard should be purchased to store all cleaning products when not in use | Review on weekly walkrounds | Spencer Morgan | 2021-12-01
297 | 2020-12-01 | Bridgend | H&S | Gas Bottles | A lockable cage should be installed (there is one on site currently not being used) to store all gas bottled on site – audit current ALL gas bottles and discard empty or damaged ones | Review on weekly walkrounds | Spencer Morgan | 2021-12-01
300 | 2020-12-01 | Bridgend | H&S | Waste Water | Replace pipe and ensure its soaking in drain / ensure sink outlet drain is not blocked | Review on weekly walkrounds | Spencer Morgan | 2021-12-01
312 | 2020-12-01 | Wokingham | H&S | Hoses & Leads | Place back on hooks when not being used | Review on weekly walkrounds | H&S Reps / Yard H&S Montors | 2021-12-01
212 | 2019-07-02 | Wokingham | H&S | Book someone onto WAMATAB Course | CD/RP to discuss with CE | Need to have someone qualified on site | Claire Djemal compelted course in July 22 | 2022-07-01
290 | 2020-12-01 | Bridgend | H&S | Housekeeping - Employees leave rubbish and items of clothing around site which can create trip hazards / health hazards etc | Daily / weekly H&S walk around. remind employees of H&S responsibilities Clear all rubbish of racks and orgnaise Consider introducing IAuditor app to make task easier | Review on weekly walkrounds | Spencer Morgan | April - Sept 22
340 | 2022-01-01 | Portsmouth | H&S | Fire Extingushers left on floor | Ensure all visable and hooked on wall | Review on weekly walkrounds | Matt Doody/James Nicklin | 2022-02-01
341 | 2022-01-01 | Portsmouth | H&S | Some equipment not PAT Tested | Conduct PAT Tests annually | Review on weekly walkrounds | Matt Doody/James Nicklin | 2022-02-01
342 | 2022-01-01 | Portsmouth | H&S | Ladders not secured | Ensure all ladders are secured to fixed point | Review on weekly walkrounds | Matt Doody/James Nicklin | Completed
343 | 2022-01-01 | Portsmouth | H&S | Smoking area to close to building | Relocate at least 4m from building | Review on weekly walkrounds | Matt Doody/James Nicklin | Completed
344 | 2022-01-01 | Portsmouth | H&S | Some site signage missing | Conduct site signage audit | Review on weekly walkrounds | Matt Doody/James Nicklin | 2022-03-01
345 | 2022-01-01 | Portsmouth | H&S | Comms cupboard door missing | Replace Comms cupboard door | Review on weekly walkrounds | Matt Doody/James Nicklin | 2022-01-01
327 | 2022-01-01 | Coventry | H&S | Hoses left on floor - trip hazards | Ensure all hoses are hooked on waal when not in use | Review on weekly walkrounds | Kathryn James | Completed
328 | 2022-01-01 | Coventry | H&S | Fire Extingushers covered | Ensure all visable and hooked on wall | Review at Future H&S meetings | Kathryn James | 2022-01-01
329 | 2022-01-01 | Coventry | H&S | Ladders not secured | Ensure all ladders are secured to fixed point | Review at Future H&S meetings | Kathryn James | 2022-01-01
330 | 2022-01-01 | Coventry | H&S | 2 Fire Assembly points | One Fire Assembly point away from main building | Review at Future H&S meetings | Kathryn James | 2022-01-01
321 | 2022-01-01 | Bridgend | H&S | Need to display names of first aiders and Fire Marshals | Display names on H&S Boards | Review at Future H&S meetings | Depot H&S Reps | 2022-01-01
322 | 2022-01-01 | Bridgend | H&S | Ladders not secured | Ensure all ladders are secured to fixed point | Review at Future H&S meetings | Depot H&S Reps | 2022-01-01
323 | 2022-01-01 | Bridgend | H&S | Fire Exit Writing on floor | Introduce repainting every 6 months or when worn | Review on weekly walkrounds | Spencer Morgan | 2022-01-01
324 | 2022-01-01 | Bridgend | H&S | Speed signs | Place large 5mph speed limit sign on front gates | Review on weekly walkrounds | Spencer Morgan | 2022-02-01
325 | 2022-01-01 | Bridgend | H&S | Fire Assembly point to close to building | Relocate Fire Assembly point away from main building | Review at Future H&S meetings | Depot H&S Reps | 2022-01-01
326 | 2022-01-01 | Bridgend | H&S | Mats in hallway are trip hazard | Remove mats in walkway | Review at Future H&S meetings | Depot H&S Reps | 2022-01-01
Note on D12: Sean Whittle: Either H&S = Health & Safety ISOQAR EAA

## Internal Audits
Internal Audit Log
IA No. | Date Raised | Depot | Details of the Non conformance | Corrective action | Preventive Action | Date Closed
1 | 2019-10-01 | All
2 | 2020-03-01 | All
3 | 2020-12-12 | All
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24